## OMAP_335.e3ac8c79-add2-4053-8a6
Board Quarter 2 Progress report against Annual Plan 2011/12 APPENDIX A
Accountability Title | Accountability Owner |  | Key Achievements in second quarter | Current Concerns | Reasons for variance and Actions Taken | (1)
Strategy - overall key priorities
Overall key priorities 01- Demonstrate year on year improvements in the clinical quality of the services delivered (x-reference to clinical quality milestones for details) - Delivery against FY12 Quality Account; Achieve FY12 CQUIN targets | Director of Nursing & Clinical Governance |  | The priority in the first two quarters has been to set up the process whereby quality targets and objectives from the 2011/12 Quality Account can be monitored and reported to the Board to assist in their statement of Quality Assurance. An initial report was produced for the 1st quarter and the 2nd quarter version is currently being produced in readiness for the November 2011 Trust Board Meeting. | The mechanism to capture the information for some of the targets is not currently being captured. | -
Overall key priorities 02 - Delivery of service development plans achieving improved access and value for money (milestones indicate completion; x-ref to service development and Operational/financial effectiveness Milestones for further detail ) | Chief Operating Officer |  | Project Board for Integration being initiated November 11. Detailed update on progress Q3. | - | -
Overall key priorities 03 - Improve the quality and functionality of the Trust’s estate (x-ref service development and capital programme Milestones for detail) | Director of Strategy and Commercial Development |  | In addition to the major schemes in capital programme an extra £900k has been allocated to improve inpatient environments this year. | Limited capacity of framework contractor delivering smaller capital schemes in Q1 and Q2. | Increased capacity from additional framework contractor agreed with procurement team to be effective during Q3.
Overall Key priority 4 - Delivery of the 2-3 year Improvement and Innovation Programme across the Trust | Chief Operating Officer |  | Advisory board met for first time in Sept and approved a number of new initiatives, all of which have either commenced implementation or are progressing to implementation. Monthly and quarterly performance reporting established. A number of programmes and projects in train, none of which are at risk to delivery at present. |  | -
Overall key priorities 05 - Implementation versions of the RiO Syetem for Mental Health and Community Services - Embedding Rio Use. Upgrade to RiO R1. Upgrade to RiO R2. | Director of Strategy and Commercial Development |  | MH Rio implementation completed. Phase 4 of community health Rio nearing completion. Project Board meeting for Release One 12.10.11. Business case for Release 1 considered by Extended Executive Board 18.10.12. Draft to be presented following updates and due to be presented to the F&I Committee 7.11.11. | The business case covers the 'must do' elements of RiO developments and implementation only. | Amber rating due to the additional investment is yet to be agreed.
Key External Impacts
Management of External impacts. 01. Impact of the economic climate on funding in NHS, Social Care and 3rd Sector. | Director of Finance |  | Continued monitoring and work around downside scenario planning. | - | -
Management of External impacts. 02. Impact of the changes as set out in the Health and Social Care Bill 2011 | Director of Strategy and Commercial Development |  | Meetings held with newly appointed Trust Lawyers to review the impacts of the Health and Social Care Bill. As Bill progresses further analysis and training sessions will be held to fully understand and respond to the impact of the changes. | Health and Social Care Bill discussed in House of Lords 12th and 13th October - awaiting formal outcome | Varience due to unknown timetable and impact.
Management of External impacts. 03. Increase in the prevalence of mental health problems in the community due to the aging population, the recession and returning military personnel | Chief Operating Officer |  | Dementia pathway review scoping in Bucks completed and proposal for full pathway redesign project made to ImPact Board - awaiting decision on funding. | Funding requested of £200k, still no decision from Commissioners to release this. | -
Management of External impacts. 04. Market Testing | Director of Strategy and Commercial Development |  | Market analysis work undertaken as a part of developing strategy document approved at the September Board of Directors meeting. Further analysis to be undertaken as a part of the development of the trusts strategic plan. Approach to strategic framework agreed at Extended Executive on 18th October | - | -
Management of External impacts. 05. Changes to the local NHS landscape e.g. Merging Trusts (opportunities and threats) other providers looking to provide traditional NHS services | Director of Strategy and Commercial Development |  | Changes to the NHS landscape included within Strategy Discussion document paper considered by the Board on 28th 2011.September. Local NHS landscape analysis will be considered within the approach to strategic framework. | Recent confirmation from CCP regarding Oxford Radcliffe Hospitals merging with NOC from 1st November 2011. Impact assessment to be completed by PMO during Q3. | -
Financial Plans: Service developments
Financial Plans: Service developments. 01. Consolidation of all inpatient services in Buckinghamshire on the Manor House site | Director of Strategy and Commercial Development |  | Outline Business Case approved at Board of Directors 28th September 2011. Next milestone is Guaranteed Maximum Price 18th November 2011. Planning permission expected in November 2011. Outline Planning Permission proposals for excess land submitted in October 2011 | New project director appointed 17th October 2011. On target to achieve forecast GMP through value engineering process. | -
Financial Plans: Service developments. 02. Delivery of integrated locality teams delivering care tailored to individual communities. | Chief Operating Officer |  | Project Board for Integration now established. First meeting planned for November. Work programme for integration of older adults pathway commencing work October 2011. | - | -
Financial Plans: Service developments. 03. Re-provision of adolescent inpatient services on the Warneford Hospital site | Director of Strategy and Commercial Development |  | Contract for the Highfield now on site with completion due November 2012 | Contract runnin on time and within budget | -
Financial Plans: Service developments. 04. Bring together Forensic Mental Health services into a two hub/spoke model with consistent pathways | Chief Operating Officer |  | Service Strategic plan has been developed and shared with executives and includes review of pathways. The work to introduce changes to the pathways is now underway and this action has been completed |  | -
Financial Plans: Service developments. 05. Reconfiguration of adult and older adult community teams to improve continuity of service, access and demonstrate value for money | Chief Operating Officer |  | Reconfiguration of Oxon teams has taken place. Proposal for the restructuring of Crisis in Bucks is being developed (paper to be re-submitted 21.10.11). Programme to deliver integration with Community Division has commenced. |  | Mitigation plans are being developed
Financial Plans: Service developments. 06. Integration of specialist inpatient Eating Disorders business, maximising opportunities to develop community services | Chief Operating Officer |  | Successful in bidding for provision of Community and Inpatient Eating Disorder Service for NHS Wiltshire. New Service operational from May 2011. Awaiting possible tender of community ED service for Swindon. | - | -
Financial Plans: Service developments. 07. Delivery of specialist addictions services in a range of community settings | Chief Operating Officer |  | Oxfordshire DAAT successful in bidding to become an Addictions PbR Pilot site. Notice given to all providers of addictions services across Oxfordshire and tendering process begun. Current intentions for the Trust is to tender for the Harm Minimisation and Recovery components of the new Oxfordshire addictions system. Addictions Services will remain within C & F Division until after completion of tendering processes. Notice of termination of contract by Oxford has been received for the addictions service, due to a national pilot changing the structure of the pathway and PBR based contracts. An exec paper was presented covering the issues which concluded that Oxford Health should attempt to win tender for Oxford addictions service. The Bucks addictions service continues to perform well. Due to the risk of the Oxford contract, it was decided to keep the addictions business within the current management arrangements and transfer this over to the Specialised Services division once the tender has been won. successful in Harm Minimisation tender. Unsuccessful at PQQ stage on Recovery. Challenge submitted through procurement route on this. Service view is that we should not bid for Recovery due to: financial risks as full PbR model, the soundness of the model proposed., commissioners will be viewing recovery provision as a conflict of interst for any org providing Harm Min. Paper to Exec Team by 17 October with recommendations. The service will transition over to the Specialised division by Feb 2012. | Destablisation of Oxfordshire Service due to tendering processes. | -
Financial Plans: Service developments. 8. Delivery of a range of accessible psychological service pathways from primary to specialist | Chief Operating Officer |  | Services operational in both Oxfordshire and Buckinghamshire. Oxfordshire work is focusing on development of new service models for Long Term Conditions and Medically Unexplained Symptoms. These are being undertaken in conjunction with Community Health Division as well as Commissioners. Medical Director Exec Sponsor for this work with Community Divisional Director leading. Psychological Services will transfer to Community Division by April 2012. | - | -
Financial Plans. Service Developments. 9. Provision of integrated CAMHS care pathways across Tier 2-4 | Chief Operating Officer |  | Successful in bidding for provision of Tier 2 Mental Health Services in BaNES. Contract to begin in August 2011. Now deliver Tiers 2 -4 in Oxon, Bucks and BaNES with tiers 3 and 4 in Swindon and Wiltshire. Much closer working arrangments with Tier 2 services in Swindon and Wiltshire. Intention to bid to be a pilot site for implementation of CAMHS IAPT. In discussion with Wiltshire commissioners about the Trust taking over provision of Tier 2. Successful CAMHS IAPT bid with Reading University- the Trust will be one of three national pilots (along with London and Manchester). All our counties will be involved and we have accepted Gloucestershire and Bournemouth, Poole and Dorset into our collaborative. Announcement due on 25 October. Highfield build commenced. In discussions with Swindon commissioners re FASS/IPPS - workshop at end of October with presentations from our services to health and social care colleagues in Swindon. Buckinghamshire commissioners have indicated wish to reduce CAMHS investment by 400K in 12./13. Remodelling underway - first workshop held with senior clinicians and managers 5 October. New model to be agreed by December for implementation in Q4. Following discussions commissioners have agreed new contract for 3 years wef 1 April 12. We have informed Ridgeway Partnership NHS Trust that we will not be renewing their contract with us in Buckinghamshire. | - | -
Workforce priorities
Workforce 01 - Achieving sustainable performance against key Workforce KPIs within Divisional and Corporate Directorates. Year on year achievement of: • Sickness rates 3.5% - 2.5% • Turnover 10% average • Use of bank and agency 4%, 3%, 2% • Average staff cost £38K, £35K | Director of Human Resources |  | Sickness absence rates are almost on target at 3.55% and have been at this level for the last quater. Turnover has stabilised at 10.28%. Bank and Agency remains within target with the further use sessional contracts. Continuous monitoring of HR KPIs with performance as at the end of Sept is 2% and 1.2% bank useage, Stability has improved to 86.16% | With the level of organisational change sickness rates may increase. Tis is being closely monitored by the HR Teams. The same could also occur with B/A/S contracts. | -
Workforce 02 - Developing management and leadership capacity for the future. Developed as part of OD planning. | Director of Human Resources |  | The re-designed Management Development Programme (MDP) is being delivered with 28 courses available of 70 dates throughout the year. MBTIhas been used with around 50 managers as part of team development programmes. Additional places have been obtained on SHA organised leadership events. Coaching services continue to be used for individuals. A second cohort of the Talent Pathway Programme has begun. Leadership and management development programmes are being reviewed to align to the revised appraisal system. The draft OD programme which covers leadership and manangement development is completed. | Progress on an integrated Leadership programme is delayed whilst funding and organisational change issues are addressed. HR support for some of the MDP events is constrained by focus on organisational change. | -
Workforce 03 - Succession planning - developed as part of OD planning | Director of Human Resources |  | First cohort of Talent Pathway Programme resulted in identified development needs for individuals. Second cohort scheduled for May-July 2011. As part of the revision to the appraisal system the Board have required that succession planning is built in to the process and is being implemented. CEO has required all executive directors to nominate deputies for operational effectiveness and business continuity. OD planning has identifies the need to m ake leadership/management development more widely available and has been addressd. | This objective needs to be linked closely to be integrated with the OD Plan. Dir HR/OD tom address. | Review of Executive succession planning by RemCom in Autumn 2011. OD plan to support strategy in place by end August 2011
Workforce 04 - Organisational change programme | Director of Human Resources |  | Organisational Design and Development Strategy has been implemented through management re-structure and in line with integration planning. Second phase transformation programme to achieve further integration benefits has been initiated . | Approval of Board still outstanding. Trust Strategic Framework currently being developed | Organisational re-strucutring taking place and is now on track with CIP plans and integration plans.
Workforce 05 - Improving staff satisfaction (Staff Survey) - Continuation of “Effective Team” programme focussing on team work and development - Plan for improving communication between senior management and staff developed and reporting on findings by October 2010. - Working group on appraisal/PDR established March 2010 to report by October 2010 - Year on year improvement in survey results | Director of Human Resources |  | 2010 results received and circulated to Divisional Directors and Board. Poor results for 2010 lhas lead to the following actions:- Dir HR/OD taking lead within the Staff Survey Working Group, Executive walk arounds agreed, membership of SSWG reviewed, identifying quick wins for 2011 and taking longer term view with revised and improved action plan. First meeting of the revised working group has taken place and agreed new action plan. This has subsequently been reviewed and agreed by wider Board. Communications plan for staff survey in place and divisions have taken forward plans locally. 2011 staff survey has been launched. Executive have approved 'Back to the Floor initiative for senior managers. The 'effective teams' initiative has been expanded and brought qwithin the management of the Innovation and Improvement Team. | 2010 results show a deterioration in many of the key findings. There is a likelyhood that 2011 results show little improvement if no immediate action taken. | The staff survey working group has meet and developed a course of action - a small team of people will visit teams within the organisation to hold focus groups to get a better understanding of staff issues and concerns in order that Divisional Directors are addressing issues locally e.g. Forensic local staff survey, Children and Families increasing staff and team leader involvement in planning decision making. Effective Teams initiative being extended by Dir of HR/OD. Revised action plan to be implemented by September 2011
Workforce 06 - Strengthening strategic planning and project management capacity and capabilities - Board workshop in June 2010 to agree strategic direction - Resource requirements managed through the newly established programme office - Monitoring of progress against key strategic milestones through the Transitional Programme Board and OBMH Board. | Director of Human Resources |  | HR Director currently holds the role of Programme Director for the Project Management Office which is to be continued for the next year to continues to monitor key strategic milestones. Programme of skills transfer from original project support to internal management has been achieved. Funding for the PMO has been agreed and the team have provided further support across all projects to maintain benefits performance. | Alignment between 'Strategy ' and OD plannning necessary to ensusure delivery of the medium / long term stategic direction | Dir HR/OD working in close collaboration with Dir of Strategy.
Workforce 07: Workforce strategy. A new Workforce strategy has been agreed to address significant reduction/change to workforce over next 3 years incl: • Introduction of more flexibility in service delivery e.g. changes to working hours • Changes in workforce profile require specific actions e.g. areas where we have an aging workforce. • Changes in roles and introduction of new roles in light of CHO integration | Director of Human Resources |  | New workforce strategy developed as part of business case for Monitor which addresses current CIPs and integration with CHO. Workforce plans to be developed with divisions/Directorates. E-Rostering programme brought forward with implementation from August 2011. Feedback from performance meetings identifying divisional hot spots for HR activity and support e.g. appraisals and mandatory training, staff satisfaction and control of agency costs. Management re-structuring has been implemented in line with integration programme and further cost reductions being identified. Revised template for long term workforce planning being completed for implmentation 3rd quarter. | Workforce strategy needs to tie in with ICT and Estates strategies and this piece of work is still to be undertaken. PMO is developing the aligment of services ICT and estates in line with the CIP programme. | Dir HR/OD taking proposal to CEO re aligment preject and changes to the programme board.
Capital Programmes (including Estate Strategy)
Capital Programmes. 01. Manor House redevelopment – new build 80 beds and community services - Buckinghamshire | Director of Strategy and Commercial Development |  | Outline Business Case approved at Board of Directors 28th September 2011. Next milestone is Guaranteed Maximum Price 18th November 2011. Planning permission expected in November 2011. Outline Planning Permission proposals for excess land submitted in October 2011 | New project director appointed 17th October 2011. On target to achieve forecast GMP through value engineering process. | -
Capital Programmes. 02. Highfield Adolescent inpatient unit re-provision. | Director of Strategy and Commercial Development |  | Contract for the Highfield now on site with completion due November 2012 | Contract running on time and within budget | -
Capital Programmes. 03. Forensic –Phoenix and Windrush (Littlemore, Oxfordshire) subject to delivery of strategic service plan | Director of Strategy and Commercial Development |  | Draft Forensic Service Strategic Plan completed September 2011 and presented to Executive Board. | Prioritisation plan required for Estate usage for clinical service strategies. | Clinical service strategies and estate rationalisation plan to be further developed in Q3.
Capital Programmes. 04. Marlborough House – Improve security and enhance the patient environment - Milton Keynes | Director of Strategy and Commercial Development |  | Perimeter fence complete. Planning Permission for new reception building received. Start on site may be delayed if scheme can be linked to proposed extension to bedrooms; will provide much more economical solution. | - | -
Capital Programmes. 05. CHO Estate Rationalisation – optimisation of community estate | Director of Strategy and Commercial Development |  | Some progress with a few leases under notice not to renew. Cuffas Leas building relocation complete with Isis Business Park due early in 2012. More schemes in pipeline (e.g. Boundary Brook House, Wallingford, Henley etc). Estate rationalisation plan and draft estate strategy to be prodiuced during Q3. | - | -
Capital Programmes. 06. Inpatient wards – improving environmental standards – Littlemore and Warneford (Oxfordshire) | Director of Strategy and Commercial Development |  | In addition to major schemes in capital programme an extra £900k has been allocated to improve inpatient environments this year. Packages being designed and planned to work in phases within live inpatient envirionment. | Limited capacity of framework contractor delivering smaller capital schemes in Q1 and Q2. | Increased capacity from additional framework contractor agreed with procurement team to be effective during Q3.
Capital Programmes. 07. Forensic Womens Enhanced Low Secure (WELS) (Oxfordshire) – extension to existing ward to provide net two additional beds | Director of Strategy and Commercial Development |  | Scheme on site with completion of beds phase scheduled by December 2011. Other phase by March 2012. Approval delayed. Scheme now on target with revised timetable. | - | -
Capital Programmes. 08. Woodlands (Buckinghamshire) – major refurbishment to inpatient ensuite bedrooms. | Director of Strategy and Commercial Development |  | Scheme completed in October. | - | -
Capital Programmes. 09. Other minor schemes/unallocated | Director of Strategy and Commercial Development |  | Range of minor schemes now being picked up, scoped and programme of delivery to be agreed | - | -
Capital Programmes. 10. Estate Capital maintenance – to reduce backlog maintenance, comply with statutory standards, address PEAT findings and infection control. | Director of Strategy and Commercial Development |  | Schemes managed by capital control group substantially on target to deliver by year end. | Limited capacity of framework contractor delivering smaller capital schemes in Q1 and Q2. | Increased capacity from additional framework contractor agreed with procurement team to be effective during Q3.
Capital Programmes. 11. Information technology. The implementation of key initiatives such as: the merger of all former CHO users and infrastructure into the Trust’s network domain; expansion of the number of devices in use, including remote working support where possible; the implementation of a new risk management system (Safeguard); the implementation of a new Patient Level Costing system; the implementation of a new Occupational Health system. | Director of Strategy and Commercial Development |  | Migration of the former CHO IT estate has now been completed. Many 'mop-up' activities will need to occur over the coming months. Safeguard has been implemented. Research and engagement activities regarding remote working are taking place. The IT Steering Group have met and began prioritising the IT work plan for the coming year. | Capacity in the IT Team has been a significant issue over the past six months leading to long waits for problems to be rectified. A strictly controlled prioritised approach will assist with delivery moving forward. | IT steering group to agree prioritisation with input from divisional directors
Clinical Plans
Clinical plans. 01. Reduce towards zero the number of inpatient deaths from suicide | Director of Nursing and clinical governance |  | In 2010/11, there was 1 in patient suicide. There have been no inpatient suicides this year. | Concerns relate to community suicides - see below.
Clinical Plans. 02. Reduce towards zero the number of community deaths of patients in Trust services | Director of Nursing and clinical governance |  | Community suspected suicide figures are: 2009/10: 24, 2010/11: 37, 2011/12 to date: 20 | The suicide figures are based on deaths that appear to be suicides. Not all these have been confirmed as ‘took own life’, or an open verdict by the coroner. With 20 apparent suicides this year already, a projection for the full year is around 40, a year on year rise since the start of the programme. | The LIPS programme has been re-invigorated but is still only active in a hand full of teams. 13 staff attended training this financial year at the NHS Institute. A new project lead has been identified in the Improvement and Innovation team and a new Project Board chaired by the Director of Nursing is due to meet in November 2011. Two showcase wards have been established to share their progress with other wards: Ashurst and Marlborough House (Wiltshire). These two teams have made impressive progress integrating the Productive Ward and LIPS programmes. Intranet resources and detailed dashboard monitoring is under development. All community teams have identified one service improvement aimed at reducing suicide (a CQUIN target). We are looking to provide a large new training cohort by running a local training programme facilitated by the NHS Institute.
Clinical Plans. 03. Reduce to 30 from 34 (the previous target) the number of cases of Clostridium Difficile by March 2012 | Director of Nursing and clinical governance |  | There have been 11 cases of C Diff this year, RCA's completed on all in 2 cases the antimicrobial prescribing was outside the guidelines. Cdiff recovery plan in place | The PCT internal target is 13 and the CQUIN target is 20. if the current level continues te Trust will just be inside the CQUIN target | -
Clinical Plans. 04. Preventing avoidable skin breakdown which can lead to pressure ulcers. 85% of patients will be assessed for pressure ulcer risk factors and preventative measures implemented within 2 days. | Director of Nursing and clinical governance |  | Quarterly documentation audit (30 sets of notes) being carried out to identify compliance with this target. The KPI for this was subsequently set at 75%. The Q1 audit has been completed – out of the 30 sets of notes only 33% of patients had been assessed within the recommended timescale’. Key risk factors were not always addressed or there was no evidence of this in the notes. An action plan is in place to address these issues. Previous audits (pre 2011/12) demonstrated compliance of 78% and 56% respectively. The new risk tool format which will simplify the risk assessment process is expected to improve compliance figures. | Difficulty in measuring some of the aspects of this target. | -
Clinical Plans. 05. 100% of mental health patients on CPA have a current care plan, had care review in the last 6 months; a care coordinator and a risk assessment which has been reviewed in the last 12 months. | Director of Nursing and clinical governance |  | % of records with all 4 elements in place - 79% % with a care co-ordinator identified - 96% % with a current care plan - 89% % with care plan been reviewed in the last 6 months - 86% % with a current Safety/Risk Assessment & Management Plan - 88% | - | Note this is Q1 figures
Clinical Plans. 06. Further reduce the incidence of emergency readmission within 28 days of discharge (2.9% March 2011) by careful discharge planning and assertive follow up. | Director of Nursing and clinical governance |  | There have been no readmissions within this time within our service (up to end of 1st quarter). Plans are agreed and care co-ordinator and other members of team attend meetings prior to admission. All patients are seen within 7 days of discharge and then followed up at least weekly until reviewed at next CPA meeting. | - | Note this is Q1 figures
Clinical Plans.07. To increase to 72% by year end the number of patients who have been receiving care for 9 months or more, that have a baseline and follow-up HoNOS rating. | Director of Nursing and clinical governance |  | 46% as of 31st July 2011 . Quarter 1 and 2 figures not available for this report. To be updated Q3. | - | -
Clinical Plans. 08. Deliver Hospital at Home services for the population of Oxfordshire. | Director of Nursing and clinical governance |  | No information available to date. To be updated Q3 | - | -
Clinical Plans. 09. For the trust to score better than average in the National Patient Survey (community) in the following areas: - Service users knowing who their care coordinator was. - Service users being offered a copy of their care plan. - Service users who have had a care review meeting in the past 12 months - Physical Health of Service users checked - Having a contact number out of hours | Director of Nursing and clinical governance |  | CQC published results of community mental health service user survey in August 2011. Mental health and Children and families divison have agreed action plans - implementing standards (as in B14) for patients not on CPA as well as those that are supported by policy change and clinical audit. | - | -
Clinical Plans. 10. Community services to improve the % of patients who rate their care good, very good or excellent. To achieve results comparable to the national top 20% of acute trusts satisfaction rating for both out-patients and in-patients as no comparable survey for community services. | Director of Nursing and clinical governance |  | In July 2011, 39% of patients rated the service excellent, with 37% rating it good. | - | Note this is Q1 figures
Regulatory requirements
Regulatory requirements. 01. Maintain Monitor Financial Risk rating. | Director of Finance |  | Current forecast above plan - likely to remain on tradjectory this year. | - | -
Regulatory requirements. 02. Maintain Governance risk rating. | Director of Finance |  | We continue to monitor all targets on a monthly basis and utilise performance improvement resources where risks are apparent. | Q2 performance for early intervention against contractual targets and self certification against requirements relating to healthcare for people with Learning Disabilities are at risk. Update to be provided at Trust Board meeting. | Action plans to be updated at Trust Board meeting.
Regulatory requirements. 03. Not prepared for the introduction of the community services governance indicators post outcome of Monitor consultation. | Director of Finance |  | Development of information management reports continue to monitor compliance against the confirmed indicators to ensure action can be taken prior to formal reporting commencing in Q3. Reporting to Board will commence in M7 Board report.
Regulatory requirements. 04. Maintain registration with CQC. Ongoing registration. | Director of Nursing and clinical governance |  | Registration with CQC maintained. | - | -
Regulatory requirements. 05. FT Membership - continued membership growth. | Chief Executive |  | During Q2 (2011/12), the Trust continued to see an overall reduction in the number of Members (excluding staff) as a consequence of a slowed recruitment rate and an increase in resignations. Specifically, during Q2 (2011/12), 12 new Members joined compared to 26 new Members in Q1 (2011/12) and for the same period, 30 existing Members left compared to 44 leaving in Q1 (2011/12) . Throughout the quarter a range of recruitment activities had taken place to try and attract new Members. The Trust's Membership Strategy was reviewed and amendments were made to some actions in order to address known concerns with recruitment at retention. | The Trust's Annual Plan requires a growth of 66 new Members each a quarter. Subtracting the number of Members leaving from the number joining, the Trust did not achieve any growth this quarter. Despite having an updated Membership Strategy in place and the opportunities that the community health services integration presented, the Trust continues to struggle to attract and retain Members. If Membership growth is not addressed over the remaining Quarters then the Trust will be at risk of missing its Membership targets. | Possible reasons for the variance include the difficulty in selling the benefits of Membership to people. In addition, those leaving have mostly reported that they no longer have any interest in receiving information from the Trust or have no time to become involved. In terms of further actions to be taken, Membership targets still need to be included as KPIs for the Divisional Directors (to be monitored through the divisional performance reviews). In addition, further recruitment activities in line with the existing Membership Strategy objectives will continue to be undertaken to increase the Membership in mental and community health services. Progress is reported to the Extended Executive Board on a quarterly basis. Finally, the Membership Officer leaving the Trust presented an opportunity to review of Membership recruitment and support was managed. As such, during Q3 Membership recruitment, management and involvement will move to the Trust's Communications and Involvement Team. It is hoped that combing FT Membership recruitment with the wider involvement agenda will help to increase the number of Members joining the Trust.
Leadership and governance
Leadership and governance. 01. Executive Director changes | Chief Executive |  | Finance Director was during appointed Q2. Further changes to Executive Director responsibilities are being worked through. | N/A | On track.
Leadership and governance. 02. Revise non Executive Appraisal process | Director of HR |  | On track for Q2. Discussion at September Board Seminar and implementation agreed. | N/A | On track Q2 FY12
Leadership and governance. 03. Substantive vacancy for the Oxfordshire Community Services Divisional Director | Chief Operating Officer |  | Substantive appointment made to vacant Divisional Director post June 2011. | N/A | Complete
Leadership and governance. 04. Non Executive re-appointments. Three Non Executive ED terms expire during 2011/12 (October 2011, January 2012, February 2012) | Director of HR |  | The members council will be supportedto (re) appoint NEDs in line with the provisions and procedures set out in the trust's constitution. Members Council Nominations and Remuneration Committee being convened to agreed further appointments. | N/A | On track
Leadership and governance. 05. Ensure Governors and the Board of Directors are aware of the changing role of Governors | Chief Executive |  | The role of NHS Governors (and Directors) is likely to change through the Government's plans for the NHS (as set out in the Health and Social Care Bill 2011). Following the Government's listening exercise on the Bill, the NHS Future Forum published their recommendations on the future for NHS modernisation and the Government published its response on 20 June 2011, setting out the changes it intends to make in response to the recommendations. Until the Bill is formally enacted, at this stage it is still not clear what, if any, new roles and responsibilities Governors (and Directors) will have. Nevertheless, the Trust has started to prepare for possible changes by instructing solicitors to assist in reviewing the Trust's Constitution and linking in with the FTN. | N/A | On track (but is dependent on externalities)