## OMAP_335.e3ac8c79-add2-4053-8a6
Board Quarter 3 Progress report against Annual Plan 2011/12 APPENDIX A
Accountability Title | Accountability Owner |  | Key Achievements in third quarter | Current Concerns | Reasons for variance and Actions Taken | Risk Rating
Strategy - overall key priorities
Overall key priorities 01- Demonstrate year on year improvements in the clinical quality of the services delivered (x-reference to clinical quality milestones for details) - Delivery against FY12 Quality Account; Achieve FY12 CQUIN targets | Director of Nursing & Clinical Governance |  | Data for the 3rd quarter Quality Account is being collated for its presentation to the February Trust Board Meeting. Generally this exercise has been easier than before due to the preparatory work of the 1st and 2nd quarters. This appears to show that people have an increasing awareness of the importance of quality measure and targets, and the consequential increase in patient care
Overall key priorities 02 - Delivery of service development plans achieving improved access and value for money (milestones indicate completion; x-ref to service development and Operational/financial effectiveness Milestones for further detail ) | Chief Operating Officer |  | Integration Board set up, now under the Medical Director and Director of Strategy as Lead. Seven project groups established and project briefs developed. Integrated model in place for Huntercombe prison. Clinical service model being revised within Bullingdon prison along with review of medication management and mental health service provision
Overall key priorities 03 - Improve the quality and functionality of the Trust’s estate (x-ref service development and capital programme Milestones for detail) | Director of Finance |  | In addition to the major schemes in capital programme an extra £900k has been allocated to improve inpatient environments this year. | Due to limited capacity of, and performance of framework contractor the smaller capital schemes in Q1, Q2 and Q3 are in delay. | Increased capacity from additional framework contractor agreed with procurement team to be effective during Q4. Numerous schemes have been reprogrammed into FY13 against the £2.5m Operational Capital budgets.
Overall Key priority 4 - Delivery of the 2-3 year Improvement and Innovation Programme across the Trust | Chief Operating Officer |  | Programme continues to deliver as per plan; monthly reporting continues and Advisory Board meeting quarterly; new initiatives including 'Back to the Floor' scheme and reward and recognition certificates for teams/individuals engaged in continuous quality improvement launched. Improvement and Innovation Committee established within Specialised Services Division to identify local initiatives. Several projects now underway. | Lack of capacity available to take on new pieces of work should they be required eg emerging from the Trust Strategy work.
Overall key priorities 05 - Implementation versions of the RiO System for Mental Health and Community Services - Embedding Rio Use. Upgrade to RiO R1. Upgrade to RiO R2. | Director of Finance |  | Both RiO R1 projects have commenced and are progressing on schedule for a March / April 2012 go-live. The Optimisation Project for the Community Health version has also commenced (ie introducing use of the available clinical functionality). The business case was formally approved by the Finance & Investment Committee in Nov 2011. | Balancing engagement from operational services with their challenging workload. | No variance
Key External Impacts
Management of External impacts. 01. Impact of the economic climate on funding in NHS, Social Care and 3rd Sector. | Director of Finance |  | None. Continued monitoring of the national position as expressed in the NHS Operating Framework and Monitor Key Financial Assumptions.
Management of External impacts. 02. Impact of the changes as set out in the Health and Social Care Bill 2011 | Director of Finance |  | Meetings held with newly appointed Trust Lawyers to review the impacts of the Health and Social Care Bill. As Bill progresses further analysis and training sessions will be held to fully understand and respond to the impact of the changes. | Health and Social Care Bill progressing through House of Lords - awaiting formal outcome | Variance due to unknown timetable and impact.
Management of External impacts. 03. Increase in the prevalence of mental health problems in the community due to the aging population, the recession and returning military personnel | Chief Operating Officer |  | Dementia and Older Adult Liaison Bids completed and submitted to both Oxon and Bucks PCTs | Bids on hold due to other submitted bids for LTC/MUS made by OHFT being prioritised ahead of services for older adults and dementia
Management of External impacts. 04. Market Testing | Director of Finance |  | Market analysis work undertaken as a part of developing strategy document approved at the September Board of Directors meeting. Further analysis to be undertaken as a part of the development of the trusts strategic plan and new business developments. Regular reporting to executive board and use of business opportunities assessment tool.
Management of External impacts. 05. Changes to the local NHS landscape e.g. Merging Trusts (opportunities and threats) other providers looking to provide traditional NHS services | Director of Finance |  | Changes to the NHS landscape included within Strategy Discussion document paper considered by the Board on 28th September 2011. Local NHS landscape analysis will be considered within the approach to strategic framework; Further work on the strategic framework has linked this to one of the trust's strategic drivers called developing our business.
Financial Plans: Service developments
Financial Plans: Service developments. 01. Consolidation of all inpatient services in Buckinghamshire on the Manor House site | Director of Finance |  | Outline Business Case approved at Board of Directors 28th September 2011. Next milestone is Guaranteed Maximum Price 18th November 2011. Planning permission expected in November 2011. Outline Planning Permission proposals for excess land submitted in October 2011 | New project director appointed 17th October 2011. On target to achieve forecast GMP through value engineering process. | -
Financial Plans: Service developments. 02. Delivery of integrated locality teams delivering care tailored to individual communities. | Chief Operating Officer |  | Integration Board set up, now under the Medical Director and Director of Strategy as Lead. Project group established and project plan completed for SPA and the move towards six integrated community localities. Oxford Health NHS FT model developed for integrated community localities to go live April 2012 with a single point of access for each locality providing a patient bureau type service, with the key objective being to ensure the seamless and safe management and referral of patients that would benefit from community service intervention, either to prevent an admission or to support early discharge | Commitment needed to ensure contracting aligned to ACE. Lack of clarity regards financial planning to support initiatives which are new developments or require expansion of existing services
Financial Plans: Service developments. 03. Re-provision of adolescent inpatient services on the Warneford Hospital site | Director of Finance |  | Contract for the Highfield now on site with completion due November 2012 | Contract running on time and within budget | -
Financial Plans: Service developments. 04. Bring together Forensic Mental Health services into a two hub/spoke model with consistent pathways | Chief Operating Officer |  | This action has been complete with the exception of the Bucks PDU which is on hold pending a demand/capacity review given the recent increases in capacity within the NHS and repatriation initiatives
Financial Plans: Service developments. 05. Reconfiguration of adult and older adult community teams to improve continuity of service, access and demonstrate value for money | Chief Operating Officer |  | Completed in Oxfordshire. Proposal for remodelling of Crisis Services across both counties submitted for Executive approval. Under integration project board, project group established for older adult integration; project brief currently being developed | Executive approval not granted for Crisis remodelling
Financial Plans: Service developments. 06. Integration of specialist inpatient Eating Disorders business, maximising opportunities to develop community services | Chief Operating Officer |  | Inpatient specialist eating disorders services to be commissioned by specialist commissioning/NHS Board from April 2012. They will commission on behalf of pacts and all contracts will transfer. | No expected impact immediately but not yet known if Specialist commissioners will buy all our capacity. issues around costs, price, current over performance on block contracts etc. Meeting with specialist commissioners February
Financial Plans: Service developments. 07. Delivery of specialist addictions services in a range of community settings | Chief Operating Officer |  | Contracts not yet signed. Issues around TUPE not yet resolved. Transferred to specialised division November 11 Oxford Health was successful in bidding to become the Harm minimisation provider. We could not tender for the Recovery components of the new Oxfordshire addictions system. Addictions Services have not transferred to the Specialised Division with support from previous management. | There are some potential TUPE risks with the new providers. There is risk that the new service model will not be implemented by the end of April due to the delays within the tender processes and implementation timescales required for organisational change. The Bucks addictions service continues to perform well however there are rumours of reduced budgets for next year . | Project Board implemented which includes clinical and management staff as well as patient representative. Project manager recruited to ensure successful management of work streams.
Financial Plans: Service developments. 8. Delivery of a range of accessible psychological service pathways from primary to specialist | Chief Operating Officer |  | Services operational in both Oxfordshire and Buckinghamshire. Oxfordshire work is focusing on development of new service models for Long Term Conditions and Medically Unexplained Symptoms. These are being undertaken in conjunction with Community Health Division as well as Commissioners. Medical Director Executive Sponsor for this work with Community Divisional Director leading. Psychological Services will transfer to Community Division by April 2012. Chief operating officer and the divisional directors for community services and children's and families have agreed that services will not move to community division until April 2013 due to priorities and issues within community division
Financial Plans. Service Developments. 9. Provision of integrated CAMHS care pathways across Tier 2-4 | Chief Operating Officer |  | IAPT underway. In discussion with Wilts CC with a view to taking over provision of tier 2 CAMHS from April 2012. Contracts with Ridgeway ending on 31 March 2012 and staff tupeing to oxford health ft. Remodel of Buckinghamshire camhs underway. building development of new Highfield on track for completion November 2012. Specialist commissioners will be taking over commissioning of inpatient camhs services. - see eating disorders issues above
Workforce priorities
Workforce 01 - Achieving sustainable performance against key Workforce KPIs within Divisional and Corporate Directorates. Year on year achievement of: • Sickness rates 3.5% - 2.5% • Turnover 10% average • Use of bank and agency 4%, 3%, 2% • Average staff cost £38K, £35K | Director of Human Resources |  | Sickness absence rates in December have risen slightly to 4.09% however for the YTD they are still close to target at 3.6%. Turnover remains stabilise at 10.61%. Bank and Agency remains within target at 3.2% supported by the further use of sessional contracts. Continuous monitoring B/A performance by the HR team has resulted in a slight improvement over the previous quarter i.e. as at the end of December 1.7% Bank and 1.5% Agency usage, Stability has dropped a little to 85.55% | Sickness less have increased slightly but this was anticipated and the HR teams have been working to minimise the effects of re-structuring to good effect. Overall position at the end of the quarter remains close to target at 3.61%. improvements have been achieved in bank and agency usage and therefore the close monitoring of these by HR within Divisions is having a positive effect. Community remains the area for closest scrutiny.
Workforce 02 - Developing management and leadership capacity for the future. Developed as part of OD planning. | Director of Human Resources |  | The re-designed Management Development Programme (MDP) is being delivered with 28 courses available of 70 dates throughout the year. MBTI has been used with around 50 managers as part of team development programmes. Additional places have been obtained on SHA organised leadership events. Coaching services continue to be used for individuals. A second cohort of the Talent Pathway Programme has begun. Leadership and management development programmes are being reviewed to align to the revised appraisal system. The draft OD programme which covers leadership and management development is completed. | Changes to the Trust's strategic framework require amendments to the leadership and management plan which are being worked through with the L&D team. A revised plan will be completed by the end of the 4th Quarter to meet the annual business plan and longer term strategic plan for HR and OD
Workforce 03 - Succession planning - developed as part of OD planning | Director of Human Resources |  | First cohort of Talent Pathway Programme resulted in identified development needs for individuals. Second cohort scheduled for May-July 2011. As part of the revision to the appraisal system the Board have required that succession planning is built in to the process and is being implemented. CEO has required all executive directors to nominate deputies for operational effectiveness and business continuity. OD planning has identified the need to make leadership/management development more widely available and has been addressed. Revised appraisal/performance management system will be in place by April 2012. | This objective needs to be linked closely to be integrated with the HR/OD Plan and will be revised to take account of the new strategic framework. Director of HR/OD to address.
Workforce 04 - Organisational change programme | Director of Human Resources |  | Organisational Design and Development Strategy has been implemented through management re-structure and in line with integration planning. Second phase transformation programme to achieve further integration benefits has been initiated . | Trust Strategic Framework has been approved by the Board, integration benefits being monitored and reviewed by integration programme monthly and further changes for efficiencies to reduce management costs are now in train.
Workforce 05 - Improving staff satisfaction (Staff Survey) - Continuation of “Effective Team” programme focussing on team work and development - Plan for improving communication between senior management and staff developed and reporting on findings by October 2010. - Working group on appraisal/PDR established March 2010 to report by October 2010 - Year on year improvement in survey results | Director of Human Resources |  | 2010 results received and circulated to Divisional Directors and Board. Poor results for 2010 has lead to the following actions:- Director HR/OD taking lead within the Staff Survey Working Group, Executive walk arounds agreed, membership of SSWG reviewed, identifying quick wins for 2011 and taking longer term view with revised and improved action plan. First meeting of the revised working group has taken place and agreed new action plan. This has subsequently been reviewed and agreed by wider Board. Communications plan for staff survey in place and divisions have taken forward plans locally. 2011 staff survey has been launched. Executive have approved 'Back to the Floor initiative for senior managers. The 'effective teams' initiative has been expanded and brought within the management of the Innovation and Improvement Team. | 2010 results show a deterioration in many of the key findings. There is a likelihood that 2011 results show little improvement if no immediate action taken. Staff representatives from the MC and also other interested MC members are being invited to help support further activities to improve staff experience of working for the Trust and the launch of the new strategic framework will add greater clarity throughout the organisation and support the changes to the performance management system. It is still anticipated that 2011 staff survey results will show only slight improvement over the previous year as more time is needed to embed the changes which have been initiated.
Workforce 06 - Strengthening strategic planning and project management capacity and capabilities - Board workshop in June 2010 to agree strategic direction - Resource requirements managed through the newly established programme office - Monitoring of progress against key strategic milestones through the Transitional Programme Board and OBMH Board. | Director of Human Resources |  | HR Director currently holds the role of Programme Director for the Project Management Office which is to be continued for the next year to continues to monitor key strategic milestones. Programme of skills transfer from original project support to internal management has been achieved. Funding for the PMO has been agreed and the team have provided further support across all projects to maintain benefits performance. | Alignment between 'Strategy ' and OD planning necessary to ensure delivery of the medium / long term strategic direction. Director of HR has drafted the OD/HR Strategic plan to underpin the new strategic framework. The continuing management of the PMO has now transferred to the Director of Finance to align with future CIP planning/monitoring/delivery
Workforce 07: Workforce strategy. A new Workforce strategy has been agreed to address significant reduction/change to workforce over next 3 years incl: • Introduction of more flexibility in service delivery e.g. changes to working hours • Changes in workforce profile require specific actions e.g. areas where we have an aging workforce. • Changes in roles and introduction of new roles in light of CHO integration | Director of Human Resources |  | New workforce strategy developed as part of business case for Monitor which addresses current CIPs and integration with CHO. Workforce plans to be developed with Divisions/Directorates. E-Rostering programme brought forward with implementation from August 2011. Feedback from performance meetings identifying divisional hot spots for HR activity and support e.g. appraisals and mandatory training, staff satisfaction and control of agency costs. Management re-structuring has been implemented in line with integration programme and further cost reductions being identified. Revised template for long term workforce planning being completed for implementation 3rd quarter. | Changes in estates management and the introduction of a project to align service development with better utilisation of estates have positively impacted on the need for improved workforce planning. The people element of the new strategic framework has a focus on the implementation of long term workforce plans to be reported at Board level in terms of monitoring progress against the plan.
Capital Programmes (including Estate Strategy)
Capital Programmes. 01. Manor House redevelopment – new build 80 beds and community services - Buckinghamshire | Director of Finance |  | Full Business Case approved at Project Board on the 12th December and Finance and Investment Committee on the 13th December 2011. Guaranteed Maximum Price agreed at £23.5m on the 21st November 2011 with Z clause required for conditions agreed as part of the agreement. Phase 3 of the contract has been approved to be extended by £750K to cover the time period between Nov and March for Monitor approval of the FBC. Planning permission for the hospital was granted on the 8th December 2011 with 18 conditions. Outline Planning Permission proposals for excess land submitted in October 2011 | Full Business Case, now with Monitor for approval, expected approval date 28th March 2012. | -
Capital Programmes. 02. Highfield Adolescent inpatient unit re-provision. | Director of Finance |  | Contract for the Highfield now on site with completion due November 2012 | Construction programme currently running approx 2 weeks behind. Finishing trades have been reprogrammed to ensure the Practical Completion date of 22nd October is achieved. | -
Capital Programmes. 03. Forensic –Phoenix and Windrush (Littlemore, Oxfordshire) subject to delivery of strategic service plan | Director of Finance |  | Approval given to proceed with feasibility and outline proposals to convert Windrush Ward into the City Community Hospital facility. The major scheme to convert Phoenix into fully en-suite and HBN compliant facility has been deferred until FY14 in line with the Capital Plan. Immediate issues around ligature risks to be addressed in FY13. | Prioritisation plan required for Estate usage for clinical service strategies. | Clinical service strategies and estate rationalisation plan to be further developed in Q4.
Capital Programmes. 04. Marlborough House – Improve security and enhance the patient environment - Milton Keynes | Director of Finance |  | Additional construction partner appointed to support the scheme, due to capacity and performance of Integrated Construction Services Framework providers causing delays to the scheme. Procurement have advised upon and supported the appointment. Project team to be established to develop the outline proposals in Q4 | - | Poor Performance of current Construction Services Framework
Capital Programmes. 05. CHO Estate Rationalisation – optimisation of community estate | Director of Finance |  | Some continued progress with a few leases under notice not to renew. Cuffas Leas and Isis Business Park completed. More schemes in pipeline (e.g. Boundary Brook House, Wallingford, Henley etc). | The Estates rationalisation plan and estates strategy are in delay. A revised structured approach to the development of the Estates Strategy and rationalisation plan is being prepared by the Head of Property and Capital Investment for submission and approval in Q4.
Capital Programmes. 06. Inpatient wards – improving environmental standards – Littlemore and Warneford (Oxfordshire) | Director of Finance |  | Limited progress made on the £900k investment plan due to pressures from Divisions to be offered Windrush Ward as a decant option. Works and phases have now been re-programmed and reprogrammed inline with constraints in working within a live inpatient environment. VT will now commence in Q4, Wintle in FY13, Q3. | Limited capacity of framework contractor delivering smaller capital schemes in Q1 and Q2. | Increased capacity from additional framework contractor agreed with procurement team to be effective during Q4.
Capital Programmes. 07. Forensic Women's Enhanced Low Secure (WELS) (Oxfordshire) – extension to existing ward to provide net two additional beds | Director of Finance |  | Scheme on site with completion of beds phase scheduled by March 2012. Approval delayed. Scheme now on target with revised timetable. |  | -
Capital Programmes. 08. Woodlands (Buckinghamshire) – major refurbishment to inpatient ensuite bedrooms. | Director of Finance |  | Scheme completed in Q4. |  | -
Capital Programmes. 09. Other minor schemes/unallocated | Director of Finance |  | Due to slippage within the FY12 programme, a number of schemes have been differed to FY13 and the FY11-FY14 plan refreshed. | Estates concerned with regards reporting process on risk, CQC outcomes etc. Concerns raised directly from Ward staff on AWOLs, ligature risks, environment deficiencies and patients accessing roofs are difficult to programme and manage. | -
Capital Programmes. 10. Estate Capital maintenance – to reduce backlog maintenance, comply with statutory standards, address PEAT findings and infection control. | Director of Finance |  | Schemes managed by capital control group substantially on target to deliver by year end. | Limited capacity of framework contractor delivering smaller capital schemes in Q1, Q2 and Q3. | Increased capacity from additional framework contractor agreed with procurement team to be effective during Q4.
Capital Programmes. 11. Information technology. The implementation of key initiatives such as: the merger of all former CHO users and infrastructure into the Trust’s network domain; expansion of the number of devices in use, including remote working support where possible; the implementation of a new risk management system (Safeguard); the implementation of a new Patient Level Costing system; the implementation of a new Occupational Health system. | Director of Finance |  | Mop-up' activities associated with the migration of the CHO IT estate continue. In consultation with the capital control group and operational representatives the IT capital programme has been re-profiled to address the funding needs of the aged desktop estate and the revised needs for merging legacy data warehouses. There are now four schemes: - PC Replacements - CHO Enabling - Server Upgrades/Replacements - Data warehouse | Scope creep from the re-profiled schemes. | Detailed analysis of the desktop estate indicated that circa 30% of devices were at the end of serviceable life and need replacing (i.e. more than five years old). A business case was produced to support the required funding. As this is a priority the existing capital funding for IT schemes was re-profiled.
Clinical Plans
Clinical plans. 01. Reduce towards zero the number of inpatient deaths from suicide | Director of Nursing and clinical governance |  | There have been no in patient deaths from suicide this financial year.
Clinical Plans. 02. Reduce towards zero the number of community deaths of patients in Trust services | Director of Nursing and clinical governance |  | There have been 28 apparent suicides so far this financial year. The LIPS Steering board has now met. Additional staff from Bucks have attended LIPS training. All community teams have initiated one new intervention aimed at reducing suicides (CQUIN target). LIPS dashboard is in preparation. Work streams on a range of patient safety areas have been identified and initiated. | A projection for the year suggests that we will have had as many suicides in the community as last year.
Clinical Plans. 03. Reduce to 30 from 34 (the previous target) the number of cases of Clostridium Difficile by March 2012 | Director of Nursing and clinical governance |  | There have been 13 cases of C Diff this year. |  | -
Clinical Plans. 04. Preventing avoidable skin breakdown which can lead to pressure ulcers. 85% of patients will be assessed for pressure ulcer risk factors and preventative measures implemented within 2 days. | Director of Nursing and clinical governance |  | Community hospitals in Q3, 88% of patients were assessed for pressure ulcer risk within 6 hours of admission
Clinical Plans. 05. 100% of mental health patients on CPA have a current care plan, had care review in the last 6 months; a care coordinator and a risk assessment which has been reviewed in the last 12 months. | Director of Nursing and clinical governance |  | % of records with all 4 elements in place - 80% % with a care co-ordinator identified - 98% % with a current care plan - 93% % with care plan been reviewed in the last 6 months - 87% % with a current Safety/Risk Assessment & Management Plan - 90%
Clinical Plans. 06. Further reduce the incidence of emergency readmission within 28 days of discharge (2.9% March 2011) by careful discharge planning and assertive follow up. | Director of Nursing and clinical governance |  | The YTD total is 5.59%
Clinical Plans.07. To increase to 72% by year end the number of patients who have been receiving care for 9 months or more, that have a baseline and follow-up HoNOS rating. | Director of Nursing and clinical governance |  | 46% as of 31st July 2011 . Quarter 1, 2 and 3 figures not available for this report. To be updated Q4.
Clinical Plans. 08. Deliver Hospital at Home services for the population of Oxfordshire. | Director of Nursing and clinical governance |  | The hospital at home service is in place in south oxfordshire and is in the process of being implemented in the west of the county. Provision in the north of the county will be in conjunction with PML
Clinical Plans. 09. For the trust to score better than average in the National Patient Survey (community) in the following areas: - Service users knowing who their care coordinator was. - Service users being offered a copy of their care plan. - Service users who have had a care review meeting in the past 12 months - Physical Health of Service users checked - Having a contact number out of hours | Director of Nursing and clinical governance |  | CQC published results of community mental health service user survey in August 2011. Mental health and Children and families divison have agreed action plans - implementing standards (as in B14) for patients not on CPA as well as those that are supported by policy change and clinical audit.
Clinical Plans. 10. Community services to improve the % of patients who rate their care good, very good or excellent. To achieve results comparable to the national top 20% of acute trusts satisfaction rating for both out-patients and in-patients as no comparable survey for community services. | Director of Nursing and clinical governance |  | After Q2, it was 79% rate their care 'good', 'very good' or 'excellent' |  | Note, this is Q2 figures
Regulatory requirements
Regulatory requirements. 01. Maintain Monitor Financial Risk rating. | Director of Finance |  | Current forecast is to deliver the plan - likely to remain on trajectory this year although there are material risks in CIP delivery and Community Services Division being managed through reserves.
Regulatory requirements. 02. Maintain Governance risk rating. | Director of Finance |  | We continue to monitor all targets on a monthly basis and utilise performance improvement resources where risks are apparent. | Q3 performance for requirements relating to healthcare for people with Learning Disabilities are at risk. Update to be provided at Trust Board meeting.
Regulatory requirements. 03. Not prepared for the introduction of the community services governance indicators post outcome of Monitor consultation. | Director of Finance |  | Information management reports have been reviewed. Some information collection processes still to be established. Formal reporting to Monitor will commence from Q3 | Data systems do not record all information required. Alternative work around solutions being sought | Capacity of information team. Capture of information. Information team and IT working together.
Regulatory requirements. 04. Maintain registration with CQC. Ongoing registration. | Director of Nursing and clinical governance |  | Registration without conditions maintained
Regulatory requirements. 05. FT Membership - continued membership growth. | Chief Executive |  | During Q3 (2011/12) the Trust gained 8 new members and there was 1 leaver. The number of joiners is less than previous quarters but the number of leavers has significantly decreased. Following the decision not to replace the Membership Officer, the lead for recruitment and engagement of members has transferred to the Communications and Involvement Team. The team met on 7 December for a workshop on membership. A report is being pulled together for the Executive Board containing recommendations from the workshop. These include a review of the membership literature and promotional materials, hosting a series of health lectures to sign up new members and encourage existing members to engage with the Trust and surveying the public on membership. An online survey is currently live on Facebook, Twitter and has been sent to members and other key contacts asking for feedback on what opportunities existing members would like to engage with the Trust and what would encourage non-members to sign up. The survey closes at the end of January. The Divisional Directors have agreed quarterly membership recruitment targets and at the request of the Chief Executive, have been asked to identify champions within their divisions to take forward the membership agenda. The Communication and Involvement Managers are also supporting Divisional Directors with membership activities. | A growth of 66 members per quarter is required and despite Divisional Directors agreeing targets a culture shift is required for staff to feel that it is their responsibility to support membership and feel empowered to recruit members. This is not a change that will happen over night. There is still a lack of clarity on the benefits of membership and this is crucial to encourage people to sign up. The Communications and Involvement Team will use feedback from the current survey to develop opportunities for membership engagement that can be factored into the benefits of becoming a member. | As mentioned, the lack of clarity on the benefits of membership means it is difficult to 'sell' membership. This will be addressed following feedback from the survey. Membership targets have now been set so this should have an impact on numbers next quarter as more staff start to take responsibility for recruitment of new members. The Trust's presence in the local community to attract membership has been minimal over the last quarter, a number of events are in the process of being planned including health lectures and stands in local supermarkets and events (Oxford Science Festival). Key partners are being identified to support local recruitment activity, these include Science Oxford, Oxfam, and Bucks New University.
Leadership and governance
Leadership and governance. 01. Executive Director changes | Chief Executive |  | The Director of Strategy and Commercial Development post has now ended with all responsibilities formerly held by this post having been distributed to other Executive Directors. | N/A
Leadership and governance. 02. Revise non Executive Appraisal process | Director of HR |  | On track for Q3; Discussion at September Board Seminar and implementation agreed.
Leadership and governance. 03. Substantive vacancy for the Oxfordshire Community Services Divisional Director | Chief Operating Officer |  | Substantive appointment made to vacant Divisional Director post June 2011.
Leadership and governance. 04. Non Executive re-appointments. Three Non Executive ED terms expire during 2011/12 (October 2011, January 2012, February 2012) | Director of HR |  | The members council will be supported to (re) appoint NEDs in line with the provisions and procedures set out in the trust's constitution. Members Council Nominations and Remuneration Committee being convened to agreed further appointments.
Leadership and governance. 05. Ensure Governors and the Board of Directors are aware of the changing role of Governors | Chief Executive |  | The role of NHS Governors (and Directors) is likely to change through the Government's plans for the NHS (as set out in the Health and Social Care Bill 2011). Following the Government's listening exercise on the Bill, the NHS Future Forum published their recommendations on the future for NHS modernisation and the Government published its response on 20 June 2011, setting out the changes it intends to make in response to the recommendations. Until the Bill is formally enacted, at this stage it is still not clear what, if any, new roles and responsibilities Governors (and Directors) will have. Nevertheless, the Trust has started to prepare for possible changes by instructing solicitors to assist in reviewing the Trust's Constitution and linking in with the FTN. | N/A