## OMAP_335.e3ac8c79-add2-4053-8a6
Board Quarter 1 Progress report against Annual Plan 2012/13 APPENDIX A
Accountability Title | Accountability Owner |  | Key Achievements in First Quarter | Current Concerns | Reasons for variance and Actions Taken | Risk Rating
Driving Quality Improvement
To reduce towards zero avoidable community suicides where risk communication is a factor: service users on leave and/ or in contact with crisis services | Director of Nursing and Clinical Standards |  | Of the apparent suicides in Quarter 1, three are in the process of RCA investigation, one is awaiting an initial report and the rest have had record reviews. None to date have fitted the definition from the annual report. This will now be assessed by SIRI panels. A post dated review of last year’s suicides against the definition will be needed to compare to this year’s numbers. | Comparison to last year will require work to review all of 2011/12's suicides. Source of this specific target is not known .
We shall broaden the Leading Improvement in Patient Safety and Productive work across all divisions | Director of Nursing and Clinical Standards |  | The Specialised Services division will identify 3 LIPS projects. The first has been well advanced in Q1 and relates to improving the nutritional health of forensic inpatients. This is being piloted with the female residents of Thames House. Funding has been successfully obtained to upgrade gym equipment and improvements to care planning and assessment of under and over nutrition have been implemented. The Divisional Management Committee has agreed to focus the other two projects within Forensic wards and is developing project plans in relation to the use of intensive care areas and the use of seclusion and restraint. | Cancellation of any further LIPS training by NHS Institute has necessitated a re-think on division's strategy. | Structure of LIPS programme changed to 3 distinct Patient Safety Projects.
Development of safety dashboard of measures in all services | Director of Nursing and Clinical Standards |  | Safety dashboard is currently with developers to bring to proof of concept stage for presentation to the LIPS Steering Board on 15th August 2012
We are aiming to improve rapid treatment of people suffering cardio-vascular events | Director of Nursing and Clinical Standards |  | We have a clear process for all call handlers in the Urgent care service to identify potential cardio and cerebrovascular events and redirect appropriately to emergency services. We are implementing the 111 system which included module 0 to determine immediate risk to life with a subsequent automated call placement in dispatch stack ensuring a 999 response at the earliest possible time. All staff in urgent care services undergo mandatory resus training at 'Immediate life support' level ensuring time spent in the recognition of cardiac events and immediate treatment.
We are reducing towards zero all healthcare associated infections | Director of Nursing and Clinical Standards |  | There have been 4 instances of Cdiff in the 1st quarter and no occurrences of bacteraemia. A Board report is being prepared discussing the current situation.G69 | Despite carrying out all the identified preventative measures and improvements, the number of infections does not decline.
We are aiming to reduce waiting times for Physiotherapy and other therapies. | Director of Nursing and Clinical Standards |  | A re-structure of service and full recruitment has reduced average waiting times in first quarter from the 2011/12 level
We are improving Child Health Services by redesigning Children’s Community Nursing Services, piloting IAPT for children and increasing the number of Health Visitors | Director of Nursing and Clinical Standards |  | Community Nursing Project- focus of project is to reduce activity at the hospital, with a remit for both reducing admissions and length of stay. Oxford Health is leading this pathway redesign, working in partnership with OUH. We have appointed a clinical project lead jointly with OUH. Commissioners are Chairing a strategic board that is monitoring progress. Investment is 400K over next two years, recurring. We are fully on track to deliver changed outcomes for families with this project and seeing a renewed relationship with acute staff that we have not had previously. Health Visiting- this is Government pledge to invest in 4200 new health visitors. Jointly with commissioners we are on track to deliver this plan. Not due to deliver until 2015. Project manager and strategic board in place with good whole system engagement. This project is about a redesign of the health visiting role with the outcome being a targeted service consistently delivered across the County. Oxford Health recently were awarded Early implementer status for this work by the DH. Heavily monitored by SHA and DH.
We are improving access to services through introducing a single point of access for Community Services and a new non emergency contact number “111” | Director of Nursing and Clinical Standards |  | SPA commenced on 30 the April there have been 294 referrals to date with 47% of these coming from GP's Next steps are to integrate this service with mental health and social services and to scope the contribution that SPA can make to the DTOC challenge .111 implementation has been delayed by the DH to late July dependant on end to end patient journey system testing. Robust local tripartite governance arrangements are in place and the local project team are assured that we are in a position to commence when DH decision is made | Implementation challenges remain unknown as no other pilot site has moved from a system of GP triage to the 111 system.
We are developing more Integrated Community Teams and strengthening District Nursing services | Director of Nursing and Clinical Standards |  | The revised model is under development and preparatory actions underway in teams (allocating caseloads, developing standard operating procedures for management of process within teams). Delivery against the action plan is currently on time. Actions currently in progress include implementation of clinical supervision across the service, recruitment to training places for assistant practitioner and specialist practitioner courses, implementation of locality reference groups, increased staff involvement in audit of standards of care, staff consultation about hours of service delivery (in line with commissioning intentions).
We are strengthening personalised care planning across all community services | Director of Nursing and Clinical Standards |  | Report has been presented to locality meetings .Awaiting comments and feedback. New care plans are being introduced on an incremental basis.• Core care plans have been developed by the community hospitals documentation group and have been ratified. These will address issues that have arisen from various reviews/incidents
We are implementing the new Specialist Harm Minimisation Services for people who misuse substances | Director of Nursing and Clinical Standards |  | The new Harm Minimisation (Harm Min) service is one of the new 6 national pilots for addiction services and the department has undergone a significant transformation both in terms of staffing, location and bringing a non-statutory organisation and NHS health care together. This model is likely to be replicated in other parts of the country in a push to move patients to recovery. The new service opened 2 April 2012 having completed a significant refurbishment at Rectory Road. The new model of care has been challenging for all providers as the patient systems are each reliant on all the other providers playing their part and Oxford health being only one part of the jigsaw. Not all patients have yet been assessed as to which part of the new treatment model they will access. A review of clinical caseload activity is due to complete in July. | Early part of new project, so current caseloads are high, before patients move on to recovery. Occasional incidents around joint working with new partners. | Problems managed as they arise. Staffing review underway.
We shall be developing models of care and care packages using evidence-based interventions; these will link to the Care Clusters that were determined during 2011/12 | Director of Nursing and Clinical Standards |  | The care clusters work is focused in the mental health division . In Specialised Services, this is in its early stages and we are piloting care clusters and five forensic pathways in line with this year’s CQUIN. | Not as advanced in SS division.
Ensure high standards of care programme approach (CPA) and personalized care plan compliance for all service users in all teams | Director of Nursing and Clinical Standards |  | CPA audit results consistently 100% in Specialised Services. On-going monitoring via GtBR and CPA audits, monitoring of training.
Roll out and take up of personal health budgets/ direct referral | Director of Nursing and Clinical Standards |  | Personal Health Budgets (PHB) are now normal operational practice in Continuing healthcare, so all new referrals are taken through PHB and offered the option of a direct payment OH are applying to be a further faster pilot site
We are investing in a new 80 bed Hospital and community Resource Centre In Aylesbury Buckinghamshire | Director of Nursing and Clinical Standards |  | Started construction work on site, reviewing financial appraisals on property and surplus land. Reviewing commissioning and decommissioning strategies. | Current 6 week delay due to subcontractor liquidation | Trust project team working with Kia to mitigate slippage
We are investing in significant upgrading of Marlborough House Milton Keynes (Medium Secure Unit) | Director of Nursing and Clinical Standards |  | Funding has been approved for changes to the day area on Watling Ward - work to commence in August 2012. Funding approved for new reception area. New drawings needed to reduce amount of glass. Work due to begin November 2012. New outer doors fitted but potentially not suitable. Boiler fencing work completed. New ICA funding not approved. New working protocols introduced instead. | Funding not achieved for ICA area | New way of working introduced to achieve an ICA area.
We aim to improve patient experience year on year | Director of Nursing and Clinical Standards |  | CQC mandated Community Mental Health patient survey closed and final report due end of July early August from Quality Health. Insufficient interest expressed for the Patient experience single tender under the Governments procurement framework so the Trust is now pursuing a provider through a two stage tender process. Initial stage completed with five organisations meeting pre tender specification.
To be above 90% for internal feedback and over two years above average in National Surveys | Director of Nursing and Clinical Standards |  | The CQUIN goals this year are to improve or maintain scores on the following 3 questions: Were you involved as much as you wanted to be in decisions about your care and treatment? How much information about your condition or treatment was given to you? Did [the clinician] listen to what you had to say? Currently overall satisfaction score targets and achieved s. In the OCS division, all but 1 target was met. The score for this service (Parkinson's disease nurse) was 89 out of 100. | There are a number of areas where there is on-going work needed to achieve 90%
Maintain registration with CQC. On-going registration. | Director of Nursing and Clinical Standards |  | No change in registration | Quality & Risk Profile starts to show deteriorating assessment of Outcomes on limited negative data
Delivering Operational Excellence
Implementation of ACE programme: • Single point of access in community services. • Reducing number of DTOC. • Implementation of access criteria for community hospitals. | Chief Operating Officer |  | • The SPA for community health services has gone live (30th April 2012) for GP referrals, and in May 109 referrals were made through the service from 17 different referral routes. Approximately half the referrals have been from GPs • Providers have met to discuss the potential for SPA service going live to support hospital discharges at scale. Further scoping work is being undertaken to establish the volume and remit that such a service could provide. • Clinical engagement workshop with CCG leads held May 15th, and further detailed clinical input session planned for June 26th, to be followed by final clinical design workshop on August 2nd. • Action is being taken to ensure the service works effectively with 111 • Locality workshops held in all six localities with attendance from all key services in health and social care. Local action plans developed to enable staff to take forward integrated working. • DTOC action plan agreed across all providers and shared with commissioners • 8 work streams identified and a programme manager appointed to manage progress across all providers • Oxford Health has formed a project group to operationally implement the actions relating to Oxford Health from the 8 work streams. • DTOC figures currently down across whole system to 139 and at lowest level for over a year within Oxford Health at 43 delays (31 relating to community hospitals). COMMUNITY BEDS • There has not been an agreement to implement access criteria to community hospitals though further work has been undertaken to clarify the function of community hospitals through the move on team. • We are now developing a revised specification for medical staffing EMU / Step up beds • Currently in discussion with commissioners in developing specification to extend EMU to a seven day service and extend opening during the evenings • Use of step up beds has facilitated admission avoidance and more targeted use of step up care | • Meeting the system requirements of Single Point of Access which are different to what can be delivered within resources • Acute and community integration – concern with regard timeframes/scope relating to work undertaken to explore joint venture opportunities between OUH and OH • Escalation of community bed stock in response to system crisis – limited capacity to escalate safely without reliance on the use of agency staff and the risks this brings in terms of cost and quality/safety • DTOC – concern that the anticipated downward trajectory may not be achievable/sustainable without fundamental system redesign outside of control of OH/OUH/OCC.
Reduce trust cancelled appointments | Chief Operating Officer |  | There is no target for Trust Cancelled appointments therefore we have taken a baseline of current rates. The current percentages for CMHTs across Oxon and Bucks taken to form baseline. Bucks - CE 2%, CW 1.6%, NE 3%, NW 3%, SE 0.3%, SW 2.5% Oxon - City East 1.2%, City West 2.7%, North 0.7%, SE 5.4%, SW 3.7% | There is a perception that the levels of Trust cancelled appointments for AWA is high. | Baseline taken at end Q1 and targets to be agreed for delivery
Data warehouse - automated one source data extraction system. | Director of Finance |  | Building on the completion of Phase A, the phase B planning has been presented to the Board and agreed in principal for a two year business intelligent programme.
Full implementation and use of RIO IT system across the trust | Director of Finance |  | RiO Release 1 upgrades have been implemented on schedule. Workshops have occurred within all divisions to identify enhancements to the use of RiO in the Mental Health Division, and the deployment of clinical functionality in the Community and Children and Family Division. Basic IT skill deficits have been identified in the latter and are being addressed. | Service capacity to undertake activities. | No variance
Delivery of cost improvement plans | Director of Finance |  | FY13 CIP target of £13.0m. £1.6m delivered (all recurrent) at month 2 against YTD plan of £2.4m, a shortfall of £0.8m for the YTD. | c. £2.4m of schemes are at risk | Delays due to additional scrutiny/assurance processes have caused shortfalls. In some cases initial estimates of returns have had to be revised down following detailed planning. PMO working to accelerate projects where possible to recover delays. Mitigation schemes being scoped to cover shortfall.
Implement care clusters and packages | Chief Operating Officer |  | Care packages and cluster specs are developed and first draft have been circulated for review. Second draft will be circulated 2nd week July 2012. From June 2012 the Clustering Project team have been visiting clinical teams to ensure that the staff know about clustering, know how to cluster and to discuss quality issues. The clusters project is still on track for the agreed pilot from October 2012. | Each cluster assessment on RiO remains "open" unless closed by clinicians, therefore patients could appear to be open to multiple clusters. | This does not affect the project timeline. The project team are working with teams and RiO central support to address this issue.
Maintain Governance risk rating. | Chief Executive |  | The Governance Risk Rating is determined by the Trust's performance against a range of targets and indicators. As reported at the June Board meeting, the Trust appeared to be at risk of missing two of the targets (C.diff and CPA). If both targets were missed then the Trust would receive an Amber-Red Governance Risk Rating. During Q1, the Executive Board discussed the C.diff target and noted concerns with how it had been set by the PCT and queried its appropriateness. The Executive Board was briefed by OUH infection control experts on C.diff and was provided with information to help explain the Trust's performance to Monitor and others. It was noted that meeting the unrealistic C.diff target during 2012/13 was problematic. The performance against the CPA target was analysed and it was found that an issue with timely data entry was the cause . Action was taken to improve performance and it was reported on 29/06/12 that the target had been met. | The C.diff target appears to be inappropriate and the likelihood of meeting it is low. Whilst the CPA target was met as of 29/06/12, sustained effort will be required to ensure that performance is maintained during the months ahead. | Actions to address the performance of both targets have been put in place. The plan resulted in an improved performance for the CPA target but the C.diff target remains an on-going risk.
Not prepared for the introduction of the community services governance indicators post outcome of Monitor consultation. | Director of Finance |  | There are three Monitor Compliance Framework 2012/13 indicators for Community Services; Cdiff, A&E waiting times and Data completeness. There is confidence in the reporting the first two indicators but it has been necessary to make some assumptions in reporting Data completeness. | Monitor definitions for Data completeness vague but the Trust believe it is reporting on the correct data items. | Waiting for the Information Centre to confirm exactly what will be included in the Community Information data set.
Delivering Innovation, Learning and Teaching
Increase number of grants for research | Medical Director/ Director of Strategy |  | There have been a number of recent grant awards e.g McShane (£190,000); cognitive health clinical research facility (£3.8 Million, Due to start in September 2012)
Increase collaboration with academic institutions | Medical Director/ Director of Strategy |  | There have been recent important developments such as The Oxford Health Academic Consortium, The wider Thames Valley Academic Health Sciences Network and liaison has commenced with the Department of Primary Care, University of Oxford to formulate research programmes relating to community services division and Liaison with Oxford Brookes University regarding multi professional academic developments.
Establish databases to identify research opportunities | Medical Director/ Director of Strategy |  | Although funding has been allocated to establish relevant databases, there has been slow progress during the first quarter |  | Given a higher priority with increased collaboration with the Trust's IT services.
Increase patient participation in research studies | Medical Director/ Director of Strategy |  | Despite good baseline patient participation in research studies, there needs to be further significant recruitment, including into commercial studies |  | Director of R&D and colleagues in the University of Oxford, Department of Psychiatry are working with clinical leaders and managers to improve recruitment
Develop clinicians to leadership roles | Medical Director/ Director of Strategy |  | Clinical leadership has been enhanced through wider portfolios for MD, DMD's, CD's, DDN's and Heads of disciplines via the CAB and divisional clinical fora. This area can be further enhanced by a more formal approach to support identified individual clinical leaders.
Developing Our Business
Roll out of an integrated care model across all services | Medical Director/ Director of Strategy |  | • Integrated Care Programme Board established with a vision of “ensuring that holistic and coordinated care is provided across clear pathways for all of our patients” • Programme Board scope covers integration agenda for all divisions and membership of board includes key partner organisations (primary, secondary care, CCG, county councils, voluntary sector etc.) • 6 Project Boards established that report to the Programme Board Chaired by members of the Programme Board with 26 separate projects running at end of Q1 addressing issues of integration • All projects ‘mapped’ to strategic framework priorities • Head of Integration supporting Medical Director/Director of Strategy in leading work programme | Meeting the system requirements of Single Point of Access which are different to what can be delivered within resources Acute and community integration – concern with regard timeframes/scope relating to work undertaken to explore joint venture opportunities between OUH and OH Project resources are working across multiple projects with limited time to implement ideas. Lack of co-ordinated approach between the Bucks and Oxon in community pathway designs.
Identify new service opportunities | Director of Finance |  | 13 new business opportunities have been identified ytd of which 7 are proceeding within the tender process. This activity has mainly involved the specialised division. Oxford Health has started the Any Qualified Provider registration/application process. The Business Tendering Process has been amended so that the appropriate Divisional engagement occurs earlier within the business opportunity evaluation. | Capability and capacity within the Divisions to provide project management tendering/bidding process The increased use of external consultants used for quality assurance for the tendering/bidding process | Review resource and skills
Introduce robust and streamlined contract management process | Director of Finance |  | Ex CHO staff have been informally integrated with the OH contracting team. Formal restructuring taking place during Q2. Alignment of systems and processes has commenced.
Develop close working relationships with clinical commissioning groups and other commissioning bodies. | Director of Finance |  | Regular meetings with Oxfordshire CCG at various levels with Clinical Directors and service operation leads. Regular meetings of Director of Finance with Ox and Bucks CCG CFOs. Established a regular commissioning relations meeting with PCT Specialised commissioners. | Lack of focus and delivery in key areas of concern to CCG - ACE program and Reablement in particular. An overall lack of positive cooperation in contract meetings and overall operational relations is evident and needs to be addressed. Lack of coordinated approach to Bucks CCG engagement. | Requires an integrated plan for developing good relations by Q2 and consider a formal review with CCGs of first half FY13 progress. In discussions to provide improved information on service provision.
Build effective GP relationships | Director of Finance |  | Memorandum of understanding signed with PML for further collaboration in Oxfordshire. Engagement with Oxfordshire GPs re SPOC 111, Oxford LMC chair and the district nursing review. Ian Neil, a GP, appointed as GP liaison in Q1. | Lack of coordinated approach to Bucks GP engagement. | Requires more formal and coordinated plan of engagement. Will investigate a presentation of information provision.
Regular communications with carers and families to encourage partnership and OHFT membership | Director of Human Resources |  | Implementation of localised membership leaflet within mental health division - worked on my service users and carers. Approved corporate membership leaflet in use. E-Insight and Insight delivered over the Quarter to members and non-members. Goldmine database training undertaken by comms team - this has identified areas for development where the database could be used to support communications. Website FT pages to be reviewed and revamped. | Lack of dedicated membership resource and small budget limits activity the Comms Team are able to undertake. | Divisional Champions have been identified and meeting needs to be set up asap to find out what support is required for divisions. FT Membership banner has been designed and ordered for use at Trust events to promote membership.
Maintain Monitor Financial Risk rating. | Director of Finance |  | FRR maintained as a minimum of 3 throughout Q1
FT Membership - continued membership growth. | Director of Human Resources |  | The total number of FT members at end of Q1 is 8915. 24 new members were recruited during Q1 and 14 members resigned. Three Health Matters events have taken place and attendance at Oxford Science Fair - these events have generated new members. | Lack of dedicated membership resource and small budget limits activity the Comms Team are able to undertake. More support required across the Trust to sign up new members. Regular report from workforce on membership numbers is not being received despite request form and chase up. | Planning a campaign to encourage each staff member to sign up one FT member - this would give us 6000 new members. Head of Comms to link with Deputy Director of HR workforce data issues.
Developing Leadership, People and Culture
Implement E-rostering | Director of Human Resources |  | E-rostering is currently being piloted in Specialised Services Division and Community Health Division. Recruitment for 3 trainers is currently underway to ensure that timescales are adhered to. The project will be delivered in 3 waves and will commence in September with a completion date of April 2013. | Currently on track no concerns at present
Development of joint clinical and managerial leadership | Director of Human Resources |  | Clinical Advisory Board has now been established and has met twice. Each division have a senior clinical advisory team (Clinical Advisory Group) responsible for ensuring standards and quality of plans and service developments | Currently on track no concerns at present
Increase number of competency based recruitment processes | Director of Human Resources |  | Competency based interviewing is currently being used in a number of areas across the Trust. To extend this practice across all areas in the Trust a training module is being developed by the HR team and delivered to all recruiting managers over the next 6 months. | Currently on track no concerns at present
Training needs analysis | Director of Human Resources |  | System re-design from recruitment to induction established to enable efficient 'on boarding' of new staff. Workforce planning process reviewed with Finance & business plan inputs. Analysis of training requirements is to be undertaken annually aligning with workforce planning. | Training Needs Analysis to be undertaken within Q3 but progress on workforce plans will impact adversely if they are not completed in accordance with current planning.
New PDR/Appraisal process | Director of Human Resources |  | New process in place, supported by training for managers in appraisals. New online performance dashboard went live enabling all managers to access detailed reports on appraisals due & an alert system to advise those required within next quarter. | Improvement made in performance against new 100% target to 85% overall, with SSD achieving 95%. | Highlighted reports to Divisional Directors to action those areas where PDRs remain 'not current'.
Leadership and management development framework in place | Director of Human Resources |  | Framework further refined after feedback from Divisional Directors, simplifying the assessment process. Identification of team managers underway via the engagement of SHRBPs to ensure that resources are targeted appropriately. Communication planning in place for Q2. System to support teamwork development in place. First tranche of Aston Team coaching event started, mainly service leads. | Currently on track no concerns at present
Framework for workforce and organisational development | Director of Human Resources |  | Revised Workforce / OD strategy will be completed in draft by 31st August 2012. This will underpin the strategic direction and framework and link more closely workforce planning, learning and development of the workforce and strategic planning (i.e. associated organisational design). | Currently on track no concerns at present
Revised statutory and mandatory training process | Director of Human Resources |  | New process in place with online performance dashboard enabling managers to have instant access to detailed reports of current training needs. Additional delivery capacity provided for majority of higher risk training subjects. Other training solutions now in development (e.g. Infection Control, Resuscitation) to reduce classroom attendance. Divisional action plans and risk assessments completed. | Whilst performance in 'mandatory' training has significantly improved (to 98% in Q1), progress on 'statutory' training has declined slightly as predicted (to 71% against a 100% target), mainly due to shorter refresher intervals for PMVA and Resuscitation training. 'Did not attend' rate high in some divisions (e.g. MHSD at 22%) | Escalation to Divisional Directors and Executive Board, with requirement to update action plans. Alternative training solutions enabled for high volume areas (e.g. Fire and Equality/Diversity). Review of cancellation processes across divisions to ensure escalation to appropriate managers.
Corporate and divisional workforce plans in place | Director of Human Resources |  | Workforce planning pro-forma developed and being rolled out within divisions by the SHRBPs with support from Learning and Development and finance team. | Template design behind plan due to resourcing problems within the Workforce Team. Project being reviewed by DHR and Deputy DHR to address slippage i.e. Additional resources are being made available to the team on a short term basis.
Implement revised set of workforce KPIs | Director of Human Resources |  | Workforce Performance report has bee implemented as part of the Board reporting. This includes workforce KPIs (e.g. Sickness, turnover, and bank/agency usage plus benchmark data and forecast information. | Currently on track no concerns at present
Continue improvement in staff survey results | Director of Human Resources |  | Wellbeing and culture group proactively taking forward results from 2011 staff survey. Divisional Action plans developed and implemented supported by SHRBPs. Local staff survey completed and results analysed. Feedback in the form of You Said, We Did communication being developed by a sub group including staff side. Next local survey being developed. | Currently on track no concerns at present
Review of Board development activities | Director of Human Resources |  | Monthly Board Seminars take place to provide time for greater strategic development and review progress against Trust wide projects and deliverables e.g. CIP programme, Estates Strategy and Business Information project. Additionally Executives and Non-Executives continue departmental visits plus the top 4 levels of management are engaged in Back to the Floor days working in frontline services. | Currently on track no concerns at present
Executive Director and Divisional Director changes | Chief Executive |  | During Q1, the CEO post was successfully appointed to. Interim appointments have been made to the COO, DD - Community Services and DD - Child & Family Services posts. These posts will be, if appropriate, recruited to on a substantive basis once the new CEO has taken up his appointment in October 2012 and determined what the Trust's executive / divisional structure should be. | There will be a one month gap between the current CEO post holder leaving and the new one starting. As the gap is short, this will be mitigated by one of the existing Executive Directors formally taking on the interim CEO role.
Revise non Executive Appraisal process | Director of Human Resources |  | Revised Non- Executive Director appraisal process simplified and now in place. All appraisals carried out by Chairman. | Currently on track no concerns at present
Chair and Non Executive re-appointments. Chair and Non Executive terms expire during 2012/13 | Director of Human Resources |  | Process agreed with the Members' Council Nominations and Remunerations Committee. Agreed format for the appointment / re-appointment now in place and process to begin mid way through Q2 i.e. August/September 2012 | Currently on track no concerns at present
Ensure Governors and the Board of Directors are aware of the changing role of Governors | Chief Executive |  | During Q1 both the Board and Council received updates on and the opportunity to discuss the Health and Social Care Act 2012. Following confirmation that the Act's key components relating to Governors will be implemented in April 2013, the Council has agreed to establish a small sub-group to work with the Trust Secretary on review the Constitution with a particular focus on the Membership provisions. This will also provide an opportunity for further discussion on the developing role of Governors. | None.
Getting The Most Out Of Technology
Embed use of RIO | Director of Finance |  | RiO Programme Board meetings have occurred. See also line 27 above.
Consolidate data warehouse | Director of Finance |  | Phase A consolidation is 95% completed
Pilot Telehealth | Director of Finance |  | A workshop has taken place with colleagues in the Community Division to scope out possible Telehealth areas for a pilot. Lots of potential areas have been identified although representation from clinical services was poor. Hence, follow-up workshops will be arranged. | Engagement and ownership. | New Community Division Programme Manager post created and will be used to help drive ownership and engagement.
New mobile working | Director of Finance |  | Further meetings have occurred with solution providers. Single sign-on and intelligent VPN management has been the focus. Attempting to acquire a free proof of concept. Achieving 'instant on' has been investigated for Windows 7 - it's not possible. Several laptop models have been purchased to assess solid state disk functionality. They demonstrate speed improvements, but at a cost premium. Vodafone and '3' mobile broadband dongles have been assessed for speeds in convenient areas (i.e., where IT staff visit). A structured assessment across the patch is being planned. Capacity issues have constrained activities. | Capacity to deliver. | Receiving priority status.
Windows 7 and application virtualisation | Director of Finance |  | Jumpstart workshops completed (technical evaluation to make us aware of what's available and compatibility issues etc.). The build of a core image has commenced. Expect to start deploying on end user devices from Q3.
Review server/applications hosting | Director of Finance |  | Not due to start yet. |  |  | N/A
Server software upgrade | Director of Finance |  | Not due to start yet. |  |  | N/A
Review wide area work | Director of Finance |  | Has started. Six upgrade orders have been placed. On-going analysis indicates that a further 10 links may need upgrading. Options to provide improved Internet and VPN access are being explored. A business case for change is being prepared. | Securing on-going revenue for upgrades.
Future telecoms options | Director of Finance |  | Requirements specification and options selection is almost complete. Significant effort being applied to understand current costs in detail. Discussions have occurred with external suppliers. Indicative costs suggest that moderate savings may be possible. By end July details will be available to confirm whether a business case exists - key decision point informing whether to proceed further.
ICT core competencies profiles | Director of Finance |  | This project is currently being scoped.
Using Our Estate Efficiently
Deliver FY13 capital programme | Director of Finance |  | FY13 capital programme of £32.4m. Capital expenditure of £3.2m at month 2 against the YTD plan of £3.5m, with the majority of spend against the Manor House and Highfield schemes. The final FY13 - FY15 Capital Investment Programme was approved at an exceptional board meeting on 26th June. Work is now progressing to develop the design and cost plans on a number of schemes. The programme is dominated by the Manor and Highfield redevelopment schemes. There are a number of schemes programmed to address CQC compliance works on the inpatient wards, along with £2m operational capital to address backlog & risk. |  | Capital investment is being prioritised to address high risks, through a group led by the Director of Nursing with representation from all service divisions. Residual risks being robustly managed.
Deliver the Manor House build in FY14 | Director of Finance |  | Full Business Case Approved (Trust and Monitor) Started on Site short list of Options for relocation agreed, full financial appraisals of options under way | Failure to locate properties with D1 use off site for CAMHS/SALT, Complex Needs and SCAS. This could impact on the land sales as currently located at Tindal and Manor parcels of land due to be sold. Failure to agree and implementation over clinical models/operations (New ways of working). De-commissioning and Commissioning Plan failure.
Carbon reduction commitment (CRC) | Director of Finance |  | A gap analysis of existing policy and procedural documentation is being completed to identify steps required to introduce an Environmental Management System ISO 14001. Introduction of an EMS will provide 'top down' structure to the Carbon Reduction initiative, identifying key responsibilities at all levels within the Trust. This will provide a platform to developing a Carbon Reduction Strategy to delivering the planned Carbon Reduction Targets and will link with the emerging Estates Strategy.
Reprovision of Orchard House Wycombe and Cotswold House, Oxford | Director of Finance |  | To be addressed within the trust state strategy. The principles of the Estate strategy have been agreed, next quarter will see engagement with divisions on specific estate issues including the provision of Orchard house Wycombe and Cotswold house | The ward is considered unfit for purpose & the reprovision of the service is being looked at as part of the Warneford SOC, old Highfield & Windrush Ward. | If this is successful, then CAMHS will stay in the building, but will need to find alternative accommodation by 31st March 2014. If the proposal is not successful, Oxford Health have indicated their willingness to work with the Council to source alternative accommodation and move before their lease end. One proposal currently being considered is to relocate Older Adults from Harlow House to Valley Centre, and Harlow House to be redeveloped to accommodate CAMHS. However, their long term aim is for CAMHS and SALT to be located together, and this building may currently be too small. However, with new ways of working and technology, the teams may be able to be accommodated. This will be considered further under the Estate Strategy.
Maintain and improve PEAT scores for cleanliness and catering | Director of Finance |  | Quarterly PEAT inspections have been completed by Modern Matrons and scores have achieved Trust target. Lead Soft FM Manager is keeping regular contact with the D of H to hear about the introduction of new cleanliness and environment inspections to gain early indication of scoring method and how patient led inspection will be carried out in the Mental Health setting.
Complete BREEAM assessment of Estate and provide programme to achieve rating of good to excellent | Director of Finance |  | The new Highfield (October 2012) and Manor Hse (October (2013) developments are targeted to provide BREEAM ratings of good or excellent. Breeam environmental assessments have been completed at Littlemore and Warneford sites and action is required to improve the rating of these two sites. Assessments of community hospitals are currently being completed. A gap analysis is being carried out to identify the work required to introduce ISO 14001 Environmental Management System.