## Sheet1
| All figures in £000 |  | FY13 |  | FY14 | [8 empty] | FY15 |  |  |  | FY16 |  |  | FY17 | FY18
Proj Ref | Project Name | Revised Plan | Outturn | Variance | Original Plan | FY13 Slippage | Allocated | FIC May Approved Plan | CPB Revisions Aug 6 | CPB Aug Revised Plan | CPB Revisions Oct 1 | CPB Revisions Nov 5 | Revised Plan | Plan | CPB Revisions Oct 1 | CPB Revisions Nov 5 | Revised Plan | Plan | CPB Revisions Nov 5 | Revised Plan | Plan | Plan | Notes
Strategic Projects
Approved (Business Cases agreed):
Stra014 | Manor House | 18610 | 14265 | 4345 | 12950 | 4345 |  | 17295 |  | 17295 | -800 |  | 16495 |  |  |  | 0 | [5 empty] | completion of existing committed scheme
Stra036 | Highfield | 5279.3028 | 5324.8 | -45.4972 |  |  | 100 | 100 |  | 100 | -50 |  | 50 |  |  |  | 0 | [5 empty] | completion of existing committed scheme; conclusion of final account
| Vaughan Thomas Ward | 150.001 | 91.4 | 58.601 |  | 90 | 850 | 940 |  | 940 |  | -190 | 750 |  |  |  | 0 | [5 empty] | environmental upgrades, approved business case
| Phoenix | 150.0045 | 28.9 | 121.1045 |  | 100 | 400 | 500 | -250 | 250 |  |  | 250 | 400 |  | -150 | 250 | [5 empty] | environmental upgrades, approved business case
| Phoenix Security Works | 360 | 176.6 | 183.4 |  | 183 |  | 183 |  | 183 |  |  | 183 |  |  |  | 0 | [5 empty] | external security improvements (fencing) approved BJ
| Wintle Ward | 50.003 | 43 | 7.003 |  | 7 | 200 | 207 |  | 207 |  |  | 207 | 700 |  | -500 | 200 | [5 empty] | environmental upgrades, approved business case
| Marlborough House MK (reception) | 199.9993 | 86.1 | 113.8993 |  | 550 |  | 550 |  | 550 | -250 |  | 300 |  |  |  | 0 | [5 empty] | medium secure standards compliance, approved business case
Stra024 | Clinical Trials Unit (phase 2) | 149.9989 | 142.1 | 7.8989 |  | 8 |  | 8 |  | 8 |  |  | 8 |  |  |  | 0 | [5 empty] | complete, final account
| Car Park Management | 490 | 258.3 | 231.7 |  | 240 |  | 240 |  | 240 |  |  | 240 |  |  |  | 0 | [5 empty] | existing scheme, approved BJ
| Clockhouse | 180 | 8.1 | 171.9 |  | 97 |  | 97 | -27 | 70 | -10 |  | 60 |  |  |  | 0 | [5 empty] | existing scheme, approved BJ
| Pharmacy | 149.9982 | 174.6 | -24.6018 |  | 20 |  | 20 |  | 20 |  |  | 20 |  |  |  | 0 | [5 empty] | complete, final account
| Warneford Infrastructure/reprovision | 150 | 67.5 | 82.5 |  | 83 |  | 83 | -33 | 50 |  |  | 50 |  |  |  | 0 | [5 empty] | complete, final account
| Forensic WELS | 100.0013 | 71.4 | 28.6013 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
[10 empty] | 0 |  |  | 0 |  |  |  | 0
| Marlborough House MK (Day Room) | 209.9982 | 159 | 50.9982 |  | 51 |  | 51 |  | 51 |  |  | 51 |  |  |  | 0 | [5 empty] | complete, final account
| Warneford Meadow | [5 empty] | 486 | 486 |  | 486 |  |  | 486 |  |  |  | 0 | [5 empty] | purchase of land adjacent to Highfield Unit, approved BJ
Allocated (Business Cases not yet approved):
| Windrush Ward | 49.9977 | 28.5 | 21.4977 |  |  | 1250 | 1250 | -950 | 300 | -100 |  | 200 | 1200 | -600 | 400 | 1000 | [5 empty] | part of service remodelling, City community hospital
| Fiennes Centre | [5 empty] | 75 | 75 |  | 75 |  |  | 75 | 250 |  | -250 | 0 | [5 empty] | part of service remodelling
Stra029 | Wenric | 50.0066 | 15.6 | 34.4066 |  |  | 200 | 200 |  | 200 |  |  | 200 |  |  | 300 | 300 | [5 empty] | compliance works
Stra037 | Woodlands | [5 empty] | 150 | 150 |  | 150 |  |  | 150 |  |  |  | 0 | [5 empty] | low secure standards compliance works
Stra060 | [9 empty] | 0 |  |  | 0 |  |  |  | 0
Stra064 | Eating Disorders Oxford (Old Highfield) | [5 empty] | 350 | 350 | -250 | 100 |  |  | 100 | 1100 | -1100 |  | 0 | [5 empty] | Awaiting decision on future use
| Thames House | [5 empty] | 150 | 150 |  | 150 |  |  | 150 |  |  |  | 0 | [5 empty] | low secure standards compliance
| Marlborough House MK Eaves | [5 empty] | 160 | 160 |  | 160 |  |  | 160 |  |  |  | 0 | [5 empty] | medium secure standards compliance
[10 empty] | 0 |  |  | 0 |  |  |  | 0
[10 empty] | 0 |  |  | 0 |  |  |  | 0
[10 empty] | 0 |  |  | 0 |  |  |  | 0
[10 empty] | 0 |  |  | 0 |  |  |  | 0
Stra072 | Wallingford CMHT | 99.9985 | 119.4 | -19.4015 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Stra067 | Marlborough House MK (environmental works) | 10 | -33 | 43 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Stra010 | [9 empty] | 0 |  |  | 0 |  |  |  | 0
Stra076 | Allen Ward | 10 | 0 | 10 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Stra011 | [9 empty] | 0 |  |  | 0 |  |  |  | 0
Stra065 | Cotswold House (wet rooms) | 109.9952 | 84.5 | 25.4952 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Stra055 | Warneford Switchgear | 1.66 | 1.7 | -0.04 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Stra059 | Marlborough House (seclusion & hard Room) | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Stra061 | Oxford Clinic (smoking rooms) | 0 |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Stra069 | Estate rationionalise/PCT community assets | 200.0022 | 119.3 | 80.7022 | 400 | 40 |  | 440 |  | 440 | -100 |  | 340 | 200 |  |  | 200 | [5 empty] | rationalisation of exisiting estate and space utilisation
| Corporate projects | [5 empty] | 100 | 100 |  | 100 | -20 |  | 80 | 150 | -50 |  | 100 | [5 empty] | including option appraisal of Trust HQ
| Dementia Environments | [6 empty] | 0 | 250 | 250 |  | 20 | 270 | 0 |  |  | 0 | [5 empty] | Enhancing Healing Environement, matched by Kings Fund/DoH funding
| Integrated Locality Hubs | [6 empty] | 0 |  | 0 |  |  | 0 | 500 |  |  | 500 | [5 empty] | part of service remodelling
| Forensic SOC | [6 empty] | 0 |  | 0 |  |  | 0 | 100 |  | -50 | 50 | 250 | 50 | 300 | 2500 | 2500 | service development (Littlemore and Oxford Clinic)
| Warneford SOC | [6 empty] | 0 |  | 0 |  |  | 0 |  |  |  | 0 |  |  |  | 250 | 500 | Warneford redevelopment
| Witney EMU | [6 empty] | 0 | 140 | 140 |  |  | 140 |  |  |  | 0 | [5 empty] | Provision of EMU
Subtotal | Strategic Projects | 26760.9674 | 21232.8 | 5528.1674 | 13350 | 5814 | 4471 | 23635 | -1120 | 22515 | -1330 | -170 | 21015 | 4600 | -1750 | -250 | 2600 | 250 | 50 | 300 | 2750 | 3000
Estates Operational & Risk Management
OPER001 | BBH Roof & Internal refurbs | 150 | 6 | 144 |  | 144 |  | 144 |  | 144 | -9 |  | 135 |  |  |  | 0 | [5 empty] | existing scheme, in progress
OPER002 | Rectory Rd refurbishment (SCAS - CDO) | 20 | 11.1 | 8.9 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 | [5 empty] | existing scheme, in progress
OPER003 | Access Control Installation (phased) | 200 | 261.4 | -61.4 | 300 |  | 238.6 | 238.6 |  | 238.6 | -39 |  | 199.6 |  |  |  | 0 | [5 empty] | existing scheme, in progress
OPER004 | Risk Reduction | 500.0009 | 251.8 | 248.2009 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
OPER005 | Green Transport Plan | 80 | 143.5 | -63.5 |  | 10 | 200 | 210 |  | 210 |  |  | 210 |  |  |  | 0 | [5 empty] | FY14 prioritised programme of works
OPER006 | Spend to Save (Sustainability Programme) | 200.0044 | 118 | 82.0044 |  | 35 | 200 | 235 |  | 235 |  |  | 235 |  |  |  | 0 | [5 empty] | FY14 prioritised programme of works
OPER007 | Risk reduction | 300 | 222.1 | 77.9 |  | 46 | 500 | 546 |  | 546 |  |  | 546 |  |  |  | 0 | [5 empty] | FY14 prioritised programme of works
OPER008 | M&E / Infrastructure (backlog) | 150.0045 | 155.8 | -5.7955 |  | 32 | 700 | 732 |  | 732 |  |  | 732 |  |  |  | 0 | [5 empty] | FY14 prioritised programme of works
Stra063 | Marlborough House MK (security/ fencing ) | 182 | 17.4 | 164.6 |  | 165 | 0 | 165 |  | 165 | -15 |  | 150 |  |  |  | 0 | [5 empty] | existing scheme, under review
|  |  |  | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog024 | Conversion of City Central to Outpatients (Warneford) | 3.2 | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog026 | Littlemore - adaptations to chapel |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog027 | Warneford - reception upgrade/safety works |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog029 | Oxford Clinic - additional fencing improvements | 22.7 | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog030 | Oxford Clinic - Conversion of SPA to staff room |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog031 | Oxford Clinic - vision panels to all patient rooms |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog034 | Thames Hse - replacement of locks, doors, frames etc |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog035 | Wenric Hse - ligature reduction works | 12.9 | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog025 | Kennington - evaluation of pharmacy supplies |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog028 | Littlemore - adaptations to shop/café |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog032 | Replacement drugs cupboards on all wards | 20.4 | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog033 | Stable-Doors to all medication rooms on wards |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Risk006 | Refurbishment of Wenric Ward Patient Bathrooms |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog036 | Refurbishment of Wenric Wards Patient Bathrooms |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog037 | Kimmeridge Wards - Security Upgrade | 46.4 | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog038 | Cotswold House - DSSA compliance (new en-suite bedroom) |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog039 | VT & Wintle - Landscaping & security improvements to garden |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog040 | Phoenix - security improvements (fencing & level 2 security windows) |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog050 | In Year Risk | 108 | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Prog054 | Skylight Replacements at the Fulbrook Centre | 38.5 | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Risk001 | Oxford Clinic - Fencing alterations & Additional Locks |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Risk003 | Woodlands - Alterations to Seclusion Suite |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Ict024 | Clinical System Interfacing |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Ict028 | Single sign-on |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Ict025 | Business Objects Upgrade |  | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Stra068 | Inpatient Wards | 9.4 | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
OPER009 | FY12 Carry over schemes | 38.4 | 0 |  |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
| Prior year carry over schemes | 300 | 228.9 | 71.1 |  |  | 200 | 200 |  | 200 |  |  | 200 |  |  |  | 0 | [5 empty] | existing schemes, in progress
| Unallocated |  |  |  | 1700 |  | 0 | 0 |  | 0 |  |  | 0 | 2000 |  |  | 2000 | 2000 |  | 2000 | 2000 | 2000 | FY15-FY18 programme of works
MEDI001 | Medical Equipment | 320 | 93.8 | 226.2 | 500 | 290 | 0 | 790 |  | 790 | -100 |  | 690 | 500 |  |  | 500 | 500 |  | 500 | 500 | 500 | FY14 programme of works and syringe drivers approved BJ
| Infection Control Compliance | [6 empty] | 0 | 350 | 350 |  |  | 350 |  |  |  | 0 | [5 empty] | Urgent essential compliance works
| Ligatures Compliance | [6 empty] | 0 | 375 | 375 |  |  | 375 |  |  |  | 0 | [5 empty] | Manchester Tool high-priorities
| Window Safety Programme | [6 empty] | 0 | 350 | 350 |  |  | 350 |  |  |  | 0 | [5 empty] | Prioiritise inpatient wards and patient areas on first floor
Subtotal | Estates Operational & Risk Management | 2401.9099 | 1509.8 | 892.2099 | 2500 | 722 | 2038.6 | 3260.6 | 1075 | 4335.6 | -163 | 0 | 4172.6 | 2500 | 0 | 0 | 2500 | 2500 | 0 | 2500 | 2500 | 2500
ICT Projects
Ict002 | PC Additions / Replacements | 550.0011 | 549.2 | 0.80107 |  |  | 800 | 800 |  | 800 |  |  | 800 |  |  |  | 0
Ict007 | Marlborough House telephony | 0 | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Ict027 | Server upgrades/replacements | 49.998 | 104 | -54.002 |  |  | 300 | 300 |  | 300 |  | -60 | 240 |  |  |  | 0
Ict029 | Network Upgrades | 149.9977 | 33.4 | 116.5977 |  | 117 | 63 | 180 |  | 180 |  |  | 180 |  |  |  | 0 | [5 empty] | existing works in progress
ICT033 | e-Fin upgrade |  | 0 | 0 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0 | [5 empty] | existing works in progress
Ict031 | Mobile Working Laptop Model | 450 | 45 | 405 |  | 405 |  | 405 |  | 405 |  | -205 | 200 |  |  |  | 0 | [5 empty] | existing works in progress
Ict032 | Mobile Enabling | 21.6245 | 21.7 | -0.07552 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
ICT036 | Business System Expansion | 50 | 0 | 50 |  | 50 |  | 50 |  | 50 |  | -50 | 0 |  |  |  | 0 | [5 empty] | FY13 project carried forward
ICT023 | Telehealth Pilot | 50 | 0 | 50 |  | 50 |  | 50 |  | 50 | -50 |  | 0 |  |  |  | 0 | [5 empty] | FY13 project carried forward
ICT034 | Windows/ Office Upgrade | 50 | 30.6 | 19.4 |  |  | 60 | 60 |  | 60 |  | 60 | 120 |  |  |  | 0
ICT035 | Strategic Telephoney | 30 | 12 | 18 |  |  | 150 | 150 |  | 150 |  |  | 150 |  |  |  | 0
| Improving IT | 0 | 0 | 0 |  |  | 30 | 30 |  | 30 |  | -30 | 0 |  |  |  | 0
| Unallocated | 0 | 0 | 0 | 1400 |  |  | 0 |  | 0 |  |  | 0 | 1400 |  |  | 1400 | 1400 |  | 1400 | 1400 | 1400 | FY14 programme being developed
Ict014 | eRostering | 80.0034 | 41.3 | 38.7034 |  | 3 |  | 3 | 36 | 39 |  |  | 39 |  |  |  | 0
Subtotal | ICT Projects | 1481.6246 | 837.2 | 644.4246 | 1400 | 625 | 1403 | 2028 | 36 | 2064 | -50 | -285 | 1729 | 1400 | 0 | 0 | 1400 | 1400 | 0 | 1400 | 1400 | 1400
Prog041 | Oxford Clinic Seclusion Room Enhancement | -0.81477 | -0.81477 | 0
Ict020 | CHO Enabling Works | -45.9608 | -45.9608 | 0
Risk004 | Woodlands - Environmental Works | -14.3858 | -14.3858 | 0
Ict022 | Homogenise/Expand IT Telephony | -0.178 | -0.178 | 0
Stra062 | Ashurst Ward (PICU) | -71.506 | -71.506 | 0
Stra057 | Marlborough House Swindon | -0.1268 | -0.1268 | 0
Prog052 | Seclusion Room Upgrade-Wenric Ward | -0.16731 | -0.16731 | 0
| IAPT | [5 empty] | 163 | 163 |  | 163 |  |  | 163 |  |  |  | 0 | [5 empty] | PDC funding receievd for IAPT project
| Prior Year Adjustments ( VAT & Accruals ) | -133 | -133.1395 | 0.13946 |  |  |  | 0 |  | 0 |  |  | 0 |  |  |  | 0
Ict030 | Data Warehouse (CUBE) |  |  | 0 |  |  | 50 | 50 |  | 50 |  |  | 50 |  |  |  | 0 | [5 empty] | existing scheme, approved business case
Unall | Unallocated | 320 | 0 | 320 | 2870 |  |  | 0 | 9 | 9 | -9 |  | 0 | 250 | -250 |  | 0 | 4470 |  | 4470 | 1970 | 1720 | funds available for future investment
[10 empty] | 0 |  |  | 0 |  |  |  | 0
Subtotal | FY13 Capital Projects (Ex PFI) | 30831.5019 | 23446.6605 | 7384.9413 | 20120 | 7161 | 8125.6 | 29136.6 | 0 | 29136.6 | -1552 | -455 | 27129.6 | 8750 | -2000 | -250 | 6500 | 8620 | 50 | 8670 | 8620 | 8620
| PFI | 395.1 | 395.1 | 0 | 380 |  |  | 380 |  | 380 |  |  | 380 | 380 |  |  | 380 | 380 |  | 380 | 380 | 380 | PFI financing costs capitalised as part of agreed accounting treatment
PFI001
Total | Capital Projects including PFI | 31226.6019 | 23841.7605 | 7384.9413 | 20500 | 7161 | 8125.6 | 29516.6 | 0 | 29516.6 | -1552 | -455 | 27509.6 | 9130 | -2000 | -250 | 6880 | 9000 | 50 | 9050 | 9000 | 9000
| Original LTFM May 2012 £m | May 2012 | 32.4 |  | 20.5 | [8 empty] | 7.1 | [8 empty] | FY13-FY15 | 60 | DRAFT PROG
| Current LTFM March 2013 £m | Current | 27.5 |  |  |  |  | 26.5 | [5 empty] | 7.1 | [8 empty] | FY13-FY15 | 61.1 | FY13-FY15 | 62.4884
[23 empty] | Total capex |  | FY13-FY18 | 89.4884
| Original LTFM £m | [16 empty] | 6.9 |  |  | 4.5 | 6.5 | FY13-FY18 | 77.9
| Current LTFM £m | [16 empty] | 6.9 |  |  | 4.5 | 6.5 | FY13-FY18 | 79
increase = cash from
PCT asset dep'n
[13 empty] | Net reduction: November v August Programme | [8 empty] | -4207

## Chart
Manor | 17.3
Approved | 3.5
Strategic | 2.8
Op Estate | 2.5
Medical | 0.8
IT | 2
Other | 0.6
29.5