BoD 113/2014

(Agenda item: 15(iv))

Finance and Investment Committee

Minutes of the meeting held on 
Monday, 14 July 2014 at 14:30 
in the Boardroom, Chancellor Court, Corporate Services, Oxford

| Present: |  |
| --- | --- |
| Lyn Williams | Non-Executive Director (the Chair/LW) |
| Stuart Bell | Chief Executive (the CEO/SB) |
| Martin Howell | Trust Chair (the Trust Chair/MH) |
| Mike McEnaney | Director of Finance (the DoF/MME) part meeting |
| Cedric Scroggs | Non-Executive Director (CS) |
| In attendance: |  |
| Sigrid Barnes | Senior Programme Manager (S. Barnes) part meeting |
| Claire Dalley | Director of Estates and Facilities (CD) part meeting |
| Paul Dodd | Deputy Director of Finance (PD) |
| Daniel Leveson | Head of Strategy and Programmes (DL) part meeting |
| Hannah Smith | Assistant Trust Secretary (Minutes) (HS) |

| 1. | Welcome and Apologies for absence |  |
| --- | --- | --- |
| a | Apologies for absence were received from Justinian Habner, Trust Secretary. |  |
| 2. a b | Minutes of the meeting held on 12 May 2014 The minutes of the meeting held on 12 May 2014 were approved as a true and accurate record. Matters Arising The Committee confirmed that the actions from the 12 May 2014 Summary of Actions had been completed: 3(d), (f) and (i); 11(a); and 13(d). CD joined the meeting. | Action |
| 3. a b c | Section 106 Manor and Tindal sites progress update CD provided an oral update on the Section 106 applications relating to the former Manor House and Tindal sites. The Trust was progressing the Tindal site viability assessment and Section 106 application first, as a test case, which would be followed by the former Manor House application which contained the same elements together with a revised planning application. The District Valuer had completed the review of the Tindal viability assessment and Section 106 application. The outcome of the review would be presented to the Council’s planning committee. The Trust would follow-up with the Council to ascertain when a decision would be made by the planning committee and whether the Tindal site Section 106 application would be approved with a reduced affordable housing element. Although the Tindal site would be ready for sale once the planning committee had made its decision, marketing would not commence until both sites were ready after the summer. The Chair asked about the likelihood of the planning committee accepting the proposal with reduced affordable housing. CD replied that other applications with reduced affordable housing had been accepted previously. The Committee noted the oral update. |  |
| 4. a b | Capital Programme Board (CPB) annual report 2013/14 CD presented Paper FIC 34/2014 which summarised the performance and work programme of the CPB during 2013/14. CD highlighted the risks to the capital investment programme including the risk that the former Manor House land sale would not realise full value in line with the business case. The decision to reduce the anticipated Manor House receipt had so far been supported by the findings of the District Valuer; it was more likely that the Trust would be able to achieve the revised anticipated receipt. The Committee noted the report. |  |
| 5. a b c d | CPB minutes – 01 April 2014, 06 May 2014 and 03 June 2014 The DoF and CD presented Papers FIC 35-37/2014, the CPB minutes for 01 April 2014, 06 May 2014 and 03 June 2014. CD confirmed that the Warneford Meadow transfer should take place very soon as the contract had now been signed. The CEO requested that regular reporting on the Townlands and Bicester developments be presented to this Committee. Under its Terms of Reference, this Committee monitored the work of the CPB, which monitored the Bicester and Townlands developments. CD reported on the delays to completion of the Bicester hospital development and the Trust’s communication with the CCG and NHS Property Services Ltd to which the Trust was awaiting a response. The Trust had been offered a move-in date in August 2014. CD highlighted remaining issues around: (i) the terms of the lease to reflect the shared occupancy nature of the building; and (ii) the increased operating costs of the new hospital, including increased staffing costs in order to safely staff the new building. The Committee noted that the Trust should not move in until cover for the increased operating costs had been agreed. Funding for extra staffing was critical in order to safely provide the new hospital. The Townlands development was not as far advanced as Bicester and was being informed by the learning from Bicester. The Trust was working with NHS Property Services Ltd to ensure that the issues which had arisen in relation to the Bicester development would not be replicated. The Committee received the minutes. CD left the meeting. | MME/ CD |
| 6. a b | Cashflow forecast to 31 March 2015 PD presented Paper FIC 39/2014 which showed actual results as at 31 May 2014 and a forecast to 31 March 2015. The Trust’s cashflow position remained positive over the period to March 2015 and the Trust’s Monitor Continuity of Service Risk Rating was anticipated to remain at level 3. PD highlighted the impact of slippage from the Manor land sale proceeds to April 2015 and noted the mitigation from the additional capital receipt forecast from the sale of Charter House in December 2014. PD drew attention to the assumptions around Income and Expenditure delivery. The Committee noted the report. |  |
| 7. a b | Treasury Management Annual Report FY14 PD presented Paper FIC 40/2014 which set out the annual report of the Treasury Management Function for FY14. PD highlighted the impact of the change in accounting policy, under the 2013/14 Monitor Annual Reporting Manual, on the calculation of the Public Dividend Capital (PDC) charge. This had significantly reduced the scope to make any external commercial deposits to ensure that the PDC charge was minimised. The Committee noted the report. S. Barnes joined the meeting. |  |
| 8. a b | Treasury Management Policy PD presented Paper FIC 41/2014, the annual review of the Treasury Management Policy. There were no changes recommended to the policy. The Committee AGREED that the existing Treasury Management Policy should remain in place with no revisions. |  |
| 9. a b c d e | Flexible Workforce Management Solution Business Case The DoF and S. Barnes presented Paper FIC AOB1/2014 which set out a proposal to establish a central flexible resourcing team to: improve the management of the Trust’s workforce, in particular the management of flexible staffing through the sessional, bank and agency workforce; improve the quality of care provided through an increased fill-rate of flexible shifts and increased quality in the flexible resource available; and reduce agency costs. The central flexible resourcing team would support the Trust to utilise its workforce in the most efficient manner and function as an internal agency provider. The central flexible resourcing team would also implement a new workforce management software solution to replace the current E-Rostering system. The DoF noted that the proposal had been considered by the Executive and recommended to the Finance and Investment Committee for approval. Although the capital cost of approximately £250,000 was below the Committee’s usual threshold of £500,000 - £2 million, the total revenue cost over five years was approximately £3.3 million (with anticipated cash releasing savings of £4.15 million). The Chair noted that taking into account the capital costs and the one-off revenue costs, the business case was within the remit of the Committee. The Chair asked what work had taken place to identify existing good practice in resourcing, in particular in the mental health and community health sectors. S. Barnes confirmed that good practice models had been discussed with other NHS Trusts operating in these sectors including those which already used the two key software suppliers and had in-house centralised workforce bank systems. The CEO declared an interest in the discussion through his role as Chair of the Picker Institute Europe; the Treasurer of the Picker Institute Europe was also Chief Financial Officer of one of the leading software suppliers of E-Rostering systems to the NHS. The Committee discussed the potential benefits of improved management of the Trust’s workforce and the DoF noted how this could enable the Trust to become more competitive as alternative contracts of employment were developed. The CEO noted that the development of an in-house workforce bank system would also enable the Trust to be able to operate the bank for other providers or to offer staff who may otherwise be TUPE-transferred away from the NHS an option to continue to work under NHS terms and conditions through membership of the bank. CS asked if the Trust had the capacity in the existing teams to manage the project. The DoF confirmed that S. Barnes would continue to be involved with the project and she had a HR and resource management background. |  |
| f g h | The implementation of the project would also supported by the E-Rostering team and additional recruitment. The Director of Informatics was supporting the software procurement although IT input was anticipated to be minimal as a standalone software system would be acquired. The Committee discussed the process to procure a workforce management system. The Chair asked whether a Single Action Tender Waiver (SATW) would be used, as referred to on page 32 of the business case. S. Barnes replied that a SATW was no longer the preferred route and a more formal procurement process would be followed. The Committee noted that for future business cases where the investment decision was relatively straight-forward, it would be useful to receive a shorter business case with a clear upfront summary of the financial analysis. After consideration, the Committee APPROVED the investment required to proceed with the Flexible Workforce Management Solution project. S. Barnes left the meeting. |  |
| 10. a b c | Utilisation of Reserves The DoF and PD provided an oral update on the utilisation of reserves and highlighted that a lower level of reserves was being held than in previous years. After allowing for the increased costs of the operation of the Whiteleaf Centre, Estates’ Planned Preventative Maintenance and the Next Generation Electronic Health Record, reserves were at approximately £3 million. The DoF highlighted the potential risks in relation to non-delivery of Cost Improvement Programmes, increased district nursing activity and PDC assumptions around the PCT estates transfer. The Committee discussed the issues around the PDC as a potential differential tariff deflator. The DoF noted that it would be useful to discuss this with other NHS Trusts first. The Committee requested that an update on the utilisation of reserves be included as a standing item at future meetings until further notice. The Committee noted the oral update. The DoF left the meeting. | MME/ PD |
| 11. a b | Oxford Pharmacy Store (OPS) performance report and OPS Board minutes 11 June 2014 The Trust Chair presented Paper FIC 42/2014 which set out the OPS commercial update and OPS Board minutes 11 June 2014. The Committee noted the report. DL joined the meeting. |  |
| 12. a b c d | Cost Improvement Programme (CIP) FY15 Month 2 performance report DL presented Paper FIC 38/2014 which set out FY15 CIP delivery against target. PD noted that the most recent figures from the closure of Month 3 were available to update the report. Against a FY15 target of £10.5 million, there were assured projects of £7.1 million which had been positively impacted through the mileage rate project and non-recurrent mitigations such as VAT refunds; additional mitigation was anticipated from the Estates rationalisation project and the cloud telephony IT project. Of the assured projects, £1.3 million was at risk. After the assured projects had been risk adjusted, £5.8 million was anticipated in forecast delivery with a remaining gap to target of £4.7 million. The Committee was assured that work was ongoing to develop CIPs and noted the importance of maintaining the quality of Trust services. However, the Committee emphasised the importance of continuing to make progress on CIPs especially as there were fewer reserves available to cover any shortfall than in previous years. PD reported that the Trust now submitted a monthly report to Monitor on CIP progress and had submitted its first report at the end of Month 2. If CIPs were not achieved to plan at the end of Month 6 then Monitor may require a more formal meeting. The Committee noted the report. |  |
| 13. a | Any Other Business None. |  |
| The meeting was closed at: 16:10. |  |  |
| Date of next meeting: - Monday, 08 September 2014: 14:30-17:00 |  |  |