## BAF
Board Assurance Framework Version: 21 July 2014
Ref | Risk description | Gross (inherent) risk rating |  |  | Controls (Mitigating actions) | Assurances (audit, monitoring, reporting, scrutiny) | Net (residual) risk rating |  |  | Gaps in controls/assurance and actions to address gaps | Exec Lead | Target risk rating |  |  | Delivery status and action updates
|  | I | L | R |  |  | I | L | R |  |  | I | L | R
1 | Strategic Objective 1: Driving Quality Improvement
1.1 | Failure to meet consistently quality standards for clinical care and to address variability across quality standards will result in poorer outcomes for patients and poorer patient safety and experience. | 4 | 5 | 20 | Controls include, but are not limited to: - models of care for every service with clear standards of care and standard operating procedures; - clinical and managerial leaders focusing on achieving standards; - day-to-day operational management structures, effective team working and application of Aston Team-based Working Approach; - optimal staffing levels; - processes to pick up exceptions/variations and for staff to raise concerns e.g. through the Whistleblowing policy; - improvement initiatives including Productive Wards, Safer Care programme, patient experience feedback, Patient Advice and Liaison Service (PALS) feedback; and - feedback of patient experience (received through a mixed medium of postal feedback and also real-time feedback through electronic devices). | Internal reporting including: - to the Board as (publicly available) standing items at each meeting on Quality and Safety, Quality and Performance and Workforce Performance; - new reporting was developed on staffing levels by the Director of Nursing and the Director of Finance which was submitted to the Board meeting in private in April and May 2014 and to the Board meeting in public in June 2014; - to the Integrated Governance Committee on clinical audit outcomes, Serious Incidents Requiring Investigation (SIRIs), complaints and PALS, patient experience and quarterly Quality Account updates. A new quality dashboard is being developed as part of the Quality Account which will be ready by September 2014; and - through Directorate Performance Reviews. | 4 | 3 | 12 | GAP: monitoring of the Safer Care programme and formal evaluation of Safer Care projects. ACTION: monitoring taking place through the Safer Care Board and reporting on safer care items to the Integrated Governance Committee and the Board. OWNER: Safer Care Lead | Director of Nursing and Clinical Standards | 4 | 2 | 8 | As at June 2014, monitoring processes established but challenge may be around adoption of methodology in Directorates to spread good practice across teams.
[10 empty] | GAP: Trust-wide learning from incidents. Although learning from incidents was effective within individual Directorates (formerly Divisions), this was not necessarily the case between and across Directorates. ACTION: to address poor attendance at previous Trust-wide learning events towards the end of 2013, the organisation of learning events has been reviewed. Learning events will remain Trust-wide to ensure that this is one way in which learning can be disseminated across Directorates but the Trust will explore merging incident, clinical audit, complaints and PALS learning events. This may provide opportunities to triangulate learning and identify themes and trends across these areas. Each Directorate now has a named link to support learning from incidents, complaints and clinical audit with attendance at Directorate governance meetings. The Corporate Risk and Incidents Team has been restructured to allow for more time to focus on Trust-wide learning. OWNER: Learning from Incidents Lead |  |  |  |  | A Trust-wide learning event took place on 06 June 2014 (in Buckinghamshire) to focus on the theme of carers and to incorporate learning from incidents, Patient Advice & Liaison Services (PALS) and clinical audit related to family, friends and carers. Each clinical directorate presented work underway to improve carer engagement and involvement. A further Trust-wide learning event is planned for around November 2014.
Internal learning from incidents, complaints and claims through: - weekly monitoring of SIRIs, complaints, claims and inquests at Clinical Standards & Joint Operations Weekly Review Meeting; - in order to improve information sharing since May 2014, the Clinical Standards Weekly Review Meeting and the Operations Senior Management Team (OPS SMT) meeting have joined together at the end of their respective meetings on Monday mornings; and - Directorate monitoring of IIR and SIRI reports to ensure clinical needs are being addressed/incidents learned from.
Controls also include strategies such as: - the Patient Experience Strategy for 2013-16. The aims of the strategy are to: provide an opportunity for every patient to give feedback about each service; use patient feedback to make improvements in the way care is delivered; share with patients and the public how their feedback has contributed to improvements; and give staff the support and resources to be able to gather and act on regular patient feedback. Monitoring by the new Patient Feedback to Improve Care Group, which met for the first time in November 2013; and - the revised Clinical Risk Management Strategy and Clinical Risk Assessment and Management training which now includes a component on suicide awareness.
[6 empty] | External assurance including: - CQC visits, surveys and inspections; - Parliamentary Ombudsman letters and themed reports in response to patient feedback and complaints; - monthly contract and quality meetings with Commissioners and closure meetings to review SIRIs. A detailed quality schedule has been agreed with Commissioners which includes a comprehensive range of quality indicators and measures which are reported quarterly in 2014/15; and - external accreditation, peer review processes and external national clinical audits. |  |  |  | GAP: wide variation in patient experience and outcomes across Directorates with learning to be triangulated. ACTION: monitoring through quarterly Patient Experience Update reports into the Integrated Governance Committee and reporting into Directorate Performance Review meetings. The BAF and risk registers are included on the agendas for Directorate Performance Review meetings for Directorate feedback against risks (since April 2014). Performance Reviews to be developed to test quality and improvement in care. Metrics to be developed for Directorate use to provide a more detailed measure with indicators and thresholds against the Impact and Likelihood ratings used in BAF and risk register risk ratings. OWNERS: Clinical Directors and Lead for Registration and Quality
[6 empty] | Other assurance through: Internal Audit; Essential Standards Audits; the Safety Thermometers; the Community Hospitals Assurance Tool and publication of the outcomes of the Friends and Family Test; the National Reporting and Learning System relating to incidents; and national confidential inquiries into homicides and suicides. |  |  |  | GAP: Quality Strategy to be created. ACTION: interim - development of Performance Reviews as referred to above to support improving consistency in quality. In progress - development of strategy by October 2014. OWNER: Head of Quality and Safety |  |  |  |  | Internal Audit Plan 2014/15 includes audits on Quality Strategy & Governance in Q1, CQC compliance in Q2/3, Specific Quality Risks in Q3 and Clinical Audit arrangements in Q4.
Monitoring of the Trust Risk Register for specific potential risks around quality and safety e.g. that patients may not be protected from harm (including through pressure ulcers and suicides in the community), the impact of increased activity levels on district nursing services in Oxfordshire and the 111 service in Oxfordshire.
Reporting against standards at team to Board level. Trend analysis and prompt response to variation. Walkarounds by staff, safety walkabouts, Board walkabouts and visits at least annually for each team. Reporting on Board walkabouts to the Institute for Healthcare Improvement as part of the South of England Patient Safety Collaborative.
1.2 | Failure of service models to deliver an integrated care pathway may mean that the individual needs of patients, including those with special needs and/or disabilities, are not met and that patients are not provided with appropriate access to, and transfer between, services. | 4 | 4 | 16 | Controls include but are not limited to: - service model review and modifications of pathways across Operations; - development of Operations Directorate Service Strategy; - ongoing work to develop care clusters/packages of care in mental health services incorporating evidence-based interventions; - service user and carer engagement in services included in the service modelling programme; - completed restructuring of Operations Directorate to provide for development of clinical leadership and for a social care lead in each directorate (completed by 31 March 2014); and - all service models have been developed and refined using bottom-up feedback over a 12 month period and with input from service users and carers, staff, partners, stakeholders and commissioners. | Reporting and monitoring at: Directorate Level, Operations Senior Management Team (OPS SMT) meeting, Executive and the Board. | 3 | 3 | 9 | GAP: impact of on-going contract negotiations for 2014/15 contracts; negotiations commenced in December 2013. ACTION: contracts for Buckinghamshire and Specialist Commissioning AGREED. All contract negotiations now concluded. Contract with Buckinghamshire CCG signed. Heads of terms agreed with Oxfordshire CCG and contract to be signed by week beginning 21 July 2014. OWNER: Chief Operating Officer | Chief Operating Officer | 3 | 2 | 6 | Gap relating to impact of on-going contract negotiations concluded; actions complete.
[6 empty] | Service Models for Adults and Older People developed over a period of 12 months with programme of consultation and development with clinicians, managers, service users, carers, third sector organisations, GPs, commissioners, Health Overview and Scrutiny Committee (HOSC) and other stakeholders. Presentations and workshops have been delivered over 12 months to stakeholders. |  |  |  | GAP: monitoring of effect of new service models. ACTION: KPIs were developed in December 2013 to monitor the effect of new service models to enable an approach of continuous improvement. KPIs have been linked in with business planning and the Quality Account. OWNER: Chief Operating Officer |  |  |  |  | The new Adult Service Model will be reviewed by September 2014.
[6 empty] | Good engagement with staff side. Adult Consultation completed with phased implementation led by patient safety considerations. Older People's (OP) model developed as above. |  |  |  | GAP: development of integrated locality teams with social care. ACTION: meeting with Director of Social Care and the CCG on 04 July 2014 to identify barriers to progression. OWNERS: Chief Operating Officer, Service Director and Clinical Director from the Older People's Directorate |  |  |  |  | Work taking place with Oxfordshire CCG, OUH and Oxfordshire CC for older people to agree an outcomes based single contract focused on the acute assessment/ admission and discharge/ reablement pathway (by September 2014). Cross-reference also to SO 4.4 and action updates against integrated partnership working.
GAP: delivery of integrated health and social urgent care pathways for Oxfordshire. ACTION: Outcomes Based Commissioning work with Oxford University Hospitals NHS Trust (OUH) - submission date 18 July 2014. Joint engagement process with public around delivery of integrated locality services. OWNERS: Service Directors and Clinical Directors for the 3 clinical directorates (Children & Young People's Services, Adult Services and Older People's Services)
1.3 | Failure to manage change effectively may compromise quality and safety during the transition from current to future service models and compromise staff and stakeholder engagement. | 4 | 4 | 16 | Controls include but are not limited to: programme structure including programme Board, workstream groups, programme risk register and robust contingency planning etc. | Comprehensive organisational change process for Adult and Older People's Services set out and consulted upon. Service user groups at locality level will continue to monitor implementation and contribute to ongoing development. Ongoing discussions with voluntary sector partners re operationalisation. Evidence of further service development through the consultation process. Quality of management of change process and communication and good joint working with Staff Side. | 2 | 2 | 4 | GAP: ongoing dialogue with partner organisations. ACTION: continue to develop strategic links with partner organisations with a view to further development of joint service delivery. Progress Outcomes Based Commissioning work for mental health and Older People. OWNERS: Chief Operating Officer, Service Directors and Clinical Directors for the 3 clinical directorates (Children & Young People's Services, Adult Services and Older People's Services) and Director of Business Development & Partnerships. | Chief Operating Officer | 2 | 2 | 4 | New Director of Business Development & Partnerships in post since June 2014.
[6 empty] | Refer back to Risk SO 1.1 above and the controls and assurances listed. The impact of change and change management on clinical care will be assessed through the assurances set out in SO 1.1. |  |  |  | GAP: ongoing dialogue with staff and staff side. ACTION: Service Directors and Clinical Directors appointed in the three Clinical Directorates. Consultation on restructuring of operations begun June 2014 for the Heads of Service posts. Appointments of Heads of Service posts anticipated by end of July 2014 and appointment of Associate Medical Directors by end of August 2014. OWNERS: Chief Operating Officer, Service Directors and Clinical Directors for the 3 clinical directorates (Children & Young People's Services, Adult Services and Older People's Services) |  |  |  |  | Anticipated completion of restructuring September 2014.
2 | Strategic Objective 2: Delivering Operational Excellence
2.1 | Failure to put effective governance (both corporate and clinical) arrangements in place may lead to: poor oversight at Board level of risks and challenges; strategic objectives not being established or structures not in place to achieve those objectives; or appropriate structures and processes not in place to maintain the Trust's integrity, reputation and accountability to its stakeholders. | 4 | 4 | 16 | Controls include but are not limited to: Constitution; Council of Governors and Board Standing Orders; Integrated Governance Framework; Standing Financial Instructions and Scheme of Delegation; Trust Risk Register and local risk registers at Divisional and departmental level; development of Risk Management Strategy; Board Assurance Framework; and the Trust Secretary. | Integrated Governance Committee and Audit Committee reviewing risks and key governance issues - reporting/escalating to Board as appropriate. | 3 | 2 | 6 | GAP: current Integrated Governance Framework (IGF) has been reviewed and some issues identified and to be addressed (mainly around the Integrated Governance Committee). ACTION: new IGF being drafted for presentation to the Board in July 2014 and will need to be evaluated post-implementation. OWNER: Trust Secretary | Chief Executive | 2 | 2 | 4 | IGF review completed and re-draft started. Board, Committees and relevant officers have been consulted. New framework to be presented to Board in July 2014.
[6 empty] | Internal Audit regular review of governance arrangements. |  |  |  | GAP: New Internal Auditors taking over review of governance arrangements; new reviews to commence. ACTION: Picked up in the process of agreeing Internal Audit plan 2014/15. OWNERS: Director of Finance and Trust Secretary |  |  |  |  | Internal Audit plan 2014/15 includes Quality Strategy & Governance audit and IGF audit in Q1/2 and Research Governance Framework audit in Q2/3.
Committee reporting to Board.
2.2 | Ineffective business planning arrangements that do not integrate activities at all levels of the Trust may lead to: the Trust being in breach of regulatory and statutory obligations; the Trust failing to achieve its annual objectives and consequently being unable to meet its strategic objectives. | 4 | 4 | 16 | The Strategic Framework sets out the key areas where appropriate plans and actions will deliver the Strategic Objectives. The business planning process, managed by the Programme Management Office (PMO), ensures that the top-down objectives and the bottom-up planned activities are aligned and that appropriate measures and targets are established to ensure that the Trust objectives can be met. The planning requirements of Monitor, including the Quality Account, are integrated within the Trust's business planning requirements. Senior leaders within the Trust and other key stakeholders are consulted on the business plan proposals. | PMO report regularly on business plan progress and achievement to Executive and Extended Executive meetings. Business planning is a key component of Extended Executive meetings with particular focus on progress review and plan themes development. Formal quarterly progress reports on the Business Plan are presented to the Executive and the Board for review of progress and assessment of achievement. The Council of Governors (CoG) is involved in the development of business planning and the CoG formally review and approve the Annual Business Plan. | 4 | 2 | 8 | GAPS include: - Communication of the objectives and Business Plan to all staff and stakeholders to be more timely. ACTION: summary of the key objectives and activities has been issued to all staff and stakeholders. - Insufficient consultation with stakeholders. ACTION: the schedule and process for developing the Business Plan has been amended to ensure all key stakeholders are identified and to allow time for effective consultation. - Key Performance Indicators (KPIs) not effectively aligned with strategic objectives and Business plans. ACTION: working with Performance teams, CUBE, and directorates to agree KPIs and method for reporting. - Business Planning process and strategic objectives not sufficiently aligned with individual PDR processes. ACTION: working with L&D and HR to align processes. | Director of Finance | 3 | 2 | 6 | KPIs continue to be developed in conjunction with PLICS, activity-based budgets and productivity management. PDRs in the process of review and will include alignment of personal objectives with those of the Trust.
3 | Strategic Objective 3: Delivering Innovation, Learning and Teaching
3.1 | Failure to fully realise the Trust's academic and Research and Development (R&D) potential may adversely affect its reputation and lead to loss of opportunity. | 3 | 3 | 9 | Controls include: - work to improve governance in R&D including through the Oxford Collaboration for Leadership in Applied Health Research and Care (Oxford CLAHRC); - membership of the Oxford Academic Health Science Network (Oxford AHSN) and the Oxford Academic Health Science Centre (Oxford AHSC) to maintain a prominent academic and R&D profile; and - expansion of the R&D team to improve patient recruitment into studies which would benefit current studies and future bids for new studies (including commercial studies). | Internal reporting including: - to the Board as (publicly available) 6 monthly reports on R&D covering KPIs on the number of patients recruited to studies and the number of studies underway/planned; and - R&D Committee reporting to the Clinical Effectiveness Committee (CEC). | 3 | 2 | 6 | GAP: quality of R&D reporting to the CEC. ACTION: reporting being developed and improvement anticipated by June 2014. OWNER: Head of R&D | Medical Director | 3 | 1 | 3 | As at June 2014, new R&D Operations Committee and R&D Strategic Group functioning and with improved reporting to CEC.
[6 empty] | External assurance through benchmarking of Trust performance by the Thames Valley Comprehensive Local Research Network. |  |  |  | GAP: R&D and Oxford CLAHRC governance improvement still ongoing and improvement anticipated by June 2014. ACTION: through CLAHRC board meetings chaired by the CEO and attended by the Medical Director. OWNERS: CEO, Medical Director and Head of R&D Finance |  |  |  |  | As at June 2014, an Operations Manager appointed to the CLAHRC, and CLAHRC board meetings taking place. Improvement ongoing and further progress anticipated by early 2015.
Internal Audit Plan 2014/15 includes Research Governance Framework audit Q2/3.
GAP: expansion of R&D team may still not result in increased/sufficient patient recruitment for studies. ACTION: outcomes to be kept under review. OWNER: Head of R&D
[10 empty] | GAP: governance arrangements in the Clinical Research Facility (CRF). Governance arrangements and supervisory structures to be reviewed. ACTION: the Director of Nursing discussed and agreed terms of review with CRF Director (April 2014) and review completed. OWNERS: Director of Nursing and CRF Director |  |  |  |  | Resolved as at June 2014, CRF governance structure revised and improved.
3.2 | Failure to be sufficiently innovative and leading edge in its practice may lead to the Trust not being able to keep current contracts or realise its potential in a competitive market. | 4 | 4 | 16 | Provision of high quality services through effective and innovative evidence-based service models e.g. in Mental Health and Interface Medicine, which result in good patient outcomes (see BAF risk SO 1.1). | In relation to the provision of high quality services, cross-reference to assurances under BAF risk SO 1.1. | 4 | 3 | 12 | GAP & ACTION: service remodelling complete but outcomes to be reviewed and evaluated by the Executive by the end of 2014. Also cross-reference to gaps/actions in controls/assurance for BAF risk SO 1.1. OWNERS: Chief Operating Officer and Executive Directors | Medical Director | 3 | 2 | 6 | Discussion at Board meeting 25 June 2014, action for the Executive to pursue.
[5 empty] | Restructuring of the R&D Committee to improve effectiveness and promote innovation through the establishment of a R&D Operational Committee and a R&D Strategic Group. | R&D reporting being monitored through Board and CEC (cross-reference to SO 3.1). |  |  |  | GAP: evaluation of outcomes ACTION & OWNER: Medical Director
[5 empty] | Work taking place through the Drugs and Therapeutics Committee around innovation, for example collaborative work with the University of Oxford which resulted in the first UK study of the use of ketamine intravenous infusions in people with treatment-resistant depression which was carried out by researchers at the Trust and the university which reported in April 2014. | The Drugs and Therapeutics Committee being monitored through CEC.
[5 empty] | Participation in the Oxford CLAHRC, Oxford AHSN and Oxford AHSC and use of these structures to improve and innovate systems around Dementia, Early Intervention, patient experience and patient reported outcomes, better management of medical-psychiatric comorbidity and patient self-management of chronic disease. | The Trust hosts the Oxford CLAHRC and is a partner in the Oxford AHSC with Oxford Brookes University, Oxford University Hospitals NHS Trust and the University of Oxford. Chief Executive's involvement at Board level with the Oxford CLAHRC (Chair of the CLAHRC Board) and Oxford AHSN.
[5 empty] | Development and maintenance of good relationships with commissioners through understanding and meeting their targets. | External assurance through contract review meetings with Commissioners to discuss outcomes and recent awards (from the Health Service Journal and the Guardian in 2013).
[5 empty] | Acting on Business Intelligence through the work of the Corporate Business Development Manager. | Internal assurance through weekly reporting to the Executive on the Business Intelligence pipeline. |  |  |  | GAP: quality of the Market Intelligence pipeline. ACTION: new Director of Business Development & Partnerships in post since June 2014 and progressing. Draft Business Development Strategy to be developed for September 2014. OWNERS: Chief Operating Officer, Director of Finance and Director of Business Development & Partnerships |  |  |  |  | Internal Audit Plan 2014/15 includes Service Innovation and Business Development audit for Q4.
Developing strategic partnerships within the NHS and indepedent sector, for example the work taking place with Oxfordshire CCG, Oxford University Hospitals Trust and Oxfordshire County Council for older people to agree an outcomes based single contract focused on the acute assessment/admission and discharge/reablement pathway (by September 2014).
4 | Strategic Objective 4: Developing Our Business
4.1 | Failure to successfully influence, manage and prepare for changes in commissioning arrangements and the wider Health and Social Care system may compromise the Trust's ability to deliver, maintain and win new contracts. | 5 | 5 | 25 | Ongoing strategic and operational engagement and joint working with all CCGs, local authorities and other partners including GP providers to understand strategic issues facing CCGs and provide input and support to delivering integrated services within the context of high levels of change within the health and social care systems. | Reporting through OPS SMT, Executive Team and Board. | 4 | 3 | 12 | GAP: instability in commissioning for Oxfordshire and Buckinghamshire and direct commissioning by NHS England of Specialised Services. ACTION: contracts now agreed. Outcomes Based Commissioning for mental health and Older People underway in Oxfordshire. OWNERS: Chief Operating Officer, Executive Directors and Service Directors | Chief Operating Officer | 3 | 3 | 9 | Gap relating to impact of on-going contract negotiations concluded.
Participation in key strategic, operational and contracting meetings by Service Directors, Clinical Directors and Chief Operating Officer
[5 empty] | Development of alliances and partnerships with other organisations, including the voluntary sector, to deliver services into the future. | Chief Operating Officer and the Executive reviewed management of the key contract meetings. |  |  |  | GAP: concern around the impact of the Better Care Fund (government pooled fund to promote integrated care) and limited engagement of providers. ACTION: ensuring engagement in national Better Care Fund dialogue at a national and local level. OWNERS: Chief Operating Officer, Director of Finance and Chief Executive
[10 empty] | GAP: changes in key personnel in CCGs. ACTION: engagement with CCGs. OWNERS: Chief Operating Officer and Executive Directors |  |  |  |  | New CEO in place at Oxfordshire CCG.
[5 empty] | Ability to deliver, maintain and win new contracts supported by service model review and development, restructuring of the Operations Directorate, new Whiteleaf Centre, Estates works at the Warneford and clinical engagement in contract meetings. | External assurance including: gateway review and collaborative planning with OUH; delivering on commissioners' strategic intent through intiatives such as moving to 7-day working via the service remodelling; and partnership approaches on Mental Health and OP services. |  |  |  | GAP: financial pressures between commissioners and central NHS management. ACTION: dialogue and engagement with Monitor. OWNERS: Chief Operating Officer, Executive Directors and Service Directors
[10 empty] | GAP: opportunity cost by not identifying or developing new strategic opportunities quickly and decisively within an agreed framework. ACTION: develop new strategic framework with guidelines for taking on new business and exploring new opportunities. OWNER: Director of Business Development & Partnerships |  |  |  |  | Board Seminar in September 2014 will consider business development opportunities in more detail.
4.2 | Non-delivery of CIP savings and productivity gains may lead to: failure to deliver the Trust's financial plans; additional scrutiny and intervention by Monitor; insufficient cash generation to fund future capital programmes. | 5 | 5 | 25 | Using the current Monitor framework for assessment, the risk of Monitor applying special measures would remain although this risk is reduced when taking into account the proposed assessment framework due to be introduced from October 2013 which focuses on liquidity ratios. | Monthly finance report (including detail on CIPs) on Board and Executive agenda (weekly item) Monthly finance report to Operations SMT. Directorate monthly monitoring of plans. Operations SMT members attend monthly CIP meeting. Robust project management and review/reporting in place for planned Directorate schemes. | 4 | 4 | 16 | GAP: update required against outcome of review of areas of opportunity based upon value and the nature of the costs from January 2014. Cross functional teams were to be assigned to the significant opportunities to increase resource and responsibility for delivery. Each theme leader to update Extended Exec meeting on progress monthly. | Director of Finance | 4 | 2 | 8
[5 empty] | Directorate CIP schemes agreed and subject to strict project management controls and monthly reporting. Operations SMT agreement regarding mitigations or replacement schemes for underperforming plans. Work commenced on planning for FY14 CIP. Five major themes identified for 13/14 with Executive leads identified for each. Work streams have begun to plan out in detail. |  |  |  |  | GAP: the capability to establish, measure and compare productivity to be expedited to identify opportunities and to provide the basis for health system-wide strategic discussions.
GAP: 3 major CIPs (around productivity, Estates and HR) to progress, evaluate whether to pursue and review to ensure duplication avoided. ACTION: workshop scheduled for mid-April to consider productivity CIP.
4.3 | Failure to ensure patients and carers are involved in managing and leading on their own care could lead to compromising patient outcomes and not delivering sustainable health care. | 4 | 4 | 16 | Controls include but are not limited to: - Trust-wide Carers' Strategy; - well-established controls in psychological services; - service user groups in place on locality basis to provide ongoing input to service development for Adult services; - assessment processes within new Adult service models include carers' assessment, housing, employment and well-being of service users; - work on outcomes with patients and carers is part of the implementation of clusters in mental health and part of the service remodelling; - technological developments such as OXTEXT for patient self-monitoring of mood and services such as CAMHS using facetime to connect with patients etc.; and - as part of the implementation of the Next Generation Electronic Health Record, a work programme is due to commence on engaging patients with their electronic plans and records. | Internal and External assurances include: - involvement in developing care plans is monitored as part of Care Programme Approach metrics and reported to Commissioners; - the CQC monitors whether care plans have been shared with patients in mental health wards; - reporting to Commissioners in 2014 will include some quality indicators relating to patient and carer involvement in care planning; - the Trust has signed up to the Triangle of Care (the Carers Trust national scheme for improving outcomes for carers accessing mental health services) which recommends better partnership working between services users and their carers and organisations; and - each Directorate has Carers' Strategy action plans and progress updates on the Trust-wide Carers' Strategy are provided to the Board, most recently to the public Board meeting in June 2014 (which included detail of the progress made in Directorates and other operational areas regarding Carers' Strategy action plans, listening to Carers and learning to improve services for Carers). | 3 | 3 | 9 | GAP: Electronic Health Record replacement project ongoing and the work programme to engage patients with their electronic plans to commence as part of the implementation of the project. The replacement needs to take place first to build in capability. ACTION: progress replacement of Next Generation Electronic Health Record. Replacement will commence August 2014 and progress through to June 2015. OWNERS: Director of Informatics, Health Informatics Development Manager, Director of Finance | Director of Nursing and Clinical Standards | 2 | 3 | 6 | The Trust-wide learning event on 06 June 2014 focused on the theme of carers and incorporated learning from incidents, PALS and clinical audit related to family, friends and carers. Each clinical directorate presented work underway to improve carer engagement and involvement. The event also raised the profile of the Carers strategy and the work planned within the framework of the Triangle of Care.
GAP: strategy on Patient and Public Involvement, to involve patients in their own care and clinical care planning as well as general involvement activities, to be developed. Ability to evidence and systematically demonstrate Trust-wide, as opposed to local, action taking place to involve patients and carers in managing and leading on their own care to be considered as part of strategy development. ACTION/OWNERS: to be discussed between the Director of Nursing, Trust Secretary and Head of Communications & Engagement.
New Head of Communications & Engagement in post since 10 March 2014. The way forward on strategy on Patient and Public Involvement may involve Extended Executive or Senior Leaders' meeting.
4.4 | Failure to work collaboratively and effectively with external partners may compromise service delivery and stakeholder engagement. | 4 | 4 | 16 | Controls include but are not limited to: - Section 75 agreements in place for Oxfordshire and Buckinghamshire; - developmental work with Police colleagues e.g. joint working with Thames Valley Police on mental health street triage and Section 136 suites; - the development of the Multi-Agency Safeguarding Hub (MASH) in Oxfordshire to bring together Health, Social Services, the Police, Education and Youth Offending services in an integrated multi-agency team to share information appropriately and securely on children or young people in order to take timely and appropriate action to safeguard them from harm; and - development of Mental Health Crisis Concordat across Thames Valley by December 2014 to improve outcomes for people experiencing mental health crisis through local partnerships of health, criminal justice and local authority agencies. | Monitoring and collaboration through Section 75 Joint Management Groups (JMGs) in place in both Oxfordshire and Buckinghamshire. Oxfordshire now has service user representation and quarterly joint meetings with the commissioning JMG. | 3 | 3 | 9 | GAP: formal partnership agreements between NHS and voluntary sector organisations to implement integration with social care for OP physical health services subject to review and, if appropriate, sign-off by the Executive and the Board. ACTION: approach to Mental Health Outcomes Based Commissioning and Older People's Outcomes Based Commissioning agreed by the Boards of the Trust and OUH. Submission to Oxfordshire CCG 18 July 2014. OWNERS: Chief Operating Officer, Director of Finance, Service Directors and Clinical Directors of 3 clinical directorates (Children & Young People's Services, Adult Services and Older People's Services) | Chief Operating Officer | 3 | 2 | 6 | Work taking place with Oxfordshire CCG, OUH and Oxfordshire CC for older people to agree an outcomes based single contract focused on the acute assessment/ admission and discharge/ reablement pathway (by September 2014). Cross-reference also to SO 1.2 and integrated care pathway development. - The MASH is due to be implemented in Oxfordshire for children in September 2014 and for adults in January 2015.
[6 empty] | Problems in Practice Group reviewed, links to JMG to ensure health and social care and commissioning approach to Section 136 issues. Police and health triage pilot in Oxfordshire begun with reporting into the JMG and the Integrated Governance Committee. By April 2014, a decrease in section 136 admissions in Oxfordshire had been noted following the impact of the street triage project with the police, whilst the number of admissions to wards had increased which indicated the improved appropriateness of section 136 use. |  |  |  | GAP: development of Mental Health Crisis Concordat across Thames Valley to be achieved by December 2014. ACTIONS: Draft action plans for Oxfordshire and Buckinghamshire to be produced by August 2014 in preparation for Thames Valley wide conference in September 2014. Local plans to be approved through Well-Being Boards and published by 31 December 2014. OWNER: Chief Operating Officer
New service models include integration with social care for Older People's (OP) physical health services. Partnership agreements to be put in place between NHS and voluntary sector organisations to implement.
4.5 | If the Trust does not proactively engage with its membership, patients and the wider public then this may compromise its ability to listen and respond to feedback, involve stakeholders proactively and communicate effectively and transparently. | 3 | 3 | 9 | Council of Governors. | Annual report and reports for Council of Governors demonstrate engagement with FT members. | 2 | 3 | 6 | GAP: Trust approach to patient involvement/ engagement in own care (rather than involvement in service redesign etc) to be reviewed and refreshed (with updated reporting to the Integrated Governance Committee). ACTION: for the new Head of Communications & Engagement by September 2014. OWNERS: Director of Nursing, Chief Executive, Trust Secretary and Head of Communications & Engagement. All owners are meeting to discuss and agree process and ownership. | Chief Executive | 2 | 2 | 4 | Head of Communications & Engagement in post since 10 March 2014; work underway to complete actions.
[5 empty] | Communications function part of the Chief Executive's team. | Involvement update report produced to Integrated Governance Committee for monitoring.
[5 empty] | Establishment of local/divisional patient groups. | Service redesign project briefs include engagement element. |  |  |  | GAP: Strategy on Patient and Public Involvement, to involve patients in their own care, to be developed (as per gap/action against risk SO 4.3 above).
[5 empty] | Complaints service, PALS surgeries and results of patient experience surveys. | Internal reporting including to the Integrated Governance Committee on complaints, PALS and patient experience; and weekly monitoring of complaints at Clinical Standards Weekly Review Meeting.
5 | Strategic Objective 5: Developing Leadership, People and Culture
5.1 | Inadequate plannning for current and future workforce requirements, including number of staff, calibre, skills and training, may lead to: impaired ability to deliver the quantity of healthcare services to the required standards of quality; inability to achieve the business plan and strategic objectives. | 5 | 3 | 15 | Controls include but are not limited to: - robust recruitment processes; - on-going staff development through resources such as the Learning and Development training matrix which defines subject areas and frequency of training for staff and provides access to appropriate e-learning; - the Performance Framework including the Performance & Development Review Policy and supporting process; - Directorate workforce plans are linked to Business plan/savings plans with regular processes for review; - Senior HR Business Partners are trained in the principles and approach to the Trust workforce planning process developed with input from L&D and Finance; - workforce planning also included as part of service remodelling which will then inform workforce plans for the next three years. | Reports to individual managers, teams, directorates and to the Board enable monitoring of leavers, vacancies and recruitment, absence/sickness and training status. Information is reviewed and actions determined at monthly Directorate senior management meetings and the weekly Operations SMT. The HR senior management team hold a performance review each month. | 2 | 3 | 6 | GAP: service remodelling complete but outcomes to be reviewed; new staffing ratios and skill mix anticipated to lead to revised workforce plans with subsequent recruitment plans, greater input into staff/career development plans, analysis of promotion opportunities. Development of CUBE anticipated to remove basic number crunching allowing focus on workforce planning in greater detail and with greater frequency in addition to better correlation of a more diverse set of metrics. | Director of Finance | 2 | 2 | 4 | Close involvement of HR with the service remodelling projects. Improved data quality and detail enabling high level correlation. Development of automated reports through the CUBE is underway.
Internal Audit plan 2014/15 includes HR audit with scope to cover workforce planning and key supporting HR processes during Q2.
Analysis of leaving questionnaires. Workforce Development manage training programmes for Health Visitors in line with plan, District Nurses and SHNs. Medical staffing workforce plan started.
5.2 | Failure to put in place a coherent and co-ordinated structure and approach to leadership development may jeopardise the development of robust clinical and non-clinical leadership to support service delivery and change and the Trust becoming a clinically-led organisation. |  |  |  | Controls include but are not limited to: - service model review and modifications of pathways across Operations (cross-reference to SO 1.2 and the risk against failure to deliver integrated care); - completed restructuring of Operations Directorates to provide for development of clinical leadership and for a social care lead in each directorate (completed by 31 March 2014); and - the Strategic Organisational Development Lead. |  |  |  |  | GAP: coherent Trust-wide learning from existing leadership development projects such as Aston Team Working. Localised good performance and good practice may not be picked up across the Trust. Although it may not always be necessary or appropriate for all Trust-wide learning in this area to be consistent, as opposed to tailored to meet specific leadership development requirements, it should be more coherent and delivered with more purpose. Unwarranted variation without justification may be a gap rather than variation itself. | tbc |  |  |  | As at July 2014, the Director of Finance, the Medical Director, the Chief Operating Officer and the Deputy Director of Nursing to meet (by the end of August) to develop the controls, assurances, gaps and actions against this risk further.
[10 empty] | GAP: Cross-reference also to SO 1.1 and the gap against Trust-wide learning from incidents and the actions, including learning events, taking place to address this. ACTION: as per SO 1.1 OWNERS: Learning from Incidents Lead and Director of Nursing and Clinical Standards |  |  |  |  | The new Adult Service Model will be reviewed by September 2014. Cross reference to SO 1.2
GAP: co-ordinated direction of career pathways to steer staff to gain wider experiences.
6 | Strategic Objective 6: Getting the most out of Technology
6.1 | Incomplete and inaccurate data and records, both clinical and operational, may lead to: less effective planning and decision-making; lesser control over service safety and quality; lesser ability to drive improvements in safety, quality and productivity. | 4 | 5 | 20 | Consolidate corporate data and key metrics in the datawarehouse where metric definitions can be maintained and automated integrity checks applied. | Regular review of overall data quality to be implemented via the CUBE on prioritised data sets. | 3 | 4 | 12 | GAP: core systems data collection compliance and quality requires significant improvement. | Director of Finance | 3 | 3 | 9 | Data inventory and priorities being established and the quality of the data reviewed.
[5 empty] | A check and approval process to be in place for all key reports and data extracts. | Audits conducted on data quality and information. Internal Audits as part of the 2013/14 plan were carried out on data pseudonymisation and the CUBE. |  |  |  | GAP: automated data checks in the core systems to be more widely used.
[5 empty] | Contract KPI reports to commissioners to be reviewed jointly by Services and Contracting prior to issue. |  |  |  |  | GAP: data quality reporting to be standardised and actions taken to remedy shortcomings. |  |  |  |  | Internal Audit Plan 2014/15 includes IT risk identification audit Q1.
6.2 | Failure to meet the key objectives of the project to replace the Electronic Health Record system may lead to: inaccurate patient records; inefficient use of clinicians' time; less safe and lesser quality of care; increased cost of operation through lost opportunities to improve productivity. | 4 | 3 | 12 | Ensure actual end users are involved in the construction of the specification of requirements and selection of the solution. | A formal Project will be established using the established Prince2 methodology. The Project Executive will be the Trust's Chief Executive Officer. A gateway process to be included. | 4 | 2 | 8 | GAP: best practice project controls to be in place to address the likelihood of this risk materialising. | Director of Finance | 3 | 2 | 6 | The controls are being applied to the Project. The detailed implementation methodology and plan is being developed.
Approval of the final specification of requirements will occur at many levels including: clinical, Divisional management and Executive Team.
Use competitive dialogue as the means of procurement as this allows prospective suppliers to gain a detailed understanding of the Trust's problem areas, needs and objectives.
Ensure prospective suppliers commit to delivering against the processes of care (scenarios), Trust objectives and required benefits, and not just system 'widgets'; these commitments will form part of the formally agreed contract with the preferred supplier.
7 | Strategic Objective 7: Using our Estate efficiently
7.1 | Facilities being unsuitable or unfit for purpose may lead to: increased risk to patient safety; lesser quality of care and patient experience; increased cost of operation; breach of statutory requirements. | 5 | 5 | 25 | Controls include: - statutory compliance monitoring and reporting in place; - risk register established to identify significant risk and identify levels of investment required; - fire risk assessments being updated; - planned works to mitigate ligature risks in progress; - PLACE (Patient-Led Assessments of the Care Environment) inspections completed and resultant action plans are developed; and - Estates Strategy in place having been approved by the Board in November 2013. | CQC Compliance is submitted to the Service and Estates QuIC (this includes statutory compliance); Progress re health and safty works i.e. ligatures/CAS alerts are reported to the Safety Committee; Progress re delivery of capital projects required to reduce risks are reported to the Captial Control Group and Capital Programme Board | 5 | 3 | 15 | GAP: limited PPM works undertaken due to budgetary pressures and lack of operational maintenance know-how. ACTION: department restructure is being developed; including review of new methods of working. OWNER: Director of Estates & Facilities | Director of Finance | 3 | 3 | 9 | Completed review and restructure of department and review of PPM plan. Extended Executive in June 2014 agreed that the PPM plan be included in the budget for FY15 and going forwards.
[6 empty] | Estates Strategy is monitored via 6 monthly reports to the Finance and Investment Committee. |  |  |  | GAP: incomplete information on statutory compliance of rented properties where the obligation sits with the landlord. ACTION: establish a register and process for regular update. OWNER: Director of Estates & Facilities |  |  |  |  | Estates & Facilities business plan for FY15-17 developed including workstreams for: providing safe and secure environments through risk-based prioritisation of investment; a new CAS alert process; establishing a PPM programme; undertaking regular surveys of properties; developing a property database; providing assurance through a detailed CQC Standard 10 assessment; establishing a Senior Estates and Facilities meeting and working with the Services & Estates Committee and performance meetings (monthly and quarterly).
GAP: no Life Cycle replacement programme /delivery in place to prevent unnecessary failures. ACTION: LC programme and associated capital investment plan to be developed. OWNER: Director of Estates & Facilities
GAP: incomplete knowledge of the condition of the estate. ACTION: estate to be surveyed and asset lists to be developed. OWNER: Director of Estates & Facilities
GAP: the Health and Safety Executive issued the Trust with an Improvement Notice in relation to the adequacy of window restrictors. In response, window restrictors have been strengthened. However, further action is required to improve the arrangements to control the risk of patients falling from windows, including a review of relevant policies and procedures. ACTION: compliance date for the Improvement Notice is 14 May 2014. The Risk and Estates Teams are working together to ensure compliance before this date. This is also subject to weekly monitoring by the Executive. OWNER: Director of Estates & Facilities

## Risk Matrix
Risk matrix (since April 2012)
|  | Likelihood |  |  |  |  | Risk Rating (R) = Impact (I) x Likelihood (L)
|  | 1 | 2 | 3 | 4 | 5
|  | Rare | Unlikely | Possible | Likely | Almost certain
Impact | 5 Catastrophic | 5 | 10 | 15 | 20 | 25 |  | Extreme risk
| 4 Major | 4 | 8 | 12 | 16 | 20 |  | High risk
| 3 Moderate | 3 | 6 | 9 | 12 | 15 |  | Medium risk
| 2 Minor | 2 | 4 | 6 | 8 | 10 |  | Low risk
| 1 Negligible | 1 | 2 | 3 | 4 | 5
Impact/Consequence
A guide to the definitions for the impact/consequences, taken from the National Patient Safety Authority (NPSA) definitions:
Potential Consequence |  | Potential impact on individuals |  |  | Patient experience/potential impact on organisation |  |  | Adverse publicity
5 Catastrophic |  | Incident leading to death Multiple permanent injuries or irreversible health effects An event which impacts on a large number of patients |  |  | Totally unacceptable level or quality of treatment/service Gross failure of patient safety if findings not acted on Inquest/ombudsman inquiry Gross failure to meet national standards |  |  | National media coverage with >3 days service well below reasonable public expectation. MP concerned (questions in the House) Total loss of public confidence
4 Major |  | Major injury leading to long-term incapacity/disability Requiring time off work for >14 days Increase in length of hospital stay by >15 days Mismanagement of patient care with long-term effects |  |  | Non-compliance with national standards with significant risk to patients if unresolved Multiple complaints/ independent review Low performance rating Critical report |  |  | National media coverage with <3 days service well below reasonable public expectation
3 Moderate |  | Moderate injury requiring professional intervention Requiring time off work for 4-14 days Increase in length of hospital stay by 4-15 days RIDDOR/agency reportable incident An event which impacts on a small number of patients |  |  | Treatment or service has significantly reduced effectiveness Formal complaint (stage 2) complaint Local resolution (with potential to go to independent review) Repeated failure to meet internal standards Major patient safety implications if findings are not acted on |  |  | Local media coverage long-term reduction in public confidence
2 Minor |  | Minor injury or illness, requiring minor intervention Requiring time off work for >3 days Increase in length of hospital stay by 1-3 days |  |  | Overall treatment or service suboptimal Formal complaint (stage 1) Local resolution Single failure to meet internal standards Minor implications for patient safety if unresolved Reduced performance rating if unresolved |  |  | Local media coverage short-term reduction in public confidence Elements of public expectations not being met
1 Insignificant |  | Minimal injury requiring no/minimal intervention or treatment. No time off work |  |  | Peripheral element of treatment or service suboptimal Informal complaint/inquiry |  |  | Rumours Potential for public concern
Likelihood
Likelihood of occurrence/reoccurence:
1 Rare | Probably never happen/recur
2 Unlikely | Do not expect it to happen/recur but is possible
3 Possible | May happen or recur occasionally
4 Likely | Will probably recur but not a persistent issue
5 Certain | Will undoubtedly happen/recur, possibly frequently

## Guidance
Guidance for completing Board Assurance Framework
Strategic Objectives | The Trust's current strategic objectives: 1) Driving Quality Improvement 2) Delivering Operational Excellence 3) Delivering Innovation, Learning and Teaching 4) Developing our Business 5) Developing Leadership, People and Culture 6) Getting the most out of Technology 7) Using our Estate efficiently
Ref | Risk identifier reference number
Risk description | Specifies the cause of the risk, what the risk/issue is and the possible consequences. A risk is the possibility that an event will occur and adversely affect the achievement of objectives.
Gross/inherent risk rating | Uses the Risk Matrix to score the risk on an inherent basis as it currently appears (before controls or assurances) for: Impact (I) x Likelihood (L) = Risk Rating (R)
Controls (mitigating actions) | Policies, procedures and practices in place to reduce the likelihood of the risk occurring or mitigate the risk if it does occur
Assurances (audit, monitoring, reporting, scrutiny) | Where evidence can be gained about how well the controls are working and what the evidence shows. For example:
| Internal Sources of Assurance | External Sources of Assurance
| Internal Audit | External Audit
| Key Performance Indicators | NHS Litigation Authority
| Performance reports | Monitor
| Committee reports | CQC reviews
| Local counter-fraud work | Royal College visits
| Clinical Audit | Deanery visits
| Staff satisfaction surveys | External benchmarking
| Staff appraisals | Patient Environment action team reports
| Training records | Accreditation schemes
| Training evaluation reports | National and regional audits
| Results of internal investigations | Peer reviews
| Serious untoward incident reports | Feedback from service users
| Complaints records | Feedback from commissioners
| Infection control reports | External advisors
| Declarations to CQC | Local networks
Information governance toolkit self-assessment
PALS reports
HR reports
Internal benchmarking
Policy evaluation or implementation reports
Net/residual risk rating | The residual level of risk remaining if all identified controls are in place and active. Also uses the Risk Matrix to score the risk for Impact (I) x Likelihood (L) = Risk Rating (R)
Gaps in controls/assurance and actions to address gaps | Where there are failures to put effective controls in place or to gain evidence about their effectiveness
Exec Lead | Executive Director who is risk owner
Target risk rating | The realistically acceptable level of risk the Trust is willing to accept in pursuit of its objectives (i.e. the risk appetite or tolerance). Failure to define risk appetite could result in taking on too much risk to achieve objectives or not enough to seize opportunities. Also uses the Risk Matrix to score the risk for target Impact (I) x Likelihood (L) = Risk Rating (R)
Delivery status and action updates | Overall status of the actions planned to mitigate the risk and progress to target for risk reduction e.g. on target, good progress, poor progress