## BAF
Board Assurance Framework PUBLIC Version: 19 January 2016
Ref | Risk description | Gross (inherent) risk rating |  |  | Controls (Mitigating actions) | Assurances (audit, monitoring, reporting, scrutiny) | Net (residual) risk rating |  |  | Gaps in controls/assurance and actions to address gaps | Exec Lead | Target risk rating |  |  | Delivery status and action updates
|  | I | L | R |  |  | I | L | R |  |  | I | L | R
1 | Strategic Objective 1: Driving Quality Improvement Goals: patients will be safe from harm; patients will achieve the outcomes they want; and patients and carers will have excellent experiences
1.1 | Failure to: (i) meet consistently quality standards for clinical care; (ii) address variability across quality standards ; or (iii) reconcile conflicting quality standards or guidance, will result in poorer outcomes for patients and poorer patient safety and experience. | 4 | 5 | 20 | Patient experience controls include, but are not limited to: - Patient Advice and Liaison Service (PALS) feedback; - feedback of patient experience (received through a mixed medium of postal feedback and also real-time feedback through electronic devices); - the Patient Experience Strategy for 2013-16. The aims of the strategy are to: provide an opportunity for every patient to give feedback about each service; use patient feedback to make improvements in the way care is delivered; share with patients and the public how their feedback has contributed to improvements; and give staff the support and resources to be able to gather and act on regular patient feedback; - development of strategic framework for patient participation/ involvement/ engagement; and - the Caring and Responsive quality sub-committee and the Quality Committee. | Patient experience monitoring by the Patient Feedback to Improve Care Group. The Group's objective is to ensure senior leadership on embedding collection and use of patient feedback across the Trust by monitoring the implementation of objectives from the Patient Experience Strategy. The Group has reported progress quarterly to the Services and Estates Committee (SEC), the Integrated Governance Committee (IGC) and the Board. From 2015, the IGC and the SEC have been replaced by the Quality Committee and new Caring and Responsive quality sub-committee with reporting being developed through the Caring and Responsive quality sub-committee. Annual reporting on patient and carer experience will be provided to the new Quality Committee and was provided at the Quality Committee meeting on 17 July 2015. On a quarterly basis the Board also receives Quality Reporting with a particular focus on Patient Experience - most recently in June 2015 and October 2015. | 4 | 3 | 12 | GAP (patient experience assurance): the progress being made against well-established themes and areas for improvement in patient experience. The need to potentially invest further resources or realign resources around quality improvement and to drive forward plans such as the development of the new Patient Engagement and Involvement Strategy. The impact upon other priorities if more emphasis and resources are given to patient experience and involvement. ACTION: monitoring through the work of the Patient Feedback to Improve Care Group and reporting into Directorate Performance Review meetings and the new Caring and Responsive quality sub-committee. Monitoring through the Board and regular reporting on patient experience. Membership of the Caring and Responsive quality sub-committee includes, but is not limited to, Directorate patient experience leads (for each clinical Directorate) and the Trust Patient Experience Lead. Cross-reference also to gap below and development of an overarching strategic framework for patient participation/ involvement/ engagement. OWNERS: Service and Clinical Directors and Lead for Registration and Quality. | Director of Nursing and Clinical Standards - Oversight of HIGH risk through Quality Committee and quality sub-committees | 4 | 2 | 8
[5 empty] | Safety controls include, but are not limited to: - improvement initiatives including Productive Wards and the Safer Care programme; - the Clinical Risk Management Strategy and Clinical Risk Assessment and Management training which now includes a component on suicide awareness; - the Central Alerting System (CAS) policy and procedure 2014-17 which was approved by the Integrated Governance Committee in November 2014. CAS is a web-based system for issuing patient safety alerts and other safety critical guidance; - the Risk Management strategy and policy 2014-17 which was approved by the Integrated Governance Committee in November 2014 and further revised through the Quality Committee in May-July 2015; - the Learning from Incidents Team; and - the Safety quality sub-committee and the Quality Committee. | Integrated internal learning across patient experience, safety, workforce and clinical and operational effectiveness through using data from incidents, complaints, claims and HR case work: - in order to improve information sharing, the Clinical Standards Weekly Review Meeting and the Operations Senior Management Team (OPS SMT) meeting join together at the end of their respective meetings on Monday mornings; - weekly monitoring of SIRIs, complaints, claims, inquests and HR casework at Clinical Standards & Joint OPS SMT Weekly Review Meeting; - Directorate monitoring of IIR and SIRI reports to ensure clinical needs are being addressed/incidents learned from; and - the Board receives quarterly Quality Reporting with a particular focus on Safety - most recently in July and November 2015. |  |  |  | GAP (patient experience controls): coherent Trust-wide strategic framework to be developed for patient participation/ involvement / engagement which Directorates can link to and draw on. ACTION: proposal to develop an overarching patient engagement and involvement strategic framework which supports the person-centred care philosophy was approved by the Board in April 2015. The proposal sets out that: patients must be involved at the outset in planning this work and then throughout its development; the work will be jointly led by the communications team, nursing and governance directorate and will call on the expert support and advice of the Oxford AHSN; the Board must take a lead role; and representatives from the Council of Governors and other known networks should convene with the Board to discuss and set out the proposed aims and key pillars of the strategic framework for engagement. OWNERS: Director of Nursing and Clinical Standards, Head of Communications and Engagement and the Patient Involvement and Experience Project Lead. |  |  |  |  | July-December 2015, a person-centred care strategy to be developed and stakeholder events to be scheduled as part of consultation on the development of the strategy.
[5 empty] | Workforce controls include, but are not limited to: - day-to-day operational management structures, effective team working and application of Aston Team-based Working Approach; - optimal staffing levels; - processes to pick up exceptions/variations and for staff to raise concerns e.g. through the Whistleblowing policy; and - the Well Led quality sub-committee and the Quality Committee. | Regular integrated internal reporting on patient experience, safety, workforce, clinical and operational effectiveness and governance and leadership including: - to the Board as (publicly available) standing items at each meeting on Quality and Safety, Quality and Performance, Workforce Performance (which considers recruitment activity, turnover, sickness and bank and agency use) and Safe Staffing Levels; - to the Board through a regular patient experience presentation at public Board meetings focusing on patient stories (with appropriate details anonymised to protect individuals' confidentiality and with permissions having been granted in all cases); - to the Quality Committee (formerly the Integrated Governance Committee) on clinical audit outcomes, Serious Incidents Requiring Investigation (SIRIs), complaints and PALS, patient experience and quarterly Quality Account updates. From 2015, the Quality Account will lead the agenda focus for the Quality Committee. The Quality Committee also regularly receives directorate safety/quality reports from all clinical directorates to provide more detail on safety and quality developments within directorates and service lines; - through the new quality sub-committees reporting into the Quality Committee from 2015: the Safety quality sub-committee, the Effectiveness quality sub-committee, the Caring and Responsive quality sub-committee and the Well Led quality sub-committee; - through Directorate Performance Reviews; - themed reports to the Extended Executive on complaints, incidents and patient experience; and - reporting against standards at team to Board level. Trend analysis and prompt response to variation. Walkarounds by staff, safety walkabouts, Board walkabouts and visits at least annually for each team. Reporting on Board walkabouts to the Institute for Healthcare Improvement as part of the South of England Patient Safety Collaborative. |  |  |  | GAP (patient experience and safety assurance): Trust-wide learning from incidents. Although learning from incidents has been effective within individual Directorates (formerly Divisions), this was not necessarily the case between and across Directorates. ACTION: to address poor attendance at previous Trust-wide learning events towards the end of 2013, the organisation of learning events was reviewed. Learning events remain Trust-wide to ensure that this is one way in which learning can be disseminated across Directorates but the Trust has merged incident, clinical audit, complaints and PALS learning events to provide opportunities to triangulate learning and identify themes and trends across these areas. Each Directorate now has a named link to support learning from incidents, complaints and clinical audit with attendance at Directorate governance meetings. The Corporate Risk and Incidents Team was restructured to allow for more time to focus on Trust-wide learning. Trust-wide learning events took place in: June 2014 (in Buckinghamshire) on carers and to incorporate learning from incidents, Patient Advice & Liaison Services (PALS) and clinical audit related to family, friends and carers; December 2014 (in Oxford) on improving physical healthcare; and June 2015 (in Oxford) on Medication Management. All events were well attended. OWNER: Learning from Incidents Lead |  |  |  |  | Trust-wide learning event on 10 December 2015 focused on improving communications and being part of sharing learning from current themes and trends in communication and what the Trust is doing/planning to do to improve safety. The next learning event will refocus on physical health care.
Clinical and operational effectiveness controls include, but are not limited to: - models of care for every service with clear standards of care and standard operating procedures; - clinical and managerial leaders focusing on achieving standards; and - the Effectiveness quality sub-committee and the Quality Committee.
Governance and leadership controls include, but are not limited to: - dialogue with regulators to feedback on quality standards and inconsistencies or conflicts noted and their potential consequences. Ongoing dialogue with regulators with a view to inviting clarification or further guidance on reconciling or resolving potential inconsistencies or conflicts; and - the Well Led quality sub-committee and the Quality Committee.
[6 empty] | Monitoring of the Trust Risk Register at Executive and Directorate levels for specific potential risks around quality and safety e.g. that patients may not be protected from harm (including through pressure ulcers and suicides in the community), the impact of increased activity levels on district nursing services in Oxfordshire and the 111 service in Oxfordshire, learning from incidents. |  |  |  | GAP (safety controls): variation in application and adoption of Safer Care and Improvement methodology in Directorates to spread good practice across teams. ACTION: monitoring of Safety Performance and progress on Safer Care projects through the Safety quality sub-committee (which will receive assurance through Directorate quality reports, the Safety thermometer, the Safer Care report and other Safety reporting). Membership of the Safety quality sub-committee includes, but is not limited to, Directorate Safety Representatives from each of the clinical Directorates. OWNERS: Directorate Safety Representatives and Director of Nursing and Clinical Standards |  |  |  |  | CQC inspection took place September-October 2015. Results were published in January 2016. The overall rating was "requires improvement" but with ratings of "good" in 3 out of 5 quality measurements (caring, responsive and well-led) and ratings of "requires improvement" in the remaining 2 quality measurements (effective and safe). Improvements are required in safety to ensure that across all Trust services the same high standards are observed.
[6 empty] | External assurance including: - CQC visits, surveys and inspections (following CQC inspection in September 2015, CQC report expected December 2015/January 2016); - Parliamentary Ombudsman letters and themed reports in response to patient feedback and complaints; - monthly contract and quality meetings with Commissioners and closure meetings to review SIRIs. A detailed quality schedule was agreed with Commissioners which included a comprehensive range of quality indicators and measures which were reported quarterly in 2014/15; and - external accreditation, peer review processes and external national clinical audits. |  |  |  | GAP (workforce controls): maintaining optimal staffing levels. Cross-reference also to SO 5.1A and SO 5.1B and the risks relating to inadequate planning for workforce requirements and inability to fill vacancies. The gaps against these risks consider national and local recruitment challenges and the impact on pressure on staff numbers, work-related stress, spend with agencies and quality of care provided. ACTION/OWNER: cross reference to SO 5.1A and 5.1B for the details. Overarching owners are the Deputy Director of HR and the Director of Finance.
[6 empty] | Other assurance through: - Essential Standards Audits; - the Safety Thermometers; - the Community Hospitals Assurance Tool and publication of the outcomes of the Friends and Family Test; - the National Reporting and Learning System relating to incidents; - national confidential inquiries into homicides and suicides; and - Internal Audit - as part of the Internal Audit Plan 2014/15, a review took place of Service Innovation and Business Development which included review of the Aston Team Working Programme; Making Every Contact Count; Tender Workshop; and Flexible Workforce Management Programme. |  |  |  | GAP (governance and leadership controls): development and interaction between a Quality Strategy or Plan and the Clinical Strategy setting out integrated clinical pathways. Moving from aspirations to implementation/delivery. ACTION: further development required following discussion at the Quality Summit in September 2015 and views not to proceed with the draft Quality Strategy then presented. OWNER: Director of Nursing and Clinical Standards; and Head of Strategy and Programmes. |  |  |  |  | Internal Audit Plan 2015/16 includes reviews of: Quality Strategy and Governance; assessment of the methodology used over CQC compliance; validating metrics reported for patient experience and complaints; medical devices; infection control; and patient and public engagement (review of engagement with key stakeholders and the way that relationships are managed).
1.2 | Failure of service models to deliver an integrated care pathway may mean that the individual needs of patients, including those with special needs and/or disabilities, are not met and that patients are not provided with appropriate access to, and transfer between, services. | 4 | 4 | 16 | Controls include but are not limited to: - Oxfordshire Mental Health Partnership - Mental Health Outcomes Based Commissioning (OBC) head contract signed. Sub-contracts and partnership arrangements completed and in place. Formal launch November 2015; - Integrated Locality Teams in place and development continuing; - joint working with Oxfordshire GP Federations relating to joining up of Primary and Community Services; - Older People's OBC being advanced through the FY16 Oxfordshire System Winter Plan; - development of urgent mental health care in both Oxfordshire & Buckinghamshire. Continuing development of Adult Mental Health Teams; - Service Reviews as part of CIP programme; and - Learning Disability Programme in place. | Reporting and monitoring at: Directorate Level, Operations Senior Management Team (OPS SMT) meeting, Executive and the Board. | 3 | 3 | 9 | GAP (controls - contracts in place to provide services): Internal review process in place following CQC inspection. Clarity still required of future role of Learning Disability Services in Oxfordshire and Buckinghamshire. ACTION: OWNER: Chief Operating Officer | Chief Operating Officer Oversight of HIGH risk through Quality Committee and quality sub-committees | 3 | 2 | 6 | Review of Forensic Services underway. Plans for Wave 1 & 2 Service Reviews to be completed by 31 December 2015.
[6 empty] | Organisational Development (OD) programme, Planning the Future, in place to support cultural changes and new ways of working. Completed in Adult and Children and Families' directorates and commenced within Older People's Directorate. Linking Leaders programmes in place across all counties. |  |  |  | GAP (controls - service model reviews and development): development of integrated locality teams with social care. ACTION: appointment of programme director within OCCG working on behalf of all partners has progressed the development of integrated locality teams. Social Care anticipated to be incorporated in 2015/16. Further development of work with GP federations ongoing. Cross-reference also to SO 4.2 and action updates against integrated partnership working. OWNERS: Chief Operating Officer, Service Director and Clinical Director from the Older People's Directorate |  |  |  |  | Development of MH urgent care ongoing in both Oxfordshire and Buckinghamshire. Work taking place with Oxfordshire CCG on the development of new models for 111/GP Out Of Hours services, new models for Complex Needs and Improving Access to Psychological Therapies identified. As at July 2015, Psychological services review commenced.
External review of effectiveness of OD programme as part of transformational change commissioned for completion August 2015. Trust successful in winning tender in Buckinghamshire in partnership with Bernardos to deliver new CAMHS model. As at July 2015, Adult Directorate acute and rehabilitation inpatient wards had all achieved AIMS (Accreditition for Inpatient Mental Health Services). AIMS is a nationally recognised standard from the Royal College of Psychiatry College Centre for Quality Improvement. Triangle of care being implemented and monitored via the Carers Strategy Group. MH OBC contract agreed and signed September 2015 and the Oxfordshire Mental Health Partnership had begun to design, develop and implement some of the proposals contained within the MH OBC. OUH/OHFT confirmed as 'most capable provider' within OP OBC process. System Transformation Board now in place in Oxfordshire. Healthy Bucks Leaders Programme in place in Buckinghamshire - both groups provide oversight of all transformational work within each county. Trust is represented on these groups as well as reporting to them on progress.
1.3 | Failure to manage change effectively may compromise quality and safety during the transition from current to future service models and compromise staff and stakeholder engagement. | 4 | 4 | 16 | Controls include but are not limited to: - programme structure including programme Board, workstream groups, programme risk register and robust contingency planning etc.; - Director of Business Development & Partnerships; and - collaborative working with partner organisations. | Comprehensive organisational change process for Adult and Older People's Services set out, consulted upon and concluded. Service user groups at locality level will continue to monitor implementation and contribute to ongoing development. Ongoing discussions with voluntary sector partners re operationalisation. Evidence of further service development through the consultation process. Quality of management of change process and communication and good joint working with Staff Side. | 2 | 2 | 4 | GAP (controls): ongoing dialogue with partner organisations. ACTION: Strategic links developed with partner organisations with a view to further development of joint service delivery. Outcomes Based Commissioning work progressed for mental health and Older People. MH OBC contract agreed and signed September 2015. Re OP OBC, the Trust and OUH named as "most capable provider". Formalisation of partnership between the two Trusts in development. OP OBC contract negotiations commenced during May 2015 and Heads of Terms between the Trust and OUH agreed. Tactical application of elements of OBC being progressed through FY16 Winter Plan. The proposed change in models and provision of Learning Disability Services remain at an early stage. OWNERS: Chief Operating Officer, Service Directors and Clinical Directors for the 3 clinical directorates (Children & Young People's Services, Adult Services and Older People's Services) and Director of Business Development & Partnerships. | Chief Operating Officer | 2 | 2 | 4 | Oxfordshire Learning Disabilities - a Board with an independent chair will be established to oversee the transformation of services for adults with Learning Disability (LD) in Oxfordshire. The first stage is to scope the extent of the work involved. Buckinghamshire is also engaged in a process to change the nature and provider of its adult LD services and there is a critical interdependence between the two counties if certain elements of the service are to have the critical mass to be viable. Coordination will be key to a successful outcome.
Internal Audit - 2014/15 programme included review of the Quality Impact of Service Changes which found overall reasonable assurance. The review was to determine that when a Cost Improvement Plan work stream or major project was undertaken, there was both a clear initial Quality Impact Assessment and subsequent monitoring of qualitative impact through the life of the work stream or project.
Refer back to Risk SO 1.1 above and the controls and assurances listed. The impact of change and change management on patient experience, safety, workforce and clinical and operational effectiveness will be assessed through the assurances set out in SO 1.1.
1.4 | Failure to ensure patients and carers are involved in managing and leading on their own care could lead to compromising patient outcomes and not delivering sustainable health care. | 4 | 4 | 16 | Controls include but are not limited to: - Trust-wide Carers' Strategy; - the Triangle of Care (the Carers Trust national scheme for improving outcomes for carers accessing mental health services) which recommends better partnership working between services users and their carers and organisations and is being rolled out across the Trust as at July 2015; - development of Recovery Colleges (Oxfordshire and Buckinghamshire); - well-established controls in psychological services; - service user groups in place on locality basis to provide ongoing input to service development for Adult services; - assessment processes within new Adult service models include carers' assessment, housing, employment and well-being of service users; - ongoing work within Adult services to transform patient experience including through the Forensic Patient Council, "have your say" sessions and CPA reviews. CPA guidance has been produced which was written by patients for patients; - work on outcomes with patients and carers is part of the implementation of clusters in mental health and part of the service remodelling; - technological developments such as OXTEXT for patient self-monitoring of mood and services such as CAMHS using facetime to connect with patients etc.; and - part of the implementation of the Next Generation Electronic Health Record will include a work programme on engaging patients with their electronic plans and records. | Internal and External assurances include: - involvement in developing care plans is monitored as part of Care Programme Approach metrics and reported to Commissioners; - the CQC monitors whether care plans have been shared with patients in mental health wards; - reporting to Commissioners since 2014 included quality indicators relating to patient and carer involvement in care planning; - each Directorate has Carers' Strategy action plans; and - progress updates on the Trust-wide Carers' Strategy are provided to the Board (see reporting to the public Board meeting in September 2015 which also included an update on work to implement the Triangle of Care in the Trust). | 4 | 4 | 16 | GAP (controls - implementation of Next Generation Electronic Health Record): the work programme to engage patients with their electronic plans to commence as part of the implementation of the project. The replacement needed to take place first to build in capability. ACTION: replacement of Next Generation Electronic Health Record completed end of 2015 (see also SO 6.2). OWNERS: Director of Informatics, Health Informatics Development Manager, Director of Finance | Director of Nursing and Clinical Standards Oversight of HIGH risk through Quality Committee and quality sub-committees | 2 | 3 | 6 | The development of the Recovery College is progressing in Oxfordshire - the first courses are expected to be running by January 2016. Some funding for the development of a Recovery College in Buckinghamshire has been agreed with commissioners.
[10 empty] | GAP: cross reference to gap at SO 1:1 and note proposal to develop an overarching patient engagement strategic framework which supports the person-centred care philosophy was approved by the Board in April 2015. |  |  |  |  | CQC inspection took place September - October 2015. Results were published in January 2016. The Trust had an overall rating of "requires improvement" but was rated "good" in 3 out of 5 quality measurements - caring, responsive and well-led. The Trust was rated as "requires improvement" in the remaining 2 quality measurements - effective and safe.
2 | Strategic Objective 2: Delivering Operational Excellence Goals: our services will be effective and efficient; and we will deliver our financial plan
2.1 | Failure to put effective governance (both corporate and clinical) arrangements in place may lead to: poor oversight at Board level of risks and challenges; strategic objectives not being established or structures not in place to achieve those objectives; or appropriate structures and processes not in place to maintain the Trust's integrity, reputation and accountability to its stakeholders. | 4 | 4 | 16 | Controls include but are not limited to: - the Trust's Constitution; - Council of Governors and Board Standing Orders; - Standing Financial Instructions and Scheme of Delegation; - Integrated Governance Framework (IGF); - Risk Management Strategy; - Board Assurance Framework; - Trust Risk Register and local risk registers at Directorate and departmental levels; and - the Director of Corporate Affairs/Company Secretary. | The Quality Committee (formerly the Integrated Governance Committee) and Audit Committee reviewing risks and key governance issues - reporting/escalating to Board as appropriate. | 3 | 2 | 6 | GAP (controls): new Integrated Governance Framework (IGF) to be implemented and then to be evaluated post-implementation. The Integrated Governance Committee to become the new Quality Committee and the previous Quality Improvement Committees to become new quality sub-committees (Safety, Effectiveness, Caring and Responsive, Well Led) from January 2015. ACTION: The first ordinary meeting of the Quality Committee (QC) took place in February 2015. The QC will be responsible for: (i) overseeing the effective development of the Trust's corporate and clinical governance arrangements; and (ii) ensuring that there is an objective and systematic approach to the identification and assessment of risk and delivery of the Trust's priorities in the context of all national standards. Internal Audit also reported on the new IGF as part of the 2014/15 Internal Audit Plan. The QC reviewed the IGF and committee effectiveness in May 2015. OWNER: Director of Corporate Affairs/Company Secretary | Chief Executive | 2 | 2 | 4 | The Quality Summit held in September 2015 reviewed corporate and directorate quality governance arrangements and the merits of developing a standalone quality strategy. The view of the people attending, which included the Board of Directors, service and clinical directors and heads of service, was that there was clear and sufficient articulation of the Trust vision for quality in the strategic objectives, business plan and the annual quality account, enacted through a broad range of trust wide and local quality activity. The decision of the summit was therefore not to proceed with the development of a standalone quality strategy.
Internal Audit regular review of governance arrangements. Internal Audit reviews, as part of the Internal Audit Plan 2014/15, included reviews of Quality Strategy & Governance, the IGF, Clinical Audit, Electronic Health Record Programme Governance, the Research Governance Framework, Information Governance, the Board Assurance Framework and Risk. The Internal Audit Plan 2015/16 also includes review of the BAF and risk management arrangements.
2.2 | Ineffective business planning arrangements that do not integrate activities at all levels of the Trust may lead to: the Trust being in breach of regulatory and statutory obligations; the Trust failing to achieve its annual objectives and consequently being unable to meet its strategic objectives. | 4 | 4 | 16 | The Strategic Framework sets out the key areas where appropriate plans and actions will deliver the Strategic Objectives. The business planning process, managed by the Programme Management Office (PMO), ensures that the top-down objectives and the bottom-up planned activities are aligned and that appropriate measures and targets are established to ensure that the Trust objectives can be met. The planning requirements of Monitor, including the Quality Account, are integrated within the Trust's business planning requirements. Senior leaders within the Trust and other key stakeholders are consulted on the business plan proposals. | PMO report regularly on business plan progress and achievement to Executive and Extended Executive meetings. Business planning is a key component of Extended Executive meetings with particular focus on progress review and plan themes development. Formal quarterly progress reports on the Business Plan are presented to the Executive and the Board for review of progress and assessment of achievement. The Council of Governors (CoG) is involved in the development of business planning and the CoG formally review and approve the Annual Business Plan. | 4 | 2 | 8 | GAP: Communication of the objectives and Business Plan to all staff and stakeholders to be more timely. ACTION: summary of the key objectives and activities has been issued to all staff and stakeholders, most recently in September 2014. The Strategic Framework was reviewed and amended by the Extended Executive in October 2014. OWNER: PMO | Director of Finance Oversight of HIGH risk through Finance and Investment Committee. | 3 | 2 | 6
GAP: Insufficient consultation with stakeholders. ACTION: the schedule and process for developing the Business Plan has been amended to ensure all key stakeholders are identified and to allow time for effective consultation. Amendments were completed in September 2014. OWNER: PMO
GAP: Key Performance Indicators (KPIs) not effectively aligned with strategic objectives and Business plans. ACTION: working with Performance teams, CUBE, and directorates to agree KPIs and method for reporting. Improvement anticipated for FY16 plans. KPIs continue to be developed in conjunction with PLICS, activity-based budgets and productivity management. PDRs in the process of review and will include alignment of personal objectives with those of the Trust. OWNER: PMO
GAP: Business Planning process and strategic objectives not sufficiently aligned with individual PDR processes. ACTION: working with L&D and HR to align processes for April 2015. OWNER: PMO
2.3 | Non-delivery of CIP savings and productivity gains may lead to: failure to deliver the Trust's financial plans; additional scrutiny and intervention by Monitor; insufficient cash generation to fund future capital programmes. | 5 | 5 | 25 | Overall CIP target is set as part of the financial planning process for the annual plan and long-term plan. Each Directorate and Corporate Function identifies themes that are developed into project plans and any gap to the overall target is identified and mitigations considered within the overall review of risks and opportunities for the financial plan. Where possible, provisions are made for some underachievement. | Governance and assurances include: - Project governance through weekly project meetings to review individual project progress against objectives. - Directorate Governance - a monthly confirm and challenge of each project led by Service and Clinical Directors to ensure projects remain on track and suitable recovery actions are in place where required. - Programme Governance by the CIP Delivery Group (Executive led) - reviews monthly the overall CIP programme, seeks assurance on all projects and gives close scrutiny to outliers and related recovery actions. - Overall governance provided by the OHFT Board - monthly report to the Board to provide assurance on progress and recovery actions. Regular reporting also to the Finance and Investment Committee. | 4 | 4 | 16 | GAP (controls): priority for attention and resource necessary to deliver CIPs is diluted by the demands of other transformational projects. ACTION: Executive and Service Directors to ensure that all transformational projects are properly integrated with the CIP projects. Any conflict in priority to be raised at the CIP Programme Management Board. OWNERS: Directors and Executives | Chief Operating Officer Oversight of EXTREME risk through regular reporting to the Finance and Investment Committee | 4 | 2 | 8 | CIP Confirm and Challenge sessions continue within Directorates and CIP Delivery Group meets monthly, with operational and quality oversight from the Executive. Service Development Review project under way. Project management resources have been allocated to cross-cutting themes: Learning and Development, Medicines Management and Flexible Staffing.
[5 empty] | Following the Deloitte report in February 2015, improvements to the management and coordination of the CIP programme have been implemented to improve the definition and delivery of CIP themes. - Establishment of a CIP Delivery Group, chaired by the COO and with Medical Director, Director of Nursing and Director of Finance as core members. - The PMO will report into the CIP Board and project directors will attend to provide project updates. - An amount equating to the CIP target will be removed from budgets in advance and the CIP projects tracked against these budgets - Deloitte identified a number of specific opportunities each of which will be evaluated and assesed for feasibility - Additional resource will be allocated to the PMO as required to establish strong controls and assurance. |  |  |  |  | GAP (controls): the means to delivering the required levels of CIP whilst maintaining service quality is the ongoing improvement in productivity and appropriate skill-mix. ACTION: the analytical skills and the information necessary to measure and compare productivity to be developed/brought in. OWNERS: Directors and PMO
GAP (assurance): there is a need to ensure a longer view of CIP programmes over the next 2-3 years rather than a single year view. ACTION: Directorates with support from Deloitte are identifying and developing plans for Wave 1 & 2 Service Reviews on mobile working, skill mix and productivity challenges. CIP delivery for FY16 remains on track at Month 7. OWNER: PMO and Service Performance leads
3 | Strategic Objective 3: Delivering Innovation, Learning and Teaching Goals: the impact of the AHSN, AHSC and CLAHRC will be maximised; we will collaborate in research and innovation; and we will deliver high quality teaching
3.1 | Failure to fully realise the Trust's academic and Research and Development (R&D) potential may adversely affect its reputation and lead to loss of opportunity. | 3 | 3 | 9 | Controls include: - work to improve governance in R&D both locally and through the Oxford Collaboration for Leadership in Applied Health Research and Care (Oxford CLAHRC); - membership of the Oxford Academic Health Science Network (Oxford AHSN) and the Oxford Academic Health Science Centre (Oxford AHSC) to maintain a prominent academic and R&D profile; - expansion of the R&D team to improve patient recruitment into studies which would benefit current studies and future bids for new studies (including commercial studies); and - collaborative work with the Joint Research Office at OUH. | Internal reporting including: - to the Board as (publicly available) 6 monthly reports on R&D covering KPIs on the number of patients recruited to studies and the number of studies underway/planned - most recently received in June 2015 and January 2016; and - R&D forums (R&D Governance Committee and R&D Strategy Forum) reporting to the Effectiveness quality sub-committee. | 3 | 2 | 6 | GAP (controls): expansion of R&D team may still not result in increased/sufficient patient recruitment for studies. ACTION: outcomes to be kept under review. OWNER: Head of R&D | Medical Director | 3 | 1 | 3
[6 empty] | External assurance through: - benchmarking of Trust performance by the Thames Valley Comprehensive Local Research Network; and - Internal Audit. The Internal Audit Plan 2014/15 included a review of the Research Governance Framework. |  |  |  | GAP (controls): how collaboratively governance processes work with the Joint Research Office at OUH. ACTION: R&D is working collaboratively with the Joint Research Office at OUH, under agreement, and, for example, is receiving support to ensure that research contracts are reviewed and drawn up appropriately. OWNER: Head of R&D and Medical Director
3.2 | Failure to be sufficiently innovative and leading edge in its practice may lead to the Trust not being able to keep current contracts or realise its potential in a competitive market. | 4 | 4 | 16 | Provision of high quality services through effective and innovative evidence-based service models e.g. in Mental Health and Interface Medicine, which result in good patient outcomes. Development of Outcomes Based Commissioning in Mental Health and Older Peoples services. | In relation to the provision of high quality services, cross-reference to assurances under BAF risk SO 1.1. | 4 | 3 | 12 | GAP (controls - service models) & ACTION: service remodelling complete but outcomes to be reviewed and evaluated by the Executive. Also cross-reference to gaps/actions in controls/assurance for BAF risk SO 1.1 and 1.2. OWNERS: Chief Operating Officer and Executive Directors | Medical Director Oversight of HIGH risk by the Board directly and through extended Board strategy sessions as appropriate | 3 | 2 | 6 | Discussion at Board meeting 25 June 2014, action for the Executive to pursue.
[5 empty] | Restructured R&D governance processes to improve effectiveness and promote innovation through the establishment of a R&D Governane Committee and a R&D Strategy Forum. | R&D reporting being monitored through Board and Effectiveness quality sub-committee (cross-reference to SO 3.1).
[5 empty] | An Innovation sub-group of the Drugs and Therapeutics Group (DTG) has been established with the aim of discussing proposals for the development of innovative treatments. Work has been undertaken to produce a standardized format for submissions. It is planned that this sub-group will link closely with the R&D Department to consider how innovation may lead to future research. Recent innovation has, for instance, included collaborative work with the University of Oxford on the first UK study into the use of ketamine intravenous infusions for people with treatment-resistant depression (the study reported in April 2014). | The establishment of the Innovation sub-group may increase interest amongst academic staff at the University Department of Psychiatry, who may not otherwise attend the DTG. Those submitting proposals will be invited to present to the sub-group and engage in the subsequent discussion, to help the sub-group consider any ethical and governance issues. The Innovation sub-group will be monitored through the DTG and Effectiveness quality sub-committee. |  |  |  | GAP (assurances - monitoring): lack of centralised monitoring and evaluation of the various innovative practices and developments taking place across the Trust at various levels, including locally within Directorates, and between the Trust and other organisations. ACTION: the Chief Operating Officer developed a list of local Directorate innovations during August 2014. The Board Seminar in September 2014 considered Business Development Opportunities. Translating Innovation into Practice was the theme of the Senior Leaders' Conference in November 2014. An improvement and innovation event took place on 24 February 2015: "Improvement: Everybody's Business" which was organised by the Improvement and Innovation Team to showcase improvement work from across the Trust. OWNER: Chief Operating Officer and Improvement and Innovation Team (Senior Programme Manager).
[5 empty] | Participation in the Oxford CLAHRC, Oxford AHSN and Oxford AHSC and use of these structures to improve and innovate systems around Dementia, Early Intervention, patient experience and patient reported outcomes, better management of medical-psychiatric comorbidity and patient self-management of chronic disease. | The Trust hosts the Oxford CLAHRC and is a partner in the Oxford AHSC with Oxford Brookes University, Oxford University Hospitals NHS Trust and the University of Oxford. Chief Executive's involvement at Board level with the Oxford CLAHRC (Chair of the CLAHRC Board) and Oxford AHSN.
[5 empty] | Development and maintenance of good relationships with commissioners through understanding and meeting their targets. | External assurance through contract review meetings with Commissioners to discuss outcomes and awards.
[5 empty] | Acting on Business Intelligence through the work of the Corporate Business Development Manager and the Director of Business Development & Partnerships. | Internal assurance through: - weekly reporting to the Executive on the Business Intelligence pipeline (after initial review by the OP SMT meeting); - the Improvement and Innovation Team; and - Internal Audit. As part of the Internal Audit Plan 2014/15, a review took place of Service Innovation and Business Development which focused on the following projects: Aston Team Working Programme; Making Every Contact Count; Tender Workshop; Flexible Workforce Management Programme; the Whiteleaf Centre; and Bicester Community Hospital.
Developing strategic partnerships within the NHS and indepedent sector, for example the work taking place with Oxfordshire CCG, Oxford University Hospitals Trust and Oxfordshire County Council for older people on the outcomes based single contract focused on the acute assessment/admission and discharge/reablement pathway. Development with social care and federated primary care relating to integrated locality community services; all reporting through to the Oxfordshire Transformation Board. In Buckinghamshire all transformational work reported via Healthy Bucks Leaders.
4 | Strategic Objective 4: Developing Our Business through Collaboration and Partnerships Goals: we will work in collaborative partnerships; we will maintain and grow our services where we add value; and we will have strong relationships with our stakeholders
4.1 | Failure of the Health and Social Care Systems in which we work to act together to deliver integrated care. Changes in Health and Social Care Systems may impact adversely on the operations of the Trust. | 5 | 5 | 25 | The Trust's Chief Executive chairs the Oxfordshire Transformation Board and is a member of Healthy Bucks Leaders. Executive Directors and Service/Clinical Directors engage strategically and operationally, working jointly with all CCGs, local authorities and other partners including GP providers to understand strategic issues facing CCGs and provide input and support to delivering integrated services within the context of high levels of change within the health and social care systems. | Reporting through OPS SMT, Executive Team and Board. | 4 | 3 | 12 | GAP (controls - engagement and joint working): concern around overlaps between OBC processes and the impact of the Better Care Fund (government pooled fund to promote integrated care). ACTION: ensuring engagement in national Better Care Fund dialogue at a national and local level. Strategic linking of Outcomes Based Commissioning with the Better Care Fund. OWNERS: Chief Operating Officer, Director of Finance and Chief Executive | Chief Operating Officer Oversight of HIGH risk through the Board directly and Board strategy sessions as appropriate | 3 | 3 | 9 | Improved whole systems working and process with good engagement with Partners demonstrated through the Oxfordshire Transformation Board, Healthy Bucks Leaders and System Resilience groups.
Participation in key strategic, operational and contracting meetings by Service Directors, Clinical Directors and Chief Operating Officer
[5 empty] | Development of alliances and partnerships with other organisations, including the voluntary sector, to deliver services into the future. | Whole system working across each county to deliver Integrated Care. |  |  |  | GAP (controls - engagement and joint working): financial pressure on County Councils and Social Care impacting adversely on Health. ACTION: Executive Directors and other directors engage in whole system clinical and financial planning. Engagement with Monitor and introducing them into system-wide discussion with commissioners. Confirmation that the the Trust's National Reference Costs have improved to a score of 87 and the impact on financial flexibility. OWNERS: Chief Operating Officer and Executive Directors
[5 empty] | Ability to deliver integrated care through collaboration and Partnership e.g. Mental Health OBC, Talking Space. Older People's OBC being advanced through FY16 Winter Plan. | External assurance including: collaborative planning with OUH; delivering on commissioners' strategic intent through initiatives such as moving to 7-day working via the service remodelling; and partnership approaches on Mental Health and OP services. Joint working with commissioners on new models of care and extension of contracts and MCP processes. |  |  |  | GAP (controls - engagement and joint working): financial pressures between commissioners and central NHS management. ACTION: dialogue and engagement with Monitor and NHS Providers. OWNERS: Chief Operating Officer, Executive Directors and Service Directors
Business development strategy for Trust agreed at Board Seminar in September 2014 as consolidation and expansion where possible within key operating areas - Oxfordshire, Buckinghamshire and Wiltshire/BaNES for core service offerings. Expansion in wider geography may be considered for more specialist services. Revised processes agreed for consideration of new business opportunities via OPs SMT and Exec Team.
4.2 | Failure to work collaboratively and effectively with external partners may compromise service delivery and stakeholder engagement. | 4 | 4 | 16 | Controls include but are not limited to: - Section 75 agreements in place for Oxfordshire and Buckinghamshire; - developmental work with Police colleagues e.g. joint working with Thames Valley Police on mental health street triage and Section 136 suites; - the Multi-Agency Safeguarding Hubs (MASHs) in Oxfordshire and Buckinghamshire to bring together Health, Social Services, the Police, Education and Youth Offending services in an integrated multi-agency team to share information appropriately and securely on safeguarding children or adults in order to take timely and appropriate action to safeguard them from harm; - development of Mental Health Crisis Concordat across Thames Valley to improve outcomes for people experiencing mental health crisis through local partnerships of health, criminal justice and local authority agencies; and - mental health resilience funding for one year projects achieved (as at November 2014) for: (i) enhancing the Emergency Department Psychiatric Service based at the John Radcliffe and Horton Hospitals; (ii) providing additional funding for the Psychiatric Inreach Liaison Service in Buckinghamshire; (iii) implementing a street triage programme in Buckinghamshire to provide mental health support and advice to Thames Valley Police; and (iv) providing mental health nursing support to South Central Ambulance Service to provide the 111 coordination centre with a mental health nurse. Projects rolled out January to March 2015. | Monitoring and collaboration through Section 75 Joint Management Groups (JMGs) in place in both Oxfordshire and Buckinghamshire. Oxfordshire now has service user representation and quarterly joint meetings with the commissioning JMG. MH OBC contracts agreed and signed September 2015. Sub contracts developed between the Trust and partners and legal partnership agreement being developed. Alliance between OUH and the Trust developed and governance work progressing. | 3 | 3 | 9 | GAP (controls - integration with social care for OP): to put in place formal partnership agreements between NHS and voluntary sector organisations to implement integration with social care for OP physical health services. ACTION: Mental Health Outcomes Based Commissioning contract agreed and signed September 2015. Older People's Outcomes Based Commissioning - contract negotiations commenced May 2015. OWNERS: Chief Operating Officer, Director of Finance, Service Directors and Clinical Directors of 3 clinical directorates (Children & Young People's Services, Adult Services and Older People's Services) | Chief Operating Officer Oversight of HIGH risk by the Board directly and through Board strategy sessions as appropriate | 3 | 2 | 6 | Crisis Concordats signed in both Oxfordshire and Buckinghamshire. Increased joint working taking place with TVP and SCAS; Senior Strategic group set up in Buckinghamshire, chaired by the Chief Operating Officer. Discussion taking place about establishing a similar group in Oxfordshire. AMHP service in Buckinghamshire - 24/7 model agreed to be managed by the Trust; discussion ongoing in Oxfordshire.
[6 empty] | Problems in Practice Group reviewed, links to JMG to ensure health and social care and commissioning approach to Section 136 issues. |  |  |  | GAP (controls): continued development of Urgent Care MH Services. ACTIONS: Street Triage and PIRLS in Buckinghamshire and MH input into SCAS call centre. OWNER: Chief Operating Officer |  |  |  |  | Resilience of Oxfordshire AMHP service of concern. Oxfordshire County Council have taken measures to stabilise in the short term. New 24/7 model agreed with the option of Trust management. Controls through Joint Management Group (JMG) in the short term.
[5 empty] | New service models include integration with social care for Older People's (OP) physical health services. Partnership agreements to be put in place between NHS and voluntary sector organisations to implement. | Internal Audit Plan 2015/16 includes review of partnership governance and cooperating with other providers.
4.3 | If the Trust does not proactively engage with its membership, patients and the wider public then this may compromise its ability to listen and respond to feedback, involve stakeholders proactively and communicate effectively and transparently. | 3 | 3 | 9 | Controls include but are not limited to: - Council of Governors; - Communications function part of the Chief Executive's team; - management of the membership database through the Communications function; - Trust website (content managed by Communications); - development of approach to strategic framework for patient participation /involvement /engagement (element of which will will include engagement with membership); - establishment of local/divisional patient groups; and - Complaints service, PALS surgeries and results of patient experience surveys. | Annual report and reports for Council of Governors demonstrate engagement with FT members. | 2 | 3 | 6 | GAP (controls): Trust website to be updated. ACTION: As at July 2015, the new template for the Trust website has been rigorously tested and is fully deployed, offering a more picture-led user friendly interface for people to find out about our services. A better search index has been implemented and this will continue to have incremental improvements. There have also been improvements to categorised search results and there is ongoing investigation into additional deep search solutions. OWNERS: Chief Executive, Head of Communications and Engagement and Director of Informatics | Chief Executive | 2 | 2 | 4 | The web strategy group, with membership from Comms and IT has been meeting monthly in Q2 in line with decisions taken by the group in Q1 2015/16, following the inaugural meeting. The web strategy group has had consistent representation from all three service directorates and has invited HR and PALS to attend meetings in Q3. The group has agreed and implemented processes, in line with the Trust’s web strategy, to take on oversight and governance of current and future developments, as well as the work of the web editorial group. A recent example of this in practice is a decision to develop a new web area to promote OHFT's research and development work.
Internal reporting including to the Caring and Responsive quality sub-committee and the Quality Committee on complaints, PALS, patient experience and involvement; and weekly monitoring of complaints at Clinical Standards Weekly Review Meeting.
[6 empty] | Service redesign project briefs include engagement element. |  |  |  | GAP (controls): strategic framework for patient participation /involvement /engagement to be developed ACTION/OWNERS: Cross-reference to the gap/action at SO 1.1 above. Note proposal to develop an overarching patient engagement strategic framework which supports the person-centred care philosophy was approved by the Board in April 2015.
5 | Strategic Objective 5: Developing Leadership, People and Culture Goals: staff will be satisfied with the quality of their work; staff and teams will be high-performing; and we will recruit and retain an excellent workforce
5.1A | Inadequate planning for current and future workforce requirements (including number of staff, calibre, skills and training) or ability to respond to changing requirements in a timely manner may lead to: impaired ability to deliver the quantity of healthcare services to the required standards of quality; and inability to achieve the business plan and strategic objectives. | 5 | 3 | 15 | Controls include but are not limited to: - robust recruitment processes; - on-going staff development through resources such as the Learning and Development training matrix which defines subject areas and frequency of training for staff and provides access to appropriate e-learning; - the Performance Framework including the Performance & Development Review Policy and supporting process; - Directorate workforce plans are linked to Business plan/savings plans with regular processes for review; - Senior HR Business Partners are trained in the principles and approach to the Trust workforce planning process developed with input from L&D and Finance; - workforce planning also included as part of service remodelling which will then inform workforce plans for the next three years; - analysis of leaving questionnaires; - Workforce Development manage training programmes for Health Visitors in line with plan; - Medical staffing workforce plan; and - retention measures. | Monitoring and reporting include, but are not limited to: - reports to individual managers, teams, directorates and to the Board enable monitoring of leavers, vacancies and recruitment, absence/sickness and training status; - the Board receives as a public standing item a Workforce Performance Report which considers: recruitment activity; turnover; sickness; and bank and agency use; - new reporting was developed on inpatient safe staffing levels by the Director of Nursing and the Director of Finance which was submitted to the Board meeting in private in April and May 2014 and to the Board meeting in public from June 2014 (and ongoing); - information is reviewed and actions determined at monthly Directorate senior management meetings and the weekly Operations SMT; - weekly reporting on Recruitment Action Group; - the HR senior management team hold a performance review each month; and - Internal Audit reporting on HR processes. The Internal Audit Plan 2015/16 includes review of workforce planning and key supporting HR processes. | 4 | 3 | 12 | GAP (controls): service remodelling complete but outcomes to be reviewed; new staffing ratios and skill mix anticipated to lead to revised workforce plans with subsequent recruitment plans, greater input into staff/career development plans, analysis of promotion opportunities. Development of CUBE anticipated to remove basic number crunching allowing focus on workforce planning in greater detail and with greater frequency in addition to better correlation of a more diverse set of metrics. ACTIONS: Close involvement of HR with the service remodelling projects. Improved data quality and detail enabling high level correlation. Development of automated reports through the CUBE is underway. OWNER: Director of Finance | Director of Finance Oversight of HIGH risk through HR/workforce reporting to Board | 3 | 2 | 6
[10 empty] | GAP (controls): retention measures; lack of clarity on promotion paths for posts or career progression for some job types. ACTION: as at April 2015 discussions taking place with Trade Unions on retention measures. OWNER: Deputy Director of HR, Director of Finance |  |  |  |  | October 2015 Board strategy session focused on Workforce/Staff Engagement (HR)
GAP (controls): medical staffing workforce plan started but not yet complete. ACTION: suite of workforce data to accompany workforce plans begun, including algorithm of retirements. As at April 2015, paper on reward and recognitiation circulated for agreement. OWNER: Deputy Director of HR, Director of Finance
5.1B | Inability to fill vacancies resulting in the quality and quantity of healthcare being impaired. | 4 | 4 | 16 | Controls include: - robust recruitment processes including the introduction of values based recruitment; - minimising staff absence; - making the Trust a great place to work and publicising the fact; - the development of an overarching recruitment plan for each service to address areas of candidate attraction and retention; - collaboration with other local NHS trusts to understand the overall employment marketplace and take joint pre-emptive action where possible; - recruitment candidate pipeline to monitor effectiveness of recruitment stages (as at April 2015 being developed into a database); - creative aproaches to recruitment including intensive attendance at recruitment fairs and training programmes in place for HVs, DNs, Nurses, some AHP, Associate Practitioners, Doctors and Psychologists; - Apprenticeship Programme due to start as at April 2015 [UPDATE?]; and - development pathway for HCAs. | Monitoring and reporting include, but are not limited to: - reports to individual managers, teams, directorates and to the Board enable monitoring of vacancies and recruitment effectiveness; - weekly reporting of vacancy levels and fill rates to SMT and the Service Directors; - reporting on inpatient safe staffing levels to SMT on a weekly basis; - reporting to the Extended Executive on a monthly basis regarding recruitment activity and planned actions; - the HR senior management team hold a performance review each month to review recruitment activity, including leavers exit interview data; - quarterly reporting to Health & Safety; - submission of quarterly performance report to the Board; - monitoring through Trust Risk Register at Executive and Directorate level of risks in relation to: increased levels of activity in district nursing services; and not achieving required recruitment of staff to substantive posts which may result in increased usage of agency staff; and - as at April 2015, audit of recruitment processes taken place and process mapped. | 4 | 3 | 12 | GAP (controls - recruitment processes): dealing with national and local recruitment challenges and the impact on pressure on staff numbers, work-related stress, spend with agencies and quality of care provided. Noted in particular in relation to the Older People's Directorate, South Buckinghamshire and difficulty recruiting to some community hospitals, district nursing and CPN posts. Also linked to the Trust's ability to retain staff. Cross-reference also to SO 1.1 and potential impact on meeting quality standards. ACTION: the formation of a recruitment action group with representatives from across the Directorate; the development of a robust recruitment action plan to include candidate attraction, recruitment process and recruitment retention initiatives. Some of the main areas identified are improving the Trust's website 'Working for Us' pages to also incorporate values based recruitment, identifying short-term accomodation, targeted recruitment campaigns and open days and the development of targeted recruitment materials, relocation allowances, working with Thames Valley Health Education to develop partnership working with other Trusts, developing links with Universities and local agencies, the development of an international recruitment plan, possible investigation of RRP. OWNER: Deputy Director of HR | Director of Finance Oversight of HIGH risk through HR/workforce reporting to Board | 2 | 3 | 6 | An integrated activity plan is in place and is managed daily and reviewed weekly by HR and reviewed with the Operations SMT monthly. Currently running to plan. As at April 2015, work begun on development pathway for HCAs (cross-reference to controls).
5.2 | Failure to put in place a coherent and co-ordinated structure and approach to organisational development and leadership development may jeopardise: (i) the development of robust clinical and non-clinical leadership to support service delivery and change; (ii) the Trust becoming a clinically-led organisation; and (iii) the Trust becoming a "well-led" organisation under the CQC domain. | 4 | 4 | 16 | Controls include but are not limited to: - service model review and modifications of pathways across Operations (cross-reference to SO 1.2 and the risk against failure to deliver integrated care); - completed restructuring of Operations Directorates to provide for development of clinical leadership and for a social care lead in each directorate (completed March 2014); - "planning the future" programme and ongoing Aston Team Working programme; - multi-disciplinary leadership trios within clinical directorates to support and develop clinical leadership; - the Strategic Organisational Development Lead; - the Organisational and Leadership Development Strategy Framework (approved by the Board, October 2014); - individual professional review and development through development of individual professional leadership strategies; - Leadership Development Centres (new programme started in 2014/15) - the Leadership Development Centre is a multi-disciplinary 2-day programme designed using community health and mental health scenarios to equip Bands 7&8 managers and healthcare professionals for their current roles and as leaders of change; the programme initially ran in October 2014, November 2014 and March 2015 and will run again in 2015/16 in November 2015 and February 2016; - the Well Led quality sub-committee and the Quality Committee; and - Linking Leaders conferences aimed at developing strong team networks across the middle tier of management throughout the Trust and supporting the development of a positive organisational culture (running since June 2015 across the Trust's geography and localities with the aim of improving communication and developing networks across the middle tier of management). | Internal monitoring and scrutiny includes: - Directorate "touch-point" discussions to assess organisational development and leadership development in the context of the outcomes of the Operations restructuring and remodelling. Being led by the Chief Operating Officer and underway as at October 2014; - measuring the outcomes of the Operations restructuring and remodelling. The new Adult Service Model to be reviewed (cross reference to SO 1.2); - twice yearly discussions to be scheduled (for Jan/Feb and June/July) for the Executive to review leadership roles and leadership structure. Extended Executive workshop took place in March 2015; - an annual Board Seminar from 2015 to review progress against the Organisational and Leadership Development Strategy Framework (approved by the Board in October 2014); - a regular Trust Awards event to be scheduled to recognise leadership and achievement. The first Staff Recognition Awards ceremony took place after the AGM on 10 September 2015; - use of the annual staff survey to measure progress and perception of leadership development; and - staff appraisals and ad hoc staff satisfaction surveys. | 4 | 3 | 12 | GAP (controls - application of Strategy Framework): coherent Trust-wide learning from existing leadership development projects. Localised good performance and good practice may not be picked up across the Trust. Although it may not always be necessary or appropriate for all Trust-wide learning in this area to be consistent, as opposed to tailored to meet specific leadership development requirements, it should be more coherent and delivered with more purpose. Unwarranted variation without justification may be a gap rather than variation itself. ACTION: Operations Senior Management Team away-day took place September 2014 and reviewed leadership at team level (led by Chief Operating Officer). Increased leadership focus through the Executive and Senior Leaders' groups. OWNER: Chief Operating Officer and Strategic Organisational Development Lead | Chief Executive Oversight of HIGH risk through specific reporting to Board in July 2015 on organisational and leadership development | 2 | 2 | 4
GAP (controls - individual professional review and development): co-ordinated direction of career pathways to steer staff to gain wider experiences. ACTION: development of individual professional leadership strategies. OWNERS: Chief Operating Officer, Service Directors and Clinical Directors.
[6 empty] | External Assurance: - CQC reviews |  |  |  | GAP (controls - individual professional review and development): learning from incidents to establish whether leadership or team functioning is a root cause or an issue. ACTION: appreciative peer reviews to assess the metrics at team level in relation to leadership and linking with key lines of enquiry. OWNER: Director of Nursing and Clinical Standards
GAP: Cross-reference also to SO 1.1 and the gap against Trust-wide learning from incidents and the actions, including learning events, taking place to address this. ACTION: as per SO 1.1 OWNERS: Learning from Incidents Lead and Director of Nursing and Clinical Standards
6 | Strategic Objective 6: Getting the most out of Technology Goals: our patients and staff will have the right technology available; our workforce will have the necessary IT skills to do their jobs well; an outstanding IT service will be delivered
6.1 | Incomplete and inaccurate data and records, both clinical and operational, may lead to: less effective planning and decision-making; lesser control over service safety and quality; lesser ability to drive improvements in safety, quality and productivity. | 4 | 5 | 20 | Consolidate corporate data and key metrics in the datawarehouse where metric definitions can be maintained and automated integrity checks applied. | Regular review of overall data quality to be implemented via the CUBE on prioritised data sets. | 3 | 4 | 12 | GAP (controls): core systems data collection compliance and quality requires significant improvement. ACTION: information asset registers to be refreshed by the end of Q1 FY16. Data Quality Group to agree actions to improve compliance - progress by end of Q1 FY16 but also ongoing. Review of data quality after implementation of CareNotes. OWNER: Interim Head of Information | Director of Finance Oversight of HIGH risk through Quality Committee and quality sub-committees | 3 | 3 | 9 | Data inventory and priorities being established and the quality of the data reviewed. Data Quality Group established.
[5 empty] | A check and approval process to be in place for all key reports and data extracts. | Audits conducted on data quality and information. Internal Audits as part of the 2013/14 plan were carried out on data pseudonymisation and the CUBE. |  |  |  | GAP (controls): automated data checks in the core systems to be more widely used. ACTION: feasibility to be investigated for Carenotes. OWNER: Interim Head of Information.
[5 empty] | Contract KPI reports to commissioners to be reviewed jointly by Services and Contracting prior to issue. |  |  |  |  | GAP (controls): data quality reporting to be standardised and actions taken to remedy shortcomings. ACTION: work with Directorates to agree reporting and correction cycle, then develop further data quality monitoring reports. OWNER: Interim Head of Information. |  |  |  |  | MY HCP delivered in Business Intelligence portal to present data quality issues to responsible HCPs.
[10 empty] | GAP (assurances): formal joint review of contracting reports with Services to be facilitated by the Information and Business Intelligence team. ACTION: investigate current review process and suggest improvements to end to end process. OWNER: Interim Head of Information. |  |  |  |  | Internal Audit Plan 2015/16 includes reviews of IT Risk Identification and Information Governance/Data Quality.
6.2 | Failure to meet the key objectives of the project to replace the Electronic Health Record system may lead to: inaccurate patient records; inefficient use of clinicians' time; less safe and lesser quality of care; increased cost of operation through lost opportunities to improve productivity. | 4 | 3 | 12 | Ensure actual end users are involved in the construction of the specification of requirements and selection of the solution. | A formal Project has been established using the established Prince2 methodology. The Project Executive is the Trust's Chief Executive Officer. A gateway process to be included. The Next Generation Electronic Health Record Programme has been initiated. Projects and activities related to this phase of the Programme have commenced. Regular Project and Programme meetings are taking place with good representation from corporate and clinical areas. Extensive workshops are occurring with clinical services to determine the system configuration required to support the clinical processes. | 4 | 2 | 8 | GAP (controls): best practice project controls to be in place to address the likelihood of this risk materialising. ACTION: extensive use is being made of best practice methodologies (MSP and Prince2). Internal audit is being used to provide assurance. OWNER: Director of Informatics | Director of Finance Oversight of HIGH risk through regular reporting to Finance and Investment Committee | 3 | 2 | 6 | CareNotes is now live and migration has taken place from RiO. Go-live dates were realigned from October 2014, January 2015, April 2015 and July 2015 to November 2014, April 2015 and October 2015.
Approval of the final specification of requirements will occur at many levels including: clinical, Directorate management and Executive Team.
Use competitive dialogue as the means of procurement as this allows prospective suppliers to gain a detailed understanding of the Trust's problem areas, needs and objectives.
Ensure prospective suppliers commit to delivering against the processes of care (scenarios), Trust objectives and required benefits, and not just system 'widgets'; these commitments will form part of the formally agreed contract with the preferred supplier.
7 | Strategic Objective 7: Using our Estate efficiently Goals: patients and staff will benefit from safe and appropriate environments; our estate will be sustainable and environmentally-friendly; and our estate will be cost effective
7.1 | Facilities being unsuitable or unfit for purpose may lead to: increased risk to patient safety; lesser quality of care and patient experience; increased cost of operation; breach of statutory requirements. | 5 | 5 | 25 | Controls include: - statutory compliance monitoring and reporting in place; - risk register established to identify significant risks and identify levels of investment required. Management and resolution of risks is being reviewed and prioritised by individual site/property. Used to develop FY15 Capital Programme and currently being used to develop FY16 Capital Programme including LCC requirements; - fire risk assessments have been completed by an external consultant and the Fire Advisors have in place review plans to ensure fire safety is not compromised; - ligature risks have been risk assessed using the Manchester Tool approach and the Executive has agreed the phase 1 works to be undertaken; - Annual PLACE (Patient-Led Assessments of the Care Environment) inspections for 2014 completed; - Estates Strategy in place having been approved by the Board in November 2013; - since June 2014, Estates & Facilities business plan for FY15-17 in place including workstreams for: providing safe and secure environments through risk-based prioritisation of investment; a new CAS alert process (COMPLETED); establishing a PPM programme (WORKS UNDERTAKEN); undertaking regular surveys of properties (SURVEY COMPLETED); developing a property database (COMPLETED); providing assurance through a detailed CQC Standard 10 assessment (ASSESSMENT PROCESS DEVELOPED AND UTILISED - ISSUES IDENTIFIED AND ACTION PLAN TO RESOLVE DEVELOPED); establishing a Senior Estates and Facilities meeting and working with the Services & Estates Committee (COMPLETED) and performance meetings (monthly and quarterly) (COMPLETED); and - Environmental Sustainability Policy and Sustainable Development Management Plan. | Internal reporting: - CQC Compliance is submitted to the Safety quality sub-committee (this includes statutory compliance); - progress re health and safty works i.e. ligatures/CAS alerts reported to the Safety Committee; - progress re delivery of capital projects required to reduce risks reported to the Capital Programme Board; - Estates Strategy is monitored via 6 monthly reports to the Finance and Investment Committee (FIC). Estates Strategy implementation reports were received by the FIC in May and November 2014 and 2015; - monthly performance report undertaken with Executive lead; - Estates function now included in quarterly Directorate Performance Reviews, since July 2014 and ongoing; and - Internal Audit programme. The Internal Audit Plan 2014/15 included internal audit reviews of estates procurement and statutory compliance and these are to be repeated as part of the Internal Audit Plan 2015/16. | 5 | 2 | 10 | GAP (controls): incomplete information on statutory compliance of rented properties where the obligation sits with the landlord. ACTION: establish a register and process for regular update. Estates & Facilities business plan FY15-17 developed including workstreams to undertake regular surveys of properties and to develop a property database. OWNER: Director of Estates & Facilities | Director of Finance Oversight of HIGH risk through regular reporting to Finance and Investment Committee | 3 | 3 | 9 | Work progressing with landlords and information has been provided. A review of the risk associated with those buildings for which information remains outstanding is underway.
[10 empty] | GAP (controls): incomplete knowledge of the condition of the engineering assets impacting upon ability to confidently assign funding. ACTION: asset list completed and condition of assets to be reviewed. OWNER: Director of Estates & Facilities. |  |  |  |  | Condition survey of assets - contractor appointed to undertake.
[10 empty] | GAP (controls): Manchester Tool works Phases 1 and 2 to be undertaken. ACTION: Associate Director of Estates to develop Phase 2 work plan to allow start on site of works in FY17. Deputy Director of Nursing to ensure all staff are aware of remaining ligature risks. OWNER: Associate Director of Estates; Deputy Director of Nursing; and all Service Directors. |  |  |  |  | As at November 2015, Phase 1 Manchester Tool works are on site. Remaining works will not commence until FY17.
[10 empty] | GAP (controls - PPM works): the Health and Safety Executive issued the Trust with an Improvement Notice in relation to the adequacy of window restrictors. In response, window restrictors have been strengthened. Relevant policies and procedures have been strengthened by Health & Safety. A regime of checking the window restrictors is in place. ACTION: The HSE has confirmed that the Enformencement Notice has been complied with. OWNER: Director of Finance |  |  |  |  | Process in place to carry out checks on window restrictors and report status as part of regular PPM reporting. HSE actions completed.
[10 empty] | GAP (controls): Environmental Sustainability Policy and Sustainable Development Management Plan to be developed. ACTION: completed and policy approved by the Quality Committee in July 2015. OWNER: Director of Estates and Facilities |  |  |  |  | Environmental Sustainability Policy and Sustainable Development Management Plan approved July 2015. Quarterly meetings to be held to review SDMP delivery progress. Progress to also be reported in monthly perofrmance reports.
GAP (assurances): outcome of CQC inspection which took place September-October 2015 and reported in January 2016. Trust overall rating of "requires improvement" and specific ratings of "requires improvement" for quality measurements of effective and safe. Improvements are required in safety to ensure that across all trust services the same high standards are observed. Inspectors noted that some of the Trust's older estate, especially inpatient mental health settings at the Warneford Hospital, was outdated for the delivery of modern mental health care. ACTION: the Trust has long been aware of the challenge of operating from Victorian buildings and a working group is currently developing options for future development of the Warneford Hospital site in particular to better address modern health care needs. OWNER: Director of Estates and Facilities

## Risk Matrix
Risk matrix (since April 2012)
|  | Likelihood |  |  |  |  | Risk Rating (R) = Impact (I) x Likelihood (L)
|  | 1 | 2 | 3 | 4 | 5
|  | Rare | Unlikely | Possible | Likely | Almost certain
Impact | 5 Catastrophic | 5 | 10 | 15 | 20 | 25 |  | Extreme risk
| 4 Major | 4 | 8 | 12 | 16 | 20 |  | High risk
| 3 Moderate | 3 | 6 | 9 | 12 | 15 |  | Medium risk
| 2 Minor | 2 | 4 | 6 | 8 | 10 |  | Low risk
| 1 Negligible | 1 | 2 | 3 | 4 | 5
Impact/Consequence
A guide to the definitions for the impact/consequences, taken from the National Patient Safety Authority (NPSA) definitions:
Potential Consequence |  | Potential impact on individuals |  |  | Patient experience/potential impact on organisation |  |  | Adverse publicity
5 Catastrophic |  | Incident leading to death Multiple permanent injuries or irreversible health effects An event which impacts on a large number of patients |  |  | Totally unacceptable level or quality of treatment/service Gross failure of patient safety if findings not acted on Inquest/ombudsman inquiry Gross failure to meet national standards |  |  | National media coverage with >3 days service well below reasonable public expectation. MP concerned (questions in the House) Total loss of public confidence
4 Major |  | Major injury leading to long-term incapacity/disability Requiring time off work for >14 days Increase in length of hospital stay by >15 days Mismanagement of patient care with long-term effects |  |  | Non-compliance with national standards with significant risk to patients if unresolved Multiple complaints/ independent review Low performance rating Critical report |  |  | National media coverage with <3 days service well below reasonable public expectation
3 Moderate |  | Moderate injury requiring professional intervention Requiring time off work for 4-14 days Increase in length of hospital stay by 4-15 days RIDDOR/agency reportable incident An event which impacts on a small number of patients |  |  | Treatment or service has significantly reduced effectiveness Formal complaint (stage 2) complaint Local resolution (with potential to go to independent review) Repeated failure to meet internal standards Major patient safety implications if findings are not acted on |  |  | Local media coverage long-term reduction in public confidence
2 Minor |  | Minor injury or illness, requiring minor intervention Requiring time off work for >3 days Increase in length of hospital stay by 1-3 days |  |  | Overall treatment or service suboptimal Formal complaint (stage 1) Local resolution Single failure to meet internal standards Minor implications for patient safety if unresolved Reduced performance rating if unresolved |  |  | Local media coverage short-term reduction in public confidence Elements of public expectations not being met
1 Insignificant |  | Minimal injury requiring no/minimal intervention or treatment. No time off work |  |  | Peripheral element of treatment or service suboptimal Informal complaint/inquiry |  |  | Rumours Potential for public concern
Likelihood
Likelihood of occurrence/reoccurence:
1 Rare | Probably never happen/recur
2 Unlikely | Do not expect it to happen/recur but is possible
3 Possible | May happen or recur occasionally
4 Likely | Will probably recur but not a persistent issue
5 Certain | Will undoubtedly happen/recur, possibly frequently

## Guidance
Guidance for completing Board Assurance Framework
Strategic Objectives | The Trust's current strategic objectives: 1) Driving Quality Improvement 2) Delivering Operational Excellence 3) Delivering Innovation, Learning and Teaching 4) Developing our Business through Collaboration and Partnerships 5) Developing Leadership, People and Culture 6) Getting the most out of Technology 7) Using our Estate efficiently
Ref | Risk identifier reference number
Risk description | Specifies the cause of the risk, what the risk/issue is and the possible consequences. A risk is the possibility that an event will occur and adversely affect the achievement of objectives.
Gross/inherent risk rating | Uses the Risk Matrix to score the risk on an inherent basis as it currently appears (before controls or assurances) for: Impact (I) x Likelihood (L) = Risk Rating (R)
Controls (mitigating actions) | Policies, procedures and practices in place to reduce the likelihood of the risk occurring or mitigate the risk if it does occur
Assurances (audit, monitoring, reporting, scrutiny) | Where evidence can be gained about how well the controls are working and what the evidence shows. For example:
| Internal Sources of Assurance | External Sources of Assurance
| Internal Audit | External Audit
| Key Performance Indicators | NHS Litigation Authority
| Performance reports | Monitor
| Committee reports | CQC reviews
| Local counter-fraud work | Royal College visits
| Clinical Audit | Deanery visits
| Staff satisfaction surveys | External benchmarking
| Staff appraisals | Patient Environment action team reports
| Training records | Accreditation schemes
| Training evaluation reports | National and regional audits
| Results of internal investigations | Peer reviews
| Serious untoward incident reports | Feedback from service users
| Complaints records | Feedback from commissioners
| Infection control reports | External advisors
| Declarations to CQC | Local networks
Information governance toolkit self-assessment
PALS reports
HR reports
Internal benchmarking
Policy evaluation or implementation reports
Net/residual risk rating | The residual level of risk remaining if all identified controls are in place and active. Also uses the Risk Matrix to score the risk for Impact (I) x Likelihood (L) = Risk Rating (R)
Gaps in controls/assurance and actions to address gaps | Where there are failures to put effective controls in place or to gain evidence about their effectiveness
Exec Lead | Executive Director who is risk owner
Target risk rating | The realistically acceptable level of risk the Trust is willing to accept in pursuit of its objectives (i.e. the risk appetite or tolerance). Failure to define risk appetite could result in taking on too much risk to achieve objectives or not enough to seize opportunities. Also uses the Risk Matrix to score the risk for target Impact (I) x Likelihood (L) = Risk Rating (R)
Delivery status and action updates | Overall status of the actions planned to mitigate the risk and progress to target for risk reduction e.g. on target, good progress, poor progress