## BAF
Board Assurance Framework FULL VERSION - PUBLIC Version: 18 October 2016
Ref | Risk description | Gross (inherent) risk rating |  |  | Controls (Mitigating actions) | Assurances (audit, monitoring, reporting, scrutiny) | Net (residual) risk rating |  |  | Gaps in controls/assurance and actions to address gaps | Exec Lead | Target risk rating |  |  | Delivery status and action updates
|  | I | L | R |  |  | I | L | R |  |  | I | L | R
1 | Strategic Objective 1: Driving Quality Improvement Goals: patients will be safe from harm; patients will achieve the outcomes they want; and patients and carers will have excellent experiences
1.1 | Failure to: (i) meet consistently quality standards for clinical care; (ii) address variability across quality standards ; or (iii) reconcile conflicting quality standards or guidance, will result in poorer outcomes for patients and poorer patient safety and experience. | 4 | 5 | 20 | Patient experience controls include, but are not limited to: - Complaints and Patient Advice and Liaison Service (PALS) feedback; - feedback of patient experience (received through a mixed medium of postal feedback and also real-time feedback through electronic devices); - the Patient Involvement and Experience Strategy, "Just Ask Me", for 2016-19, which had been developed with a high degree of patient involvement and approved at the Board meeting in April 2016. The aims of the strategy are: person-centred care; acting on feedback; and patient involvement and co-design of services. Actions to progress the objectives of the strategy are set out in Appendix 2 of the strategy; and - the Caring and Responsive quality sub-committee (the C&R) and the Quality Committee. | Patient experience monitoring by the Patient Feedback to Improve Care Group. The Group's objective is to ensure senior leadership on embedding collection and use of patient feedback across the Trust by monitoring the implementation of objectives from the Patient Experience Strategy. The Group has reported progress quarterly to the C&R which reports into the Quality Committee (these replaced the Services and Estates sub-committee and the Integrated Governance Committee from 2015). The C&R also receives reporting from Complaints and PALS and escalates this to the Quality Committee. Annual reporting on patient and carer experience is provided to the Quality Committee, most recently in July 2016. On a quarterly basis the Board also receives Quality Reporting with a particular focus on Patient Experience , most recently in February, May and October 2016. The Council of Governors also operates a Patient Experience sub-group to review patient experience issues and provide assurance that patient experience is given due regard in the provision and evolution of Trust services. External assurance through CQC inspection process - most recently in June 2016 which reported positively. | 4 | 3 | 12 | GAP (patient experience assurance): the progress being made against well-established themes and areas for improvement in patient experience. The need to potentially invest further resources or realign resources around quality improvement and to drive forward the Patient Involvement and Experience Strategy. The impact upon other priorities if more emphasis and resources are given to patient experience and involvement. ACTION: monitoring through the work of the Patient Feedback to Improve Care Group and reporting into Directorate Performance Review meetings and the C&R. Monitoring through the Board and regular reporting on patient experience. Membership of the C&R includes, but is not limited to, Directorate patient experience leads (for each clinical Directorate) and the Trust Patient Experience Lead. OWNERS: Service and Clinical Directors; Patient Experience and Involvement Manager; and Acting Head of Quality & Safety | Director of Nursing and Clinical Standards - Oversight of HIGH risk through Quality Committee and quality sub-committees | 4 | 2 | 8 | Reporting from the C&R to the Quality Committee in July 2016 highlighted a risk around the work required to maintain Triangle of Care accreditation. Resourcing for this was to be explored by the Trust social care lead. - CQC re-inspection in June 2016 (report published August 2016) - inspection process included CQC discussing directly with patients and collecting feedback. With few exceptions, the patients they met spoke positively about the support they received from staff and their treatment.
[5 empty] | Safety controls include, but are not limited to: - improvement initiatives including Productive Wards and the Safer Care programme; - the Clinical Risk Management Strategy and Clinical Risk Assessment and Management training which now includes a component on suicide awareness; - the Central Alerting System (CAS) policy and procedure 2014-17 which was approved by the Integrated Governance Committee in November 2014. CAS is a web-based system for issuing patient safety alerts and other safety critical guidance; - the Risk Management strategy and policy 2014-17 which was approved by the Integrated Governance Committee in November 2014 and further revised through the Quality Committee in May-July 2015; - the Learning from Incidents Team; - the Safety quality sub-committee and the Quality Committee; and - work taking place on the Trust's mortality review self-assessment. This was discussed at the Board Seminar on 13 April 2016 and the Trust's new Mortality Review Group is now operational. | Integrated internal learning across patient experience, safety, workforce and clinical and operational effectiveness through using data from incidents, complaints, claims and HR case work: - weekly monitoring of Serious Incidents, complaints, claims, inquests and HR casework at Clinical Standards Weekly Review Meeting; - Directorate monitoring of IIR and Serious Incident reports to ensure clinical needs are being addressed/incidents learned from; - the Board receives quarterly Quality Reporting with a particular focus on Safety, most recently in March and June 2016 and next due in November 2016; - the Board also receives quarterly Quality Reporting with a particular focus on Effectiveness, most recently in January, April and September 2016; and - external assurance through CQC inspection process - most recently in June 2016 which rated services as "good" overall and specifically "good" on effective but "requires improvement" on safe. |  |  |  | GAP (safety): CQC rating of "requires improvement" on the question of whether services are safe at CQC reinspection in June 2016 and following comprehensive inspection in September/October 2015. Work required to action recommendations. Details in publicly available report (published August 2016). CQC higlighted: the rehabilitiation ward for working age adults; medicines management recording and monitoring; and staffing levels. All wards were staffed to achieve safe staffing levels but this was achieved on some wards by staff working additional hours and shifts, use of temporary staff from the Trust's bank and agencies, and reducing beds on some wards. ACTION: progress CQC post-inspection improvement plan. Progress report updates to: Board Seminar in March 2016; Quality Committee in May, July and September 2016; monthly to Extended Executive meeting; quarterly to the quality sub-committees (Safety, Effectiveness, C&R and Well Led) on applicable actions. Oxfordshire CCG is the lead commissioner to sign-off completion of actions across improvement plans through quarterly quality review meetings. OWNER: Acting Head of Quality & Safety; and Director of Nursing and Clinical Standards |  |  |  |  | Overall CQC rating for the Trust as a service provider following reinspection in June 2016 was "good" and this was an improvement since the comprehensive inspection in September/October 2015 from the then overall rating of "requires improvement". At reinspection the CQC revised the rating for effective from "requires improvement" to "good".
[5 empty] | Workforce controls include, but are not limited to: - day-to-day operational management structures, effective team working and application of Aston Team-based Working Approach; - optimal staffing levels; - processes to pick up exceptions/variations and for staff to raise concerns e.g. through the Whistleblowing policy; and - the Well Led quality sub-committee and the Quality Committee. | Regular integrated internal reporting on patient experience, safety, workforce, clinical and operational effectiveness and governance and leadership including: - to the Board as (publicly available) standing items at each meeting on Quality and Safety, Quality and Performance, Workforce Performance (recruitment activity, turnover, sickness and bank and agency use) and Safe Staffing Levels; - to the Board through a regular patient experience presentation at public Board meetings focusing on patient stories (with appropriate details anonymised to protect individuals' confidentiality and with permissions having been granted in all cases); - to the Quality Committee on clinical audit outcomes, Serious Incidents (SIs), complaints and PALS, patient experience and quarterly Quality Account updates. The Quality Committee also regularly receives directorate safety/quality reports from all clinical directorates to provide more detail on safety and quality developments within directorates and service lines - for example in May 2015 (Older People's Directorate), July 2015 (Adult Directorate), September 2015 (Children & Young People's Directorate) and September 2016 (Adult Directorate); - through the new quality sub-committees reporting into the Quality Committee from 2015: the Safety quality sub-committee, the Effectiveness quality sub-committee, the Caring and Responsive quality sub-committee and the Well Led quality sub-committee; - through Directorate Performance Reviews; - themed reports to the Extended Executive on complaints, incidents and patient experience; - reporting against standards at team to Board level. Trend analysis and prompt response to variation. Walkarounds by staff, safety walkabouts, Board walkabouts and visits at least annually for each team. Reporting on Board walkabouts to the Institute for Healthcare Improvement as part of the South of England Patient Safety Collaborative; - Internal Audit - as part of Internal Audit Plan 2015/16 reviews of Partnership Governance and Quality Governance; and - CQC inspection and reinspection June 2016. |  |  |  | GAP (workforce controls): safe staffing. This has been a known risk on the BAF and other risk registers (Trust Risk Register and directorate risk registers). The CQC reinspection in June 2016 (report published August 2016) rated the Trust as "requires improvement" on the question of whether the Trust's services were safe and highlighted that safe staffing was a part of this. The CQC noted that it had seen evidence of the Trust actively seeking to fill vacancies through open days, recruitment fairs, preceptorship programmes and the development of an internal staff bank. All wards were also staffed to meet safe staffing levels (i.e. this matter remains a risk, as distinct from an issue). However, safe staffing levels were achieved on some wards by staff working additional hours and shifts, high use of temporary staff from the Trust's bank "staffing solutions" and external agencies and reducing beds on some wards. ACTION: see below risks 5.1A and 5.1B and associated actions OWNER: Interim Deputy Director of HR; and Director of Finance |  |  |  |  | Although Trust-wide learning from incidents was a gap in controls/assurances in 2013, since then regular Trust-wide learning events (merging incidents, clinical audit, complaints and PALS learning) have provided opportunities to triangulate learning and have been well attended. The CQC reinspection report (published August 2016) noted that there was clear evidence of cascading information to team members following incidents; team meeting minutes showed dedicated time to discuss learning from incidents; and there was evidence of centrally cascaded "risk notes" from the Risk Team being discussed with staff.
Clinical and operational effectiveness controls include, but are not limited to: - models of care for every service with clear standards of care and standard operating procedures; - clinical and managerial leaders focusing on achieving standards; - AIMS accreditation. As at July 2015, Adult Directorate acute and rehabilitation inpatient wards had all achieved AIMS (Accreditition for Inpatient Mental Health Services). AIMS is a nationally recognised standard from the Royal College of Psychiatry College Centre for Quality Improvement; and - the Effectiveness quality sub-committee and the Quality Committee.
[5 empty] | Governance and leadership controls include, but are not limited to: - dialogue with regulators to feedback on quality standards and inconsistencies or conflicts noted and their potential consequences. Ongoing dialogue with regulators with a view to inviting clarification or further guidance on reconciling or resolving potential inconsistencies or conflicts; - the Well Led quality sub-committee and the Quality Committee; and - Board self-assessment. |  |  |  |  | GAP (governance and leadership controls): development and interaction between a Quality Strategy or Plan and the Clinical Strategy setting out integrated clinical pathways. Moving from aspirations to implementation/delivery. ACTION: further development required following discussion at the Quality Summit in September 2015 and views not to proceed with the draft Quality Strategy then presented. OWNER: Director of Nursing and Clinical Standards; and Head of Strategy and Programmes. |  |  |  |  | In relation to governance and leadership controls - Board Development Team Workshop at Board Seminar on 10 March 2016 which provided Board with opportunity to: apply principles underly team effectiveness programme that teams been undertaking; and review current and potential effectiveness of Board as a team.
[6 empty] | Monitoring of the Trust Risk Register at Executive and Directorate levels for specific potential risks around quality and safety e.g. that patients may not be protected from harm (including through pressure ulcers and suicides in the community), the impact of increased activity levels on district nursing services in Oxfordshire and the 111 service in Oxfordshire, learning from incidents. |  |  |  | GAP (safety controls): variation in application and adoption of Safer Care and Improvement methodology in Directorates to spread good practice across teams. ACTION: monitoring of Safety Performance and progress on Safer Care projects through the Safety quality sub-committee (which will receive assurance through Directorate quality reports, the Safety thermometer, the Safer Care report and other Safety reporting). Membership of the Safety quality sub-committee includes, but is not limited to, Directorate Safety Representatives from each of the clinical Directorates. OWNERS: Directorate Safety Representatives and Director of Nursing and Clinical Standards
[6 empty] | External assurance including: - CQC visits, surveys and inspections. Following CQC re-inspection in June 2016, overall rating was "good" with ratings of "good" in 4 out of 5 quality measurements (caring, responsive, well-led and effective) and rating of "requires improvement" in the remaining 1 quality measurement (safe); - Oxfordshire CCG as lead commissioner and leading on sign-off of completion of CQC post-inspection improvement plans through existing quality review meetings. CQC will also continue to monitor progress through existing routine relationship meetings (quality); - Parliamentary Ombudsman letters and themed reports in response to patient feedback and complaints; - monthly contract and quality meetings with commissioners and closure meetings to review SIs. A detailed quality schedule was agreed with commissioners which included a comprehensive range of quality indicators and measures which were reported quarterly in 2014/15; and - external accreditation, peer review processes and external national clinical audits. |  |  |  | GAP (external assurance): as above gap re safety following CQC reinspection in June 2016 ACTION: as above to implement improvement plans to address findings from CQC inspection OWNER: Acting Head of Quality & Safety; and Director of Nursing and Clinical Standards
Other assurance through: - Essential Standards Audits; - the Safety Thermometers; - the Community Hospitals Assurance Tool and publication of the outcomes of the Friends and Family Test; - the National Reporting and Learning System relating to incidents; - national confidential inquiries into homicides and suicides; and - Internal Audit - as part of the Internal Audit Plan 2014/15, a review took place of Service Innovation and Business Development which included review of the Aston Team Working Programme; Making Every Contact Count; Tender Workshop; and Flexible Workforce Management Programme. Internal Audit Plan 2015/16 includes review o:f Patient Experience - Complaints; Quality Strategy and Governance; CQC follow-up; and Medical Devices.
1.2 | Failure of service models to deliver an integrated care pathway may mean that the individual needs of patients, including those with special needs and/or disabilities, are not met and that patients are not provided with appropriate access to, and transfer between, services. | 4 | 4 | 16 | Controls include but are not limited to: - Oxfordshire Mental Health Partnership with Mind, Response, Restore, Connection FS and Elmore - development of Recovery Colleges in Oxfordshire and Buckimghamshire; - Integrated Locality Teams in place and development continuing; - joint working with Oxfordshire GP Federations relating to joining up of Primary and Community Services. Agreement in place with all Oxfordshire GP Federations to explore joint enterprise model to deliver full multi-disciplinary primary care (fruition of location/neighbourhood integration) to maximise support to patients and reduce pressure on GP and community workforce; - Older People's OBC being advanced through the Oxfordshire System Winter Plan; - development of Urgent Mental Health Care in both Oxfordshire & Buckinghamshire (with South Central Ambulance Service (SCAS) and Thames Valley Police (TVP)). SCAS mental health nurse scheme established at ambulance control. Street Triage with TVP fully operational in both Oxfordshire & Buckinghamshire and ongoing work with TVP to provide appropriate mental health crisis response; - CAMHS (Child & Adolescent Mental Health Services) model in Buckinghamshire delivered in partnership with Barnardo's; - Service Reviews as part of CIP programme; - section 75 agreements with Oxfordshire County Council and Buckinghamshire County Council to provide health and social care service functions with a pooled provider budget. Governed through Joint Management Groups; - Learning Disability Programme in place; and - in development - Thames Valley and Wessex Forensic Mental Health New Care Model for adult forensic mental health (new provider-led commisioning approach for medium and low secure services). Overall aim of new care model to reduce lengths of stays in region, treat more people closer to home, reduce inpatient stays and reinvest in other out of hospital forensic mental health services. Trust leads network of other providers of specialist mental health care to coordinate services. | - Strategic partnerships' reporting and monitoring at: Directorate Level, Operations Senior Management Team (OPS SMT) meeting, Executive, Quality Committee and the Board - Away-day for the Oxfordshire Mental Health Partnership in May 2016 to take stock of achievements of the partnership - Reporting to the Quality Committee on section 75 Joint Management Groups with annual reporting most recently provided in July 2016 - Quarterly reporting to the Board on Strategic Partnerships setting out progress and objectives, most recently in May and September 2016 - Board and Council of Governors (public and private) also received progress reports on Learning Disability Transformation and the Thames Valley and Wessex Forensice Mental Health New Care Model, for example in July 2016 Board and September 2016 Board and Council of Governors | 3 | 3 | 9 | GAP (controls - Learning Disability): Clarity still required on future role of Learning Disability Services in Oxfordshire. ACTION: ongoing work in partnership with Southern Health NHS FT and other key stakeholders to increase understanding of the services offered by Southern Health to people with a learning disability and their families in Oxford. OWNER: Programme Director - Learning Disability | Chief Operating Officer Oversight of HIGH risk through Quality Committee and quality sub-committees | 3 | 2 | 6 | Discussions and updates on Learning Disability Services at Board Seminar on 14 September 2016 and Board meetings on 28 September 2016 - following on from Board Seminar on 13 July 2016 which was attended by Southern Health.
GAP (controls - service model reviews and development): development of integrated locality teams with social care. ACTION: appointment of programme director within OCCG working on behalf of all partners has progressed the development of integrated locality teams. Further development of work with GP federations ongoing. Cross-reference also to SO 4.2 and action updates against integrated partnership working. OWNERS: Chief Operating Officer, Service Director and Clinical Director from the Older People's Directorate
[10 empty] | GAP (controls - Oxfordshire Mental Health Partnership and Recovery Colleges) - Recovery College funding being met from Directorate budget as no additional funding for this project. £250,000 p.a. to the host, Restore. Gap highlighted by quarterly Strategic Partnerships reporting to Board. ACTION: source external or continue to provide funding. OWNER: Service Director - Adult Services; and Chief Operating Officer |  |  |  |  | Thames Valley and Wessex Forensic Mental Health New Care Model - Trust successful in application to lead one of 4 new care models for adult forensic mental health. Initial network meetings completed August/Sept 2016. Financial and patient level data received and initial reviews of data conducted. Shadow go live from October 2016 (NHS England remains responsible for budget). Business Case for sign-off in December 2016. Subject to sign-off, full go live April 2017.
GAP (controls - Thames Valley and Wessex Forensic Mental Health New Care Model): to be developed, with thorough due diligence of financial, contractual and patient level information satisfactorily completed and governance arrangements confirmed and established before full go live on the new care model. ACTION: complete due diligence; confirm governance arrangements and structure; prepare Business Case for sign-off in December 2016. Subject to sign-off, prepare for full go live in April 2017. OWNER: Associate Director of Strategy and Organisational Development
1.3 | Failure to manage change effectively may compromise quality and safety during the transition from current to future service models and compromise staff and stakeholder engagement. | 4 | 4 | 16 | Controls include but are not limited to: - programme structures including programme Board, workstream groups, programme risk register and robust contingency planning etc. For example, Oxfordshire Learning Disabilities - a Board with an independent chair has been established to oversee the transformation of services for adults with Learning Disability (LD) in Oxfordshire. A new Learning Disabilities Programme Director started in post from 01 July 2016 to pick up the transformation of Oxfordshire LD services; - collaborative working with partner organisations; and - the Trust's Chief Executive chairs the Oxfordshire Transformation Board and is a member of Healthy Bucks Leaders. | Comprehensive organisational change process for Adult and Older People's Services set out, consulted upon and concluded. Service user groups at locality level will continue to monitor implementation and contribute to ongoing development. Ongoing discussions with voluntary sector partners re operationalisation. Evidence of further service development through the consultation process. Quality of management of change process and communication and good joint working with Staff Side. | 2 | 2 | 4 | GAP (controls - resourcing of programme structures): the Trust is involved in a number of significant projects which could lead to change e.g. transformation of Oxfordshire Learning Disability; and Thames Valley and Wessex Forensic Mental Health New Care Model. These opportunities also have a potential impact upon management time and regular service provision. The time and resource required to plan and undertake new activity could have a negative impact upon the Trust. ACTION: Board/senior management to think strategically about the the opportunity cost of these choices and developments. Executive has discussed the Trust’s management capacity and capability to become involved in these developments and undertaken appropriate due diligence to understand the scale of the tasks involved. As reported to the Board meeting in July 2016, this demonstrated that the the scale of the tasks was not as daunting as might be suspected. Different management teams were also involved in the developments with specialist commissioning and with learning disability so the same team(s) was not being put under pressure. OWNER: Chief Operating Officer; and Chief Executive | Chief Operating Officer | 2 | 2 | 4
Internal Audit - 2014/15 programme included review of the Quality Impact of Service Changes which found overall reasonable assurance. The review was to determine that when a Cost Improvement Plan work stream or major project was undertaken, there was both a clear initial Quality Impact Assessment and subsequent monitoring of qualitative impact through the life of the work stream or project.
[6 empty] | Refer back to Risk SO 1.1 above and the controls and assurances listed. The impact of change and change management on patient experience, safety, workforce and clinical and operational effectiveness will be assessed through the assurances set out in SO 1.1. |  |  |  | GAP (controls): communication of change internally to staff and externally to patients/stakeholders. Anticipating the impact upon staff of consultation exercises/changes in models of care and pre-empting and responding to staff anxiety about what the future may hold e.g. with the upcoming public consultation on proposals for changes to health services in Oxfordshire (including community hospitals). The Oxfordshire Transformation Board has agreed that consultation will now start at the end of December 2016/beginning of January 2017 to ensure proposals for change are rigorously tested first, including through public engagement/local events. Consultation will last for 3 months and be the culmination of 7 months of local discussions between NHS organisations, patients, the public, local groups and local councils. ACTION: The Chief Executive, as chair of the Oxfordshire Transformation Board, keeps the Board and senior management informed and involved. Active Comms through Comms team and Trust website. Information also available through Oxfordshire Transformation website. OWNER: Chief Operating Officer and Chief Executive
GAP (controls): ongoing dialogue with partner organisations. ACTION: Strategic links developed with partner organisations with a view to further development of joint service delivery. OWNERS: Chief Operating Officer, Service Directors and Clinical Directors for the 3 clinical directorates (Children & Young People's Services, Adult Services and Older People's Services)
1.4 | Failure to ensure patients and carers are involved in managing and leading on their own care could lead to compromising patient outcomes and not delivering sustainable health care. | 4 | 4 | 16 | Controls include but are not limited to: - Trust-wide Carers' Strategy; and the Patient Involvement and Experience Strategy, "Just Ask Me", for 2016-19; - the Triangle of Care (the Carers Trust national scheme for improving outcomes for carers accessing mental health services) which recommends better partnership working between services users and their carers and organisations and is being rolled out across the Trust. The Triangle of Care being implemented and monitored via the Carers Strategy Group; - development of Recovery Colleges (Oxfordshire and Buckinghamshire); - well-established controls in psychological services; - service user groups in place on locality basis to provide ongoing input to service development for Adult services; - assessment processes within new Adult service models include carers' assessment, housing, employment and well-being of service users; - ongoing work within Adult services to transform patient experience including through the Forensic Patient Council, "have your say" sessions and CPA reviews. CPA guidance has been produced which was written by patients for patients; - work on outcomes with patients and carers is part of the implementation of clusters in mental health and part of the service remodelling; - technological developments such as OXTEXT for patient self-monitoring of mood and services such as CAMHS using facetime to connect with patients etc.; and - part of the implementation of the Next Generation Electronic Health Record will include a work programme on engaging patients with their electronic plans and records. | Internal and External assurances include: - involvement in developing care plans is monitored as part of Care Programme Approach metrics and reported to Commissioners; - the CQC monitors whether care plans have been shared with patients in mental health wards; - reporting to Commissioners since 2014 included quality indicators relating to patient and carer involvement in care planning; - each Directorate has Carers' Strategy action plans; and - progress updates on the Trust-wide Carers' Strategy are provided to the Board (see reporting to the public Board meeting in September 2015 which also included an update on work to implement the Triangle of Care in the Trust). | 3 | 3 | 9 | GAP (controls - implementation of Next Generation Electronic Health Record): the work programme to engage patients with their electronic plans to commence as part of the implementation of the project. The replacement needed to take place first to build in capability. ACTION: replacement of Next Generation Electronic Health Record (see also SO 6.2). Go-live of Carenotes in October 2015 marked completion of the Transition Phase of the EHR Programme (moving away from RiO and SystmOne). Transformation Phase of the programme now commenced. OWNERS: Director of Informatics, Health Informatics Development Manager, Director of Finance | Director of Nursing and Clinical Standards Oversight of HIGH risk through Quality Committee and quality sub-committees | 2 | 3 | 6
GAP (controls): Reporting from the Caring & Responsive quality sub-committee to the Quality Committee in July 2016 highlighted a risk around the work required to maintain Triangle of Care accreditation. ACTION: Resourcing for this was to be explored by the Trust social care lead. OWNER: Chief Operating Officer
GAP (controls): see gap at 1.2 above re Recovery College funding being met from Directorate budget as no additional funding for this project. £250,000 p.a. to the host, Restore.
2 | Strategic Objective 2: Delivering Operational Excellence Goals: our services will be effective and efficient; and we will deliver our financial plan
2.1 | Failure to put effective governance (both corporate and clinical) arrangements in place may lead to: poor oversight at Board level of risks and challenges; strategic objectives not being established or structures not in place to achieve those objectives; or appropriate structures and processes not in place to maintain the Trust's integrity, reputation and accountability to its stakeholders. | 4 | 4 | 16 | Controls include but are not limited to: - the Trust's Constitution; - Council of Governors and Board Standing Orders; - Standing Financial Instructions and Scheme of Delegation; - Integrated Governance Framework (IGF); - Risk Management Strategy; - Board Assurance Framework; - Trust Risk Register and local risk registers at Directorate and departmental levels; and - the Director of Corporate Affairs/Company Secretary. | The Quality Committee (formerly the Integrated Governance Committee) and Audit Committee reviewing risks and key governance issues - reporting/escalating to Board as appropriate. | 3 | 2 | 6 | GAP (controls): new Integrated Governance Framework (IGF) to be implemented and then to be evaluated post-implementation. The Integrated Governance Committee to become the new Quality Committee and the previous Quality Improvement Committees to become new quality sub-committees (Safety, Effectiveness, Caring and Responsive, Well Led) from January 2015. ACTION: The first ordinary meeting of the Quality Committee (QC) took place in February 2015. The QC is responsible for: (i) overseeing the effective development of the Trust's corporate and clinical governance arrangements; and (ii) ensuring that there is an objective and systematic approach to the identification and assessment of risk and delivery of the Trust's priorities in the context of all national standards. Internal Audit also reported on the new IGF as part of the 2014/15 Internal Audit Plan. The QC reviewed the IGF and committee effectiveness in May 2015. OWNER: Director of Corporate Affairs/Company Secretary | Chief Executive | 2 | 2 | 4
Internal Audit regular review of governance arrangements including annual review of the BAF and risk management arrangements. Internal Audit reviews, as part of the Internal Audit Plan 2014/15, included reviews of Quality Strategy & Governance, the IGF, Clinical Audit, Electronic Health Record Programme Governance, the Research Governance Framework, Information Governance, the Board Assurance Framework and Risk. The Internal Audit Plan 2015/16 also included review Quality Governance.
The Quality Summit held in September 2015 reviewed corporate and directorate quality governance arrangements and the merits of developing a standalone quality strategy. The view of the people attending, which included the Board of Directors, service and clinical directors and heads of service, was that there was clear and sufficient articulation of the Trust vision for quality in the strategic objectives, business plan and the annual quality account, enacted through a broad range of trust wide and local quality activity. The decision of the summit was therefore not to proceed with the development of a standalone quality strategy.
2.2 | Ineffective business planning arrangements that do not integrate activities at all levels of the Trust may lead to: the Trust being in breach of regulatory and statutory obligations; the Trust failing to achieve its annual objectives and consequently being unable to meet its strategic objectives. | 4 | 4 | 16 | The Strategic Framework sets out the key areas where appropriate plans and actions will deliver the Strategic Objectives. The business planning process, managed by the Programme Management Office (PMO), ensures that the top-down objectives and the bottom-up planned activities are aligned and that appropriate measures and targets are established to ensure that the Trust objectives can be met. The planning requirements of NHS Improvement (formerly Monitor), including the Quality Account, are integrated within the Trust's business planning requirements. Senior leaders within the Trust and other key stakeholders are consulted on the business plan proposals. | PMO report regularly on business plan progress and achievement to Executive and Extended Executive meetings. Business planning is a key component of Extended Executive meetings with particular focus on progress review and plan themes development. Formal quarterly progress reports on the Business Plan are presented to the Executive and the Board for review of progress and assessment of achievement (in January, April, July and October of each year). The Council of Governors (CoG) is involved in the development of business planning and the CoG formally review and approve the Annual Business Plan, most recently in September 2016. | 4 | 2 | 8 | GAP: Communication of the objectives and Business Plan to all staff and stakeholders to be more timely. ACTION: summary of the key objectives and activities has been issued to all staff and stakeholders, and is available on the Trust Strategy pages of the intranet. The Strategic Framework was reviewed and amended by the Extended Executive in October 2014. OWNER: PMO and Associate Director of Strategy and OD | Director of Finance Oversight of HIGH risk through Finance and Investment Committee. | 3 | 2 | 6
GAP: Insufficient consultation with stakeholders. ACTION: the schedule and process for developing the Business Plan has been amended to ensure all key stakeholders are identified and to allow time for effective consultation. OWNER: PMO and Associate Director of Strategy and OD
[5 empty] | Each year the Trust completes an Annual Strategic Plan which is approved by the Board and submitted to Monitor/NHS Improvement. A 5-year Strategic Plan 2014-19 was submitted to Monitor in June 2014. A 2-year Operational Business Plan was submitted to Monitor in May 2015 which set out the plan to deliver appropriate high quality and cost effective services for patients. The Trust's Operational Plan for 2016/17 was submitted in April 2016 and set out the Trust's business plan over the next 12 months. |  |  |  |  | GAP: Key Performance Indicators (KPIs) not effectively aligned with strategic objectives and Business plans. ACTION: working with Performance teams, CUBE, and directorates to agree KPIs and method for reporting. Improvement anticipated for FY16 plans. KPIs continue to be developed in conjunction with PLICS, activity-based budgets and productivity management. PDRs in the process of review and will include alignment of personal objectives with those of the Trust. OWNER: PMO and Associate Director of Strategy and OD
[5 empty] | The annual planning process begins in the autumn and is "bottom-up" including consultation with internal and external stakeholders, working with Directorates, aligning priorities with the strategy and developing a Trust-wide Business Plan and Priorities. |  |  |  |  | GAP: Business Planning process and strategic objectives not sufficiently aligned with individual PDR processes. ACTION: working with L&D and HR to align processes. OWNER: PMO and Associate Director of Strategy and OD
2.3 | Non-delivery of CIP savings and productivity gains may lead to: failure to deliver the Trust's financial plans; additional scrutiny and intervention by NHS Improvement (formerly Monitor); insufficient cash generation to fund future capital programmes. | 5 | 5 | 25 | Overall CIP target is set as part of the financial planning process for the annual plan and long-term plan. Each Directorate and Corporate Function identifies themes that are developed into project plans and any gap to the overall target is identified and mitigations considered within the overall review of risks and opportunities for the financial plan. Where possible, provisions are made for some underachievement. | Governance and assurances include: - Project governance through weekly project meetings to review individual project progress against objectives. - Directorate Governance - a monthly confirm and challenge of each project led by Service and Clinical Directors to ensure projects remain on track and suitable recovery actions are in place where required. - Programme Governance by the CIP Delivery Group (Executive led) - reviews monthly the overall CIP programme, seeks assurance on all projects and gives close scrutiny to outliers and related recovery actions. - Overall governance provided by the OHFT Board - monthly report to the Board to provide assurance on progress and recovery actions. Regular reporting also to the Finance and Investment Committee. - Internal Audit Plan 2015/16 included review of CIP - report confirmed that governance arrangements had been strengthened. | 4 | 4 | 16 | GAP (controls): priority for attention and resource necessary to deliver CIPs is diluted by the demands of other transformational projects. ACTION: Executive and Service Directors to ensure that all transformational projects are properly integrated with the CIP projects. Any conflict in priority to be raised at the CIP Programme Management Board. OWNERS: Directors and Executives | Chief Operating Officer Oversight of EXTREME risk through regular reporting to the Finance and Investment Committee and the Board | 4 | 2 | 8 | The Finance and Investment Committee meeting on 06 September 2016 received an update that the Adult Directorate was at significant risk of not being able to meet its CIP target and that no major mitigations could be put in place to avoid this. The projected shortfall would mean a call on the Trust’s reserves and would therefore impact on investment. Longer term non-recurrent CIP would also impact adversely on FY17. The Well Led quality sub-committee meeting on 14 September 2016 also received an update that there was a risk of non-recurrence in CIPs for the Children & Young People's Directorate for this year and next year.
[5 empty] | Following the Deloitte report in February 2015, improvements to the management and coordination of the CIP programme have been implemented to improve the definition and delivery of CIP themes. - Establishment of a CIP Delivery Group, chaired by the Chief Operating Officer and with Medical Director, Director of Nursing and Director of Finance as core members. - The PMO will report into the CIP Board and project directors will attend to provide project updates. - An amount equating to the CIP target will be removed from budgets in advance and the CIP projects tracked against these budgets - Additional resource will be allocated to the PMO as required to establish strong controls and assurance. |  |  |  |  | GAP (controls): the means to delivering the required levels of CIP whilst maintaining service quality is the ongoing improvement in productivity and appropriate skill-mix. ACTION: the analytical skills and the information necessary to measure and compare productivity to be developed/brought in. OWNERS: Directors and PMO
GAP (assurance): there is a need to ensure a longer view of CIP programmes over the next 2-3 years rather than a single year view. ACTION: Directorates with support from Deloitte have identified and developed plans for Wave 1 & 2 Service Reviews on mobile working, skill mix and productivity challenges. Wave 1 Service Reviews took place December 2015 - January 2016. Wave 2 Service Reviews took place January - February 2016. OWNER: PMO and Service Performance leads
[5 empty] | The Finance and Investment Committee meeting in July 2016 received an update that FY17 CIPs were forecasting below target mainly due to lack of plans to reach the target of £6.5 million ad some slippage. A healthcare consulting firm was commissioned by the Chief Operating Officer to work with PMO and the directorates to: assure the current CIP position; close the gap between projected CIPs and the FY17 target; and create long term transformational plans for clinical services. |  |  |  |  | GAP (controls - Deloitte findings): The Finance and Investment Committee (FIC) in July 2016 requested analysis of the opportunities previously identified by Deloitte, in particular any reasons for not pursuing ideas identified, and consideration of whether further action could be done to build on the work already carried out by Deloitte. ACTION: The FIC in September 2016 heard that the previous Deloitte work had highlighted schemes that offered savings of £5.36m that the Trust could meet. However other savings identified by Deloitte had proved unachievable due to reasons such as unexpected increase in demand, increased complexity of service, or transformation that required a longer time to be implemented. The Deloitte report had stimulated ideas for staff and they were now in the process of creating new plans of which they took ownership and therefore were more likely to deliver. OWNER: PMO and Chief Operating Officer
3 | Strategic Objective 3: Delivering Innovation, Learning and Teaching Goals: the impact of the AHSN, AHSC and CLAHRC will be maximised; we will collaborate in research and innovation; and we will deliver high quality teaching
3.1 | Failure to fully realise the Trust's academic and Research and Development (R&D) potential may adversely affect its reputation and lead to loss of opportunity. | 3 | 3 | 9 | Controls include: - work to improve governance in R&D both locally and through the Oxford Collaboration for Leadership in Applied Health Research and Care (Oxford CLAHRC); - membership of the Oxford Academic Health Science Network (Oxford AHSN) and the Oxford Academic Health Science Centre (Oxford AHSC) to maintain a prominent academic and R&D profile; - academic collaborations such as OAHSN - Psychological Perspectives in Education and Primary Care (PPEPCare) with Operational Management Group established to oversee project implementation in 2016; - expansion of the R&D team to improve patient recruitment into studies which would benefit current studies and future bids for new studies (including commercial studies); - collaborative work with the Joint Research Office at OUH; - Bio-medical Research Centre (BRC) - as at September 2016, successful joint bid by the Trust and the University of Oxford for one of only two BRCs across the counrty dedicated to mental health and dementia; and - application for Collaborative Research Fund (CRF) - potential positive impact upon funding. | Internal reporting including: - to the Board as (publicly available) twice yearly reports on R&D covering KPIs on the number of patients recruited to studies and the number of studies underway/planned - most recently received in June 2015, January 2016 and September 2016; and - R&D forums (R&D Governance Group and R&D Strategy Forum) reporting to the Effectiveness quality sub-committee. | 3 | 2 | 6 | GAP (controls - funding): The level of research funding is predicted to drop by £890k between FY17 and FY18. The significant reductions are due to the Clinical Research Facility funding coming to an end (re-applied)(£717k), no NIHR Final Payments due next year (£180k) and reduced Department of Psychiatry\Trust CLAHRC RCF (£310k) following the completion of all NIHR studies. The lower RCF will reduce the Trust's flexibility and ability to potentially pump-prime certain areas of research. ACTION: to be kept under review. CRN & Commercial, NIHR sub-contracted and other income is assumed to remain constant but will be reviewed in detail as part of the FY18 budget process. OWNER: Head of R&D | Medical Director | 3 | 1 | 3 | Successful joint bid by the Trust and the University of Oxford for a new National Institute for Health Research Biomedical Research Centre (NIHR BRC), one of only two across the country dedicated to mental health and dementia. Over five years, the centre will receive £12.8 million pounds to fund its research. Research at the new NIHR Oxford Health BRC aims to enable the NHS to routinely use innovations such as using an app to track mood changes to help diagnose and personalise treatments for mood disorders, treat paranoia using virtual reality simulations, treat psychotic disorders using neuroimmunology and deliver therapy over the internet for conditions such as anxiety.
[6 empty] | External assurance through: - benchmarking of Trust performance by the Thames Valley Comprehensive Local Research Network; and - Internal Audit. The Internal Audit Plan 2014/15 included a review of the Research Governance Framework. |  |  |  | GAP (controls): expansion of R&D team may still not result in increased/sufficient patient recruitment for studies. ACTION: outcomes to be kept under review. As at April 2016, the Trust is achieving 100% against the target of recruiting the first patient into a study within 70 days of receiving a valid research application. Results will fluctuate due to the low numbers of studies (typically 10). However, R&D still struggling to meet the time to target for recruiting a set number of patients for individual studies within the recruitment period (25%). This will take time to change as studies generally run over a minimum of 12 to 24 months. OWNER: Head of R&D
GAP (controls): how collaboratively governance processes work with the Joint Research Office at OUH. ACTION: R&D is working collaboratively with the Joint Research Office at OUH, under agreement, and, for example, is receiving support to ensure that research contracts are reviewed and drawn up appropriately. Work is taking place to streamline processes and working practices across the organisations. OWNER: Head of R&D and Medical Director
GAP (controls - governance processes): move to the Health Research Authority (HRA), through which all research studies will need to be approved, and ongoing work to integrate changes to governance processes. HRA will be providing NHS permission for studies that cover the whole of the NHS and these are not site specific. This has the potential to give the green light to researchers to start studies and approach Trust clinical teams without coming through the R&D department and puts the Trust at risk of being unaware what studies are taking place within the organisation. ACTION: to be managed through the Research Governance Group. OWNER: Head of R&D
GAP (assurances - Research Governance Group): attendance and representation from members has been inconsistent and discussions are ongoing as to how to increase involvement and how the research governance structure will develop pending successful NIHR infrastructure awards. ACTION: as at September 2016, terms of reference and membership due to be reviewed in the coming months to take into account the new meetings structures within R&D. OWNER: Head of R&D
3.2 | Failure to be sufficiently innovative and leading edge in its practice may lead to the Trust not being able to keep current contracts or realise its potential in a competitive market. | 4 | 4 | 16 | Provision of high quality services through effective and innovative evidence-based service models e.g. in Mental Health and Interface Medicine, which result in good patient outcomes. Development of Outcomes Based Commissioning in Mental Health and Older Peoples services. | In relation to the provision of high quality services, cross-reference to assurances under BAF risk SO 1.1. | 3 | 2 | 6 | GAP (controls - service models) & ACTION: service remodelling complete but outcomes to be reviewed and evaluated by the Executive. Also cross-reference to gaps/actions in controls/assurance for BAF risk SO 1.1 and 1.2. OWNERS: Chief Operating Officer and Executive Directors | Medical Director Oversight of HIGH risk by the Board directly and through extended Board strategy sessions as appropriate | 3 | 2 | 6 | In July 2016 the Trust was successful in leading an application to develop a new model of care for low and medium secure adult mental health services - the Thames Valley and Wessex Forensic Mental Health New Care Model. One of the rationales for developing the new model of care was to promote innovation in service commissioning, design and provision that joins up care across in-patient and community pathways across and beyond the NHS. The Trust will work in a network with the following providers of specialist mental health care to coordinate inpatient and community based services: Berkshire Healthcare NHS FT, Southern Health NHS FT, C&NWL NHS FT, Dorset Healthcare NHS FT, Solent NHS Trust and Response (voluntary sector provider promoting independent and community living).
[5 empty] | Use of innovative tools e.g. roll-out of Clinical Record Interactive Search (CRIS). | Monitoring through Effectiveness quality sub-committee and CRIS oversight group meetings attended monthly to discuss submitted applications and monitor the audit of CRIS searches. The group is chaired by the Medical Director and Caldicott Guardian and is attended by the CRIS Coordinator, Director of IT, Head of Information Governance, Head of R&D, two Carer/patient representatives, representatives from the trust Clinical Directorates, Trust Audit Team and University. |  |  |  | GAP (controls - CRIS): CRIS operational. 3 research applications approved by April 2016 and 6 applications approved by September 2016 (and total to date). However due to static data set from 5 years of RiO electronic health records, not as much uptake as hoped. Also dependent upon CareNotes functionality to record information. ACTION: move from D CRIS service contract to UK CRIS service contract (although access to current D CRIS still available ). May also increase uptake. Testing now started on UK CRIS which will move to a live data set via CareNotes. Go live for UK CRIS planned for end September 2016. OWNER: Head of R&D
[5 empty] | Restructured R&D governance processes to improve effectiveness and promote innovation through the establishment of a R&D Governance Committee and a R&D Strategy Forum. | R&D reporting being monitored through Board and Effectiveness quality sub-committee (cross-reference to SO 3.1).
[5 empty] | An Innovation sub-group of the Drugs and Therapeutics Group (DTG) has been established with the aim of discussing proposals for the development of innovative treatments. Work has been undertaken to produce a standardized format for submissions. It is planned that this sub-group will link closely with the R&D Department to consider how innovation may lead to future research. Recent innovation has, for instance, included collaborative work with the University of Oxford on the first UK study into the use of ketamine intravenous infusions for people with treatment-resistant depression (the study reported in April 2014). A clinic has also been established for the therapeutic use of ketamine in the treatment of depression. | The establishment of the Innovation sub-group may increase interest amongst academic staff at the University Department of Psychiatry, who may not otherwise attend the DTG. Those submitting proposals will be invited to present to the sub-group and engage in the subsequent discussion, to help the sub-group consider any ethical and governance issues. The Innovation sub-group will be monitored through the DTG and Effectiveness quality sub-committee. Improvement and Innovation annual event also took place on 19 April 2016 to showcase the improvement work which teams across the Trust have been undertaking in the past 12 months. |  |  |  | GAP (assurances - monitoring): lack of centralised monitoring and evaluation of the various innovative practices and developments taking place across the Trust at various levels, including locally within Directorates, and between the Trust and other organisations. ACTION: the Chief Operating Officer developed a list of local Directorate innovations during August 2014. The Board Seminar in September 2014 considered Business Development Opportunities. Translating Innovation into Practice was the theme of the Senior Leaders' Conference in November 2014. An improvement and innovation event took place on 24 February 2015: "Improvement: Everybody's Business" which was organised by the Improvement and Innovation Team to showcase improvement work from across the Trust. OWNER: Chief Operating Officer and Improvement and Innovation Team (Senior Programme Manager).
[5 empty] | Participation in the Oxford CLAHRC, Oxford AHSN and Oxford AHSC and use of these structures to improve and innovate systems around Dementia, Early Intervention, patient experience and patient reported outcomes, better management of medical-psychiatric comorbidity and patient self-management of chronic disease. | The Trust hosts the Oxford CLAHRC and is a partner in the Oxford AHSC with Oxford Brookes University, Oxford University Hospitals NHS Trust and the University of Oxford. Chief Executive's involvement at Board level with the Oxford CLAHRC (Chair of the CLAHRC Board) and Oxford AHSN.
[5 empty] | Development and maintenance of good relationships with commissioners through understanding and meeting their targets. | External assurance through contract review meetings with Commissioners to discuss outcomes and awards.
[5 empty] | Developing strategic partnerships within the NHS and indepedent sector, for example the work taking place with Oxfordshire CCG, Oxford University Hospitals Trust and Oxfordshire County Council for older people on the outcomes based single contract focused on the acute assessment/admission and discharge/reablement pathway. Development with social care and federated primary care relating to integrated locality community services; all reporting through to the Oxfordshire Transformation Board. In Buckinghamshire all transformational work reported via Healthy Bucks Leaders. | Internal assurance through: - reporting to the Executive on the Business Intelligence pipeline; - the Improvement and Innovation Team; and - Internal Audit. As part of the Internal Audit Plan 2014/15, a review took place of Service Innovation and Business Development which focused on the following projects: Aston Team Working Programme; Making Every Contact Count; Tender Workshop; Flexible Workforce Management Programme; the Whiteleaf Centre; and Bicester Community Hospital.
4 | Strategic Objective 4: Developing Our Business through Collaboration and Partnerships Goals: we will work in collaborative partnerships; we will maintain and grow our services where we add value; and we will have strong relationships with our stakeholders
4.1 | Failure of the Health and Social Care Systems in which we work to act together to deliver integrated care. Changes in Health and Social Care Systems may impact adversely on the operations of the Trust. | 5 | 5 | 25 | The Trust's Chief Executive chairs the Oxfordshire Transformation Board and is a member of Healthy Bucks Leaders. Executive Directors and Service/Clinical Directors engage strategically and operationally, working jointly with all CCGs, local authorities and other partners including GP providers to understand strategic issues facing CCGs and provide input and support to delivering integrated services within the context of high levels of change within the health and social care systems. | Reporting through OPS SMT, Executive Team and Board. Participation in key strategic, operational and contracting meetings by Service Directors, Clinical Directors and Chief Operating Officer | 4 | 3 | 12 | GAP (assurances - whole system working across counties): impact of local government change and devolution. Oxfordshire Devolution - in November 2015, Oxfordshire local authorities submitted a proposal to central government for devolution involving health and social care. Follow-up discussions taking place through CCG and County Council. Also separate proposal for development of unitary authorities made public by District Councils in Oxfordshire which entails some integration and devolution of health and social care. ACTION: ongoing monitoring and participation. Updates to the Board from the Chief Executive. OWNER: Chief Executive | Chief Operating Officer Oversight of HIGH risk through the Board directly and Board strategy sessions as appropriate | 3 | 3 | 9 | Oxfordshire County Council proposed an independent review of local government structures in Oxfordshire and appointed Grant Thornton to consider how local government could be reorganised to ‘reduce costs, improve service outcomes, support economic growth and enhance local engagement’. The city and district councils commissioned a study from PricewaterhouseCoopers (PwC) into the future of local government. Both the Grant Thornton Study and the PwC Report were published in August 2016. The County, as well as City and District officers have since met with officials from the Department for Communities and Local Government (DCLG) who were positive about the potential for achieving significant change if local partners work together to identify shared priorities and solutions.
[5 empty] | Development of alliances and partnerships with other organisations, including the voluntary sector, to deliver services into the future. Development of Oxfordshire Integrated Locality Teams. Oxfordshire Mental Health Partnership - development of Recovery College completed and outcome measures being monitored monthly through contract meetings and reported monthly to CCG via schedule 4 and OBC measures. | Whole system working across each county to deliver Integrated Care. Improved whole systems working and process with good engagement with Partners demonstrated through the Oxfordshire Transformation Board, Healthy Bucks Leaders and System Resilience groups. |  |  |  | GAP (controls - engagement and joint working): concern around overlaps between OBC processes and the impact of the Better Care Fund (government pooled fund to promote integrated care). ACTION: ensuring engagement in national Better Care Fund dialogue at a national and local level. Strategic linking of Outcomes Based Commissioning with the Better Care Fund. OWNERS: Chief Operating Officer, Director of Finance and Chief Executive
[5 empty] | Progressing discussions with Oxfordshire’s GP Federations to establish opportunities for more formal partnerships and collaborations. PML, OxFed and Oxford Health FT are exploring a united approach to new models of delivery and contracting, to be operational across much of the County from 01 April 2017. More recently that discussion has also involved colleagues at OUH. Proposals will describe how community services can be integrated with primary care to provide a genuine 'place' based service, addressing population management, prevention and access, and in addition how the relationship with the urgent care pathway and hospital based services will work in the short term and longer term. | Reporting to/discussions with Oxfordshire CCG and Trust Board. |  |  |  | GAP (controls - Oxfordshire GP Federation engagement): as at October 2016, written outline of proposals and Memorandum of Understanding to be developed to describe proposals. ACTION: to develop and make available to the Board. OWNER: Chief Executive
[5 empty] | Ability to deliver integrated care through collaboration and Partnership e.g. Mental Health OBC, Talking Space. Older People's OBC being advanced through FY16 Winter Plan. | External assurance including: collaborative planning with OUH; delivering on commissioners' strategic intent through initiatives such as moving to 7-day working via the service remodelling; and partnership approaches on Mental Health and OP services. Joint working with commissioners on new models of care and extension of contracts and MCP processes. |  |  |  | GAP (controls - engagement and joint working): financial pressure on County Councils and Social Care impacting adversely on Health. ACTION: Executive Directors and other directors engage in whole system clinical and financial planning. Engagement with NHS Improvement (Monitor) and introducing them into system-wide discussion with commissioners. Confirmation that the the Trust's National Reference Costs have improved to a score of 87 and the impact on financial flexibility. OWNERS: Chief Operating Officer and Executive Directors
Business development strategy for Trust agreed at Board Seminar in September 2014 as consolidation and expansion where possible within key operating areas - Oxfordshire, Buckinghamshire and Wiltshire/BaNES for core service offerings. Expansion in wider geography may be considered for more specialist services. Revised processes agreed for consideration of new business opportunities via OPs SMT and Exec Team.
4.2 | Failure to work collaboratively and effectively with external partners may compromise service delivery and stakeholder engagement. | 4 | 4 | 16 | Controls include but are not limited to: - Section 75 agreements in place for Oxfordshire and Buckinghamshire; - developmental work with Police colleagues e.g. joint working with Thames Valley Police on mental health street triage and Section 136 suites; - the Multi-Agency Safeguarding Hubs (MASHs) in Oxfordshire and Buckinghamshire to bring together Health, Social Services, the Police, Education and Youth Offending services in an integrated multi-agency team to share information appropriately and securely on safeguarding children or adults in order to take timely and appropriate action to safeguard them from harm; - development of Mental Health Crisis Concordat across Thames Valley to improve outcomes for people experiencing mental health crisis through local partnerships of health, criminal justice and local authority agencies. Crisis Concordats signed in both Oxfordshire and Buckinghamshire; and - mental health resilience funding for one year projects achieved (as at November 2014) for: (i) enhancing the Emergency Department Psychiatric Service based at the John Radcliffe and Horton Hospitals; (ii) providing additional funding for the Psychiatric Inreach Liaison Service in Buckinghamshire; (iii) implementing a street triage programme in Buckinghamshire to provide mental health support and advice to Thames Valley Police; and (iv) providing mental health nursing support to South Central Ambulance Service to provide the 111 coordination centre with a mental health nurse. Projects rolled out January to March 2015. | Monitoring and collaboration through Section 75 Joint Management Groups (JMGs) in place in both Oxfordshire and Buckinghamshire. Oxfordshire now has service user representation and quarterly joint meetings with the commissioning JMG. MH OBC contracts agreed and signed September 2015. Sub contracts developed between the Trust and partners and legal partnership agreement being developed. Alliance between OUH and the Trust developed and governance work progressing. | 3 | 3 | 9 | GAP: high level strategic aims been developed for partnership working but up to early 2016 not yet a supportive governance framework and a list of partnerships is not in place. Updates on partnership working not reported to Board on a regular basis (and would help to inform future development of partnership working). ACTION: since May 2016 the Board now receives quarterly updates on Strategic Partnerships including partnership performance and innovations and effectiveness. Aim of reporting to: underpin development of individual partnership working arrangements and any wider development; providing some supporting definition; and identify any further steps that might be required. A list of contractual partnerships and working alliances will also be developed and monitored. OWNER: Chief Operating Officer | Chief Operating Officer Oversight of HIGH risk by the Board directly and through Board strategy sessions as appropriate | 3 | 2 | 6 | Contract position - only one contract remained to be signed with Oxfordshire CCG (OCCG). An interim agreement, which was extended to the end of July 2016, was put in place to allow OCCG, OUH and the Trust to develop an integrated partnership approach, particularly around the frail & elderly urgent care pathway. Unfortunately, agreement could not be reached on an effective partnership approach and OCCG consequently agreed a contract with OUH for £8m more than was anticipated. With OCCG in a tight financial position the Trust has been working to finalise its contract in line with its original financial plan assumptions.
[6 empty] | Problems in Practice Group reviewed, links to JMG to ensure health and social care and commissioning approach to Section 136 issues. |  |  |  | GAP (controls - integration with social care for OP): to put in place formal partnership agreements between NHS and voluntary sector organisations to implement integration with social care for OP physical health services. ACTION: Mental Health Outcomes Based Commissioning contract agreed and signed September 2015. Older People's Outcomes Based Commissioning - contract negotiations commenced. OWNERS: Chief Operating Officer, Director of Finance, Service Directors and Clinical Directors of 3 clinical directorates (Children & Young People's Services, Adult Services and Older People's Services)
[5 empty] | New service models include integration with social care for Older People's (OP) physical health services. Partnership agreements to be put in place between NHS and voluntary sector organisations to implement. | Internal Audit review of Partnership Governance Arrangements (completed April 2016) - it did not therefore evaluate the quality and effectiveness of partnership working but it has been recognised that the CQC commented positively on partnership working by the Trust in its report following inspection in Sept/Oct 2015 |  |  |  | GAP (controls): continued development of Urgent Care MH Services. ACTIONS: Street Triage and PIRLS in Buckinghamshire and MH input into SCAS call centre. OWNER: Chief Operating Officer
4.3 | If the Trust does not proactively engage with its membership, patients and the wider public then this may compromise its ability to listen and respond to feedback, involve stakeholders proactively and communicate effectively and transparently. | 3 | 3 | 9 | Controls include but are not limited to: - Council of Governors and working groups of the Council e.g. the Working Together Group; - Communications function part of the Chief Executive's team; - management of the membership database through the Communications function; - Trust website (content managed by Communications); - Patient Involvement and Experience Strategy 2016-19 (includes engagement with membership, the development of a single members' database, increased working with the voluntary sector and review of the Use of Volunteers Policy); - development of Community Involvement Framework including Fundraising Strategy and Volunteering Services Strategy; - establishment of local/divisional patient groups; and - Complaints service, PALS surgeries and results of patient experience surveys. | Annual report and reports for Council of Governors demonstrate engagement with FT members. | 2 | 3 | 6 | GAP (controls): Trust website to be updated. ACTION: new template for the Trust website deployed since July 2015 and offering a more picture-led user friendly interface for people to find out about our services. A better search index has been implemented and this will continue to have incremental improvements. There have also been improvements to categorised search results and there is ongoing investigation into additional deep search solutions. Web Strategy Group meetings (with membership from Comms, IT, directorates and membership invited from HR and PALS). The group has agreed and implemented processes, in line with the Trust’s web strategy, to take on oversight and governance of current and future developments, as well as the work of the web editorial group. A recent example of this in practice is a decision to develop a new web area to promote OHFT's research and development work. OWNERS: Head of Communications and Engagement and Director of Informatics | Director of Corporate Affairs & CoSec | 2 | 2 | 4
Internal reporting including to the Caring and Responsive quality sub-committee and the Quality Committee on complaints, PALS, patient experience and involvement; and weekly monitoring of complaints at Clinical Standards Weekly Review Meeting. Charity Committee monitoring development of Community Involvement Framework including Fundraising Strategy and Volunteering Services Strategy - most recent update provided to the meeting in July 2016.
[6 empty] | Service redesign project briefs include engagement element. |  |  |  | GAP (controls): strategic frameworks for patient participation /involvement /engagement and Community Involvement/Fundraisingto be developed ACTION: Cross-reference to the gap/action at SO 1.1 above. New Patient Involvement and Experience Strategy 2016-19 in place. Actions in relation to membership and volunteers development to be progressed but work around volunteering developing and being monitored through the Charity Committee. OWNER: Director of Corporate Affairs & Company Secretary
GAP (controls - Council and membership engagement): if the member attrition rate is high and levels of engagement are low then the Council/membership will not fulfil its purpose and the Trust will not only lose the significant power of voice, but is likely to be more removed from the needs of the community and will risk breaching its authorisation. ACTION: Community involvement. Work with membership to develop 2-way commuication (i.e. learn from each other); develop mutually beneficial relationships with current membership and ensure cohesive approach in dealing with local partnerships; ongoing recruitment of new members; evolve members into volunteers, donors, supporters and ambassadors. OWNER: Director of Corporate Affairs & Company Secretary
5 | Strategic Objective 5: Developing Leadership, People and Culture Goals: staff will be satisfied with the quality of their work; staff and teams will be high-performing; and we will recruit and retain an excellent workforce
5.1A | Inadequate planning for current and future workforce requirements (including number of staff, calibre, skills and training) or ability to respond to changing requirements in a timely manner may lead to: impaired ability to deliver the quantity of healthcare services to the required standards of quality; and inability to achieve the business plan and strategic objectives. | 5 | 3 | 15 | Controls include but are not limited to: - robust recruitment processes and retention measures; - on-going staff development through resources such as the Learning and Development training matrix which defines subject areas and frequency of training for staff and provides access to appropriate e-learning; - the Performance Framework including the Performance & Development Review Policy and supporting process; - Directorate workforce plans are linked to Business plan/savings plans with regular processes for review; - Senior HR Business Partners are trained in the principles and approach to the Trust workforce planning process developed with input from L&D and Finance; - workforce planning also included as part of service remodelling which will then inform workforce plans for the next three years; - analysis of leaving questionnaires; - Workforce Development manage training programmes for Health Visitors in line with plan; - Medical staffing workforce plan; - implementation of flexible Workforce Management System and centralised Bank of staff (38% of Trust live by December 2016, 71% anticipated by end of next wave of implementation). Provides detailed management information to drive efficiencies in staffing use and control of temporary staffing spend; - increased HR activity on Attraction and Recrutiment measures including: advertising through Twitter and Instagram accounts, regular meetings with Job Centre Plus, organising recruitment open days and attending job fairs and careers events, advertising through "Jobs the Word"/RCN/Stonewall, meetings with agency staff to explore barriers to moving to substantive roles; and - increased HR activity on Recruitment efficiency measures including increased notice periods, introduction of a temporary candidate pipeline manager, introduction of in-house recruitment database. | Monitoring and reporting include, but are not limited to: - reports to individual managers, teams, directorates and to the Board enable monitoring of leavers, vacancies and recruitment, absence/sickness and training status; - the Board receives as a public standing item a Workforce Performance Report which considers: recruitment activity; turnover; sickness; and bank and agency use; - strategic review by the Board e.g. October 2015 Board strategy session focused on Workforce/Staff Engagement (HR) and October 2016 Board Seminar focus on Workforce Risks and Issues, Recruitment and Retention; - new reporting since 2014 to the Board on inpatient safe staffing levels by the Director of Nursing; - information is reviewed and actions determined at monthly Directorate senior management meetings and Operations SMT; - Recruitment Action Group; - Staff Movement Form introduced July 2016 which requests more detailed information from line managers (to inform Retention strategies and to support information available through Leaver Forms, Exit Questionnaires and Exit Interviews); - the HR senior management team hold a performance review each month; and - Internal Audit reporting on HR processes including Internal Audit review of HR (January 2016) - Workforce Management System. All Phase 1 internal system changes been implemented. Flexible Workforce Project Board established. Additional staff to be recruited to increase support for live units on the Workforce Management System and to provide a centralised bank facility. | 4 | 4 | 16 | GAP (controls and assurances): retention/recruitment balance and impact of high staff turnover (retention issue) on ongoing work to fill increasing number of vacancies (recruitment issue). More strategic solutions required to address retention issues in order to have more positive impact upon recruitment issues. Lack of information re retention issues - reasons for leaving on Leaver Form are restricted and uptake of Exit Questionnaires and Exit Interviews has been poor therefore quantity of information available needs to be improved. Need to also respond to Staff Survey results (see Gap under risk SO 5.1B below). ACTIONS: Further to Board Seminar October 2016, HR to present a more detailed plan of options, benefits and costs by end 2016. OWNER: Deputy Director of HR | Director of Finance Oversight of HIGH risk through HR/workforce reporting to Board | 3 | 2 | 6 | Detailed discussion at Board Seminar on 12 October 2016 focused on Workforce Risks and Issues, Recruitment and Retention. Further follow-up by end 2016. HR to present a more detailed plan of options, benefits and costs.
[10 empty] | GAP (controls - staff and career development): risk of losing skilled nurses (retention) to other healthcare organisations/trusts who have developed more attractive clinical nurse specialist/consultant nurse roles. The no. 1 reason given for leaving/staff movement over July-September 2016 (all staff groups, not just nursing) was promotion/better prospects. However, link to Gap above and lack of information re retention issues - the no. 2 reason given on the form was "no details provided". Recognise need for clinical as well as managerial career paths and consider speed of progression to Band 6 nursing roles. ACTION: develop more specialist nursing roles to retain staff who want to remain clinically focused. Work planned to commence in Adult Directorate before roll out across other clinical directorates. Other retention activities/strategies: apprenticeships to grow the existing workforce; developing career development pathways in some areas for Bands 4 & staff; role redesign being considered as part of service reviews OWNER: Deputy Director of HR |  |  |  |  | As at October 2016, increasing pressure from NHS Improvement (NHSI) to reduce agency spend. Temporary staffing use across the Trust continues to grow and agency spend high - will impact upon NHSI scrutiny and financial and use of resources risk rating; and agency spend will form part of STP (Sustainability and Transformation Plan) discussions. From November 2016, NHSI will share benchmarking data for all trusts in the South detailing agency spend in relation to each trust's workforce spend and agency ceiling.
GAP (controls): Workforce Management System (WFMS) still in implementation phase and to be fully rolled out. Also impact upon management time to be monitored - teams with high levels of temporary staffing may find that use of the WFMS increases time spent managing rostering and temporary staffing. Risk that despite implementation of WFMS, agency spend may still be high and/or above the ceiling imposed by NHS Improvement. Need to also increase recruitment of Flexible Workers to meet demand and consider whether aim to ultimately reduce demand for temporary staffing or embrace development of more flexible staffing opportunities so can be offered as a career alternative/opportunity. ACTION: complete implementation and rollout and monitor impact of usage. Develop improved reporting in conjunction with Performance team to drive efficiencies in staffing use. Develop website and use social media to actively advertise and recruit Flexible Workers. OWNER: Deputy Director of HR
5.1B | Inability to fill vacancies resulting in the quality and quantity of healthcare being impaired. | 4 | 4 | 16 | Controls include: - robust recruitment processes including the introduction of values based recruitment - values based questions are embedded in job application forms and work continues on developing recruitment materials; - minimising staff absence; - making the Trust a great place to work and publicising the fact; - the development of an overarching recruitment plan for each service to address areas of candidate attraction and retention; - collaboration with other local NHS trusts to understand the overall employment marketplace and take joint pre-emptive action where possible; - recruitment candidate pipeline to monitor effectiveness of recruitment stages; - creative aproaches to recruitment including intensive attendance at recruitment fairs and training programmes in place for HVs, DNs, Nurses, some AHP, Associate Practitioners, Doctors and Psychologists; - Apprenticeship Programme since 2015; - development pathway for HCAs; - meetings with Directorates to continue work on open days and job rotations; and - Recruitment Action Group (as at January 2016) has held initial meetings on improving links with universities. | Monitoring and reporting include, but are not limited to: - reports to individual managers, teams, directorates and to the Board enable monitoring of vacancies and recruitment effectiveness; - weekly reporting of vacancy levels and fill rates to SMT and the Service Directors; - reporting on inpatient safe staffing levels to SMT on a weekly basis; - integrated activity plan in place and is managed daily and reviewed weekly by HR and reviewed by the Operations SMT monthly; - reporting to the Extended Executive on a monthly basis regarding recruitment activity and planned actions; - the HR senior management team hold a performance review each month to review recruitment activity, including leavers exit interview data; - quarterly reporting to Health & Safety; - submission of quarterly performance report to the Board; - monitoring through Trust Risk Register at Executive and Directorate level of risks in relation to: increased levels of activity in district nursing services; and not achieving required recruitment of staff to substantive posts which may result in increased usage of agency staff; and - as at April 2015, audit of recruitment processes taken place and process mapped. | 4 | 4 | 16 | GAP (controls - recruitment processes): dealing with national and local recruitment challenges and the impact on pressure on staff numbers, work-related stress, spend with agencies and quality of care provided. Also linked to the Trust's ability to retain staff. ACTION: Further to Board Seminar October 2016, HR to present a more detailed plan of options, benefits and costs by end 2016. OWNER: Deputy Director of HR | Director of Finance Oversight of HIGH risk through HR/workforce reporting to Board | 2 | 3 | 6 | Detailed discussion at Board Seminar on 12 October 2016 focused on Workforce Risks and Issues, Recruitment and Retention. Further follow-up by end 2016. HR to present a more detailed plan of options, benefits and costs.
GAP (controls - recruitment processes): impact upon operational management of constant advertising and interviewing and time away from the day job. Also impact because of increase in the number of acting up/secondment roles in order to cover vacancies - leads to chains of staff acting up and additional staffing gaps being created. Impact upon HR of increased candidate pipelines due to the number of vacancies at any one time - HR resourcing required in order to take forward change activities and support the recruitment process. ACTION: increase recruitment efficiency e.g. through increased notice periods, introduction of a temporary candidate pipeline manager and introduction of in-house recruitment database. OWNER: Deputy Director of HR
GAP (controls - making the Trust a great place to work): need to improve staff experience and respond to issues identified by Staff Survey results in order to improve retention and take pressure off recruitment. Health & Wellbeing to be addressed. ACTION: respond to Staff Survey results e.g. as at October 2016, training for managers to ensure that everyone is getting meaingful appraisals; and development of Fair Treatment at Work Facilitators to provide confidential support to all staff. Health & Wellbeing Action Group now operational (see recent presentation to the Board meeting in July 2016) and empowering health and wellbeing in the workplace and using Champions to create intiatives at a local level. OWNER: Deputy Director of HR
5.2 | Failure to put in place a coherent and co-ordinated structure and approach to organisational development and leadership development may jeopardise: (i) the development of robust clinical and non-clinical leadership to support service delivery and change; (ii) the Trust becoming a clinically-led organisation; and (iii) the Trust becoming a "well-led" organisation under the CQC domain. | 4 | 4 | 16 | Controls include but are not limited to: - service model review and modifications of pathways across Operations (cross-reference to SO 1.2 and the risk against failure to deliver integrated care); - completed restructuring of Operations Directorates to provide for development of clinical leadership and for a social care lead in each directorate (completed March 2014); - "planning the future" programme and ongoing Aston Team Working programme; - effective team-based working training in place with L&D, commencing from April 2016; - multi-disciplinary leadership trios within clinical directorates to support and develop clinical leadership; - the Strategic Organisational Development Lead and the Associate Director of Strategy & Organisational Development; - the Organisational and Leadership Development Strategy Framework (approved by the Board, October 2014) - aims to maximise effectiveness of staff at every level of the Trust by coordinating a range of activities which will promote their ability to deliver high quality services and patient care and by ensuring that structures are in place to enable their effective delivery; - individual professional review and development through development of individual professional leadership strategies e.g. Nursing Strategy launched in November 2015; - Leadership Development Centres (new programme started in 2014/15) - the Leadership Development Centre is a multi-disciplinary 2-day programme designed using community health and mental health scenarios to equip Bands 7&8 managers and healthcare professionals for their current roles and as leaders of change; the programme initially ran in October 2014, November 2014 and March 2015 and will run again in 2015/16 in November 2015 and February 2016; - the Well Led quality sub-committee and the Quality Committee; - Linking Leaders conferences aimed at developing strong team networks across the middle tier of management throughout the Trust and supporting the development of a positive organisational culture (running since June 2015 across the Trust's geography and localities with the aim of improving communication and developing networks across the middle tier of management); and - Trainee Leadership Board to run from Oct 2016-April 2017. | Internal monitoring and scrutiny includes: - Directorate "touch-point" discussions to assess organisational development and leadership development in the context of the outcomes of the Operations restructuring and remodelling, led by the Chief Operating Officer; - measuring the outcomes of the Operations restructuring and remodelling. The new Adult Service Model to be reviewed (cross reference to SO 1.2); - twice yearly discussions to be scheduled (for Jan/Feb and June/July) for the Executive to review leadership roles and leadership structure. Extended Executive workshop took place in March 2015; - annual Board or Board sub-committee progress review against the Organisational and Leadership Development Strategy Framework (approved by the Board in October 2014) - review at Board meeting in public July 2015; annual report on OD & Leadership Strategy to the Quality Committee in September 2016; - a regular Trust Awards event to be scheduled to recognise leadership and achievement. The first Staff Recognition Awards ceremony took place after the AGM on 10 September 2015. Next scheduled for December 2016; - use of the annual staff survey to measure progress and perception of leadership development; and - staff appraisals and ad hoc staff satisfaction surveys. | 3 | 2 | 6 | GAP (controls - application of Strategy Framework): coherent Trust-wide learning from existing leadership development projects. Localised good performance and good practice may not be picked up across the Trust. Although it may not always be necessary or appropriate for all Trust-wide learning in this area to be consistent, as opposed to tailored to meet specific leadership development requirements, it should be more coherent and delivered with more purpose. Unwarranted variation without justification may be a gap rather than variation itself. ACTION: Senior Leaders and Team away days e.g. Operations Senior Management Team away-day took place September 2014 and reviewed leadership at team level (led by Chief Operating Officer). Increased leadership focus through the Executive and Senior Leaders' groups. Leadership Engagement through Senior Leaders Conferences (x3 per year) and Linking Leaders Conferences (x4 per year). OWNER: Associate Director of Strategy & OD | Chief Executive Oversight of HIGH risk through specific reporting to Board in July 2015 on organisational and leadership development | 2 | 2 | 4 | The Trainee Leadership Board (TLB) is an idea developed by the Director of Medical Education, the Associate Director of Strategy & OD, the Strategic OD Lead and trainee doctors. TLB objectives to offer a small group of next generation clinical leaders an opportunity to learn about the current leadership of the Trust, work as a leadership team on a real problem the Trust faces and also an opportunity for the current leadership of the Trust to see how a different leadership group tackles a problem the organisation faces. Currently under development and will run from October 2016 to April 2017.
GAP (controls - individual professional review and development): co-ordinated direction of career pathways to steer staff to gain wider experiences. Note also links to Gap at SO 5.1A above re staff and career development. ACTION: development of individual professional leadership strategies. Nursing Strategy developed and launched in November 2015. However, risk that may not be sufficient capacity to deliver Nursing Strategy in a timely way. Also, talent management dependent upon PDR system roll-out. New appraisal process and training delayed following feedback from Extended Executive. More recently appointment of Associate Director of Clinical Education and Nursing who will review progress against development and delivery of leadership pathways. OWNERS: Chief Operating Officer and Director of Nursing and Clinical Standards.
[6 empty] | External Assurance: - CQC reviews. Following CQC inspection in September/October 2015, a rating of "good" was achieved in the domain/quality measurement of being Well Led. |  |  |  | GAP (controls): the annual report on OD & Leadership Strategy identified the following areas of concern at an organisational level: motivation (as a result of involvement and improvements); staff satisfaction with the quality of their work; working hours and work-related stress; and bullying, harassment and discrimination. ACTION: Current OD activities are designed to address these areas of concern, as set out in the annual report on OD. OWNER: Associate Director of Strategy & OD
GAP (controls): equality and diversity. National picture of little progress having been made in the past 20 years to address the issue of discrimination (BME and other groups including LGBT, people with disabilities and religious groups) in the NHS. ACTION: work of the Equality & Diversity Lead. NHS Workforce Race Equality Standard reporting. Focus at Board level in Board Seminar in September 2016. Current actions set out in the annual report on OD e.g. development of Equality & Diversity Strategy and various Staff Equality Networks including for BME, LGBT and Disability. Ongoing work with HR to develop routine statistical analysis to identify key areas for actions and follow-up. OWNER: Equality & Diversity Lead and Associate Director of Strategy & OD
6 | Strategic Objective 6: Getting the most out of Technology Goals: our patients and staff will have the right technology available; our workforce will have the necessary IT skills to do their jobs well; an outstanding IT service will be delivered
6.1 | Incomplete and inaccurate data and records, both clinical and operational, may lead to: less effective planning and decision-making; lesser control over service safety and quality; lesser ability to drive improvements in safety, quality and productivity. | 4 | 5 | 20 | ~ Consolidate corporate data and key metrics in the datawarehouse where metric definitions can be maintained and automated integrity checks applied. ~ A check and approval process to be in place for all key reports and data extracts. Checks to be implemented to ensure that data reported in the Performance Report is consistent with source data ~ data quality exceptions are highlighted to the Board via the Performance Report executive summary and annoted against the affected indicator score. The Board receives monthly Performance Reports (which have already been received and reviewed by the Executive) which capture performance against key targets (contractual and non-contractual) and other key performance indicators. ~ Contract KPI reports to commissioners to be reviewed jointly by Services and Contracting prior to issue ~Integrated Information Governance Policy - includes high level expectations for data quality re validity, completeness, consistency, coverage, accuracy and timeliness ~ Data Quality Strategy to be developed | Regular review of overall data quality to be implemented via the CUBE on prioritised data sets. Data Quality Group and potential re-establishment of Information Forum. Data Quality review commenced with workshop in February 2016 to explore and determine performance and reporting needs and approaches. An outcome may be re-establishment of an Information Forum. | 3 | 4 | 12 | GAP (controls & assurances): core systems data collection compliance and quality requires significant improvement. Existing CUBE performance requires improvement through additional engineering. Information Management & Business Intellingence (IM&BI) effort focused on stabilising the current position following implementation of Carenotes before new additional activities can commence. Also issue with knowledge of legacy IM&BI infrastructure held by temporary contractor staff who have now left, requiring time to address essential knowledge gap. ACTION: information asset registers to be refreshed. Data Quality Group to agree actions to improve compliance. Review of data quality after implementation of CareNotes. OWNER: Chief Information Officer | Director of Finance Oversight of HIGH risk through Quality Committee and quality sub-committees | 3 | 3 | 9 | Actions required following Internal Audit of Information Governance and Data Quality in January 2016 and Internal Audit of Data Quality in September 2016. Highlighted by the Audit Committee Chair to the Board meeting on 28 September 2016.
[6 empty] | Audits conducted on data quality and information. Internal Audits as part of the 2013/14 plan were carried out on data pseudonymisation and the CUBE. Internal Audit Plan 2015/16 included review of Information Governance and Data Quality. Internal Audit Plan 2016/17 included Review of Data Quality to ensure that an adequate and effective control framework exists in the area of planning and delivery of the Trust’s Data Quality. Actions required following Internal Audit of Information Governance and Data Quality in January 2016 and Internal Audit of Data Quality in September 2016. |  |  |  | GAP (controls): no overarching document to provide assurance on data quality of Performance Report indicators. Performance data not consistently signed off by indicator owners. Formalised programme of audit for performance report indicators not in place. Performance report indicators not RAG rated for data quality. Risk of inaccurate information being reported or unexplained disparities between Performance Reports and source spreadsheets. ACTION: data assurance scheme/schedule to be developed to detail source of data, data validation and audit cycle for each performance indicator. As part of development of overarching data assurance scheme, all Performance Report indicators to be RAG rated for data quality and target dates for resolving data quality issues to be included in the scheme as appropriate. OWNER: Performance Information Manager and Interim Director of Performance
GAP (controls): Data Quality Strategy to be completed and approved by the Board. ACTION: strategy under construction, draft document developed as at September 2016. Appointment of new Interim Director of Performance (in post since August 2016) anticipated to progress this further and to lead on a Trust-wide programme of data quality improvements. OWNER: Interim Director of Performance
GAP (controls): data quality reporting to be standardised and actions taken to remedy shortcomings. ACTION: work with Directorates to agree reporting and correction cycle, then develop further data quality monitoring reports. OWNER: tbc - formerly Interim Head of Information.
GAP (assurances): formal joint review of contracting reports with Services to be facilitated by the Information and Business Intelligence team. ACTION: investigate current review process and suggest improvements to end to end process. OWNER: tbc - formerly Interim Head of Information.
6.2 | Failure to meet the key objectives of the project to replace the Electronic Health Record (EHR) system may lead to: inaccurate patient records; inefficient use of clinicians' time; less safe and lesser quality of care; increased cost of operation through lost opportunities to improve productivity. | 4 | 3 | 12 | Ensure actual end users are involved in the construction of the specification of requirements and selection of the solution. | A formal Project has been established using the established Prince2 methodology and including a gateway process. The Project Executive is the Trust's Chief Executive Officer. Regular Project and Programme meetings are taking place with good representation from corporate and clinical areas. Extensive workshops are occurring with clinical services to determine the system configuration required to support the clinical processes. Monitoring by the Executive. During 2016, increased regular reporting into the Finance and Investment Committee, the Board (meeting in private). | 4 | 3 | 12 | GAP (controls): ongoing work required with system supplier to improve overall performance ACTION: work taking place to develop action plan to confirm the roadmap for Carenotes over the coming years. The Trust has taken the lead in creating an online forum for other product users to take a coordinated approach to aid development. OWNER: Chief Information Officer | Director of Finance Oversight of HIGH risk through regular reporting to Finance and Investment Committee and the Board in private session | 3 | 2 | 6 | CareNotes live since October 2015 and migration has taken place from RiO. Formal review in February 2016 of delivery against the Trust's Statement of Requirements; a defined list of outstanding issues is being worked on to embed the new system. Risk: to achieve objectives and performance, ongoing commitment and engagement from directorates required together with support and resource of software provider. Discussion/ monitoring: at each meeting of the Board in private session since April 2016.
Approval of the final specification of requirements at many levels including: clinical, Directorate management and Executive Team.
Ensure supplier(s) commit to delivering against the processes of care (scenarios), Trust objectives and required benefits, and not just system 'widgets'.
7 | Strategic Objective 7: Using our Estate efficiently Goals: patients and staff will benefit from safe and appropriate environments; our estate will be sustainable and environmentally-friendly; and our estate will be cost effective
7.1 | Facilities being unsuitable or unfit for purpose may lead to: increased risk to patient safety; lesser quality of care and patient experience; increased cost of operation; breach of statutory requirements. | 5 | 5 | 25 | Controls include: - statutory compliance monitoring and reporting in place; - risk register established to identify significant risks and identify levels of investment required. Management and resolution of risks is being reviewed and prioritised by individual site/property. Used to develop FY15 Capital Programme and currently being used to develop FY16 Capital Programme including LCC requirements; - fire risk assessments have been completed by an external consultant and the Fire Advisors have in place review plans to ensure fire safety is not compromised; - ligature risks have been risk assessed using the Manchester Tool approach and the Executive has agreed the phase 1 works to be undertaken; - Annual PLACE (Patient-Led Assessments of the Care Environment) inspections for 2014 completed; - Estates Strategy in place having been approved by the Board in November 2013; - since June 2014, Estates & Facilities business plan for FY15-17 in place including workstreams for: providing safe and secure environments through risk-based prioritisation of investment; a new CAS alert process (COMPLETED); establishing a PPM programme (WORKS UNDERTAKEN); undertaking regular surveys of properties (SURVEY COMPLETED); developing a property database (COMPLETED); providing assurance through a detailed CQC Standard 10 assessment (ASSESSMENT PROCESS DEVELOPED AND UTILISED - ISSUES IDENTIFIED AND ACTION PLAN TO RESOLVE DEVELOPED); establishing a Senior Estates and Facilities meeting and working with the Services & Estates Committee (COMPLETED) and performance meetings (monthly and quarterly) (COMPLETED); - Environmental Sustainability Policy and Sustainable Development Management Plan; and - Asset condition survey now in place to enable infrastructure investment to be determined. | Internal reporting: - CQC Compliance is submitted to the Safety quality sub-committee (this includes statutory compliance); - progress re health and safty works i.e. ligatures/CAS alerts reported to the Safety quality sub-committee; - progress re delivery of capital projects required to reduce risks reported to the Capital Programme Board; - Estates Strategy is monitored via 6 monthly reports to the Finance and Investment Committee (FIC). Estates Strategy implementation reports were received by the FIC in May and November 2014 and 2015; next scheduled for November 2016. Board level review will also take place at the private Board Strategy session on 01 December 2016; - annual reporting on the Safety of the Physical Estate to the Quality Committee, most recently in September 2016; - monthly performance report undertaken with Executive lead; - monthly Estates and Facilities Senior Management Team meeting at which Safe Environment Reports presented; - Estates function now included in quarterly Directorate Performance Reviews, since July 2014 and ongoing; and - Internal Audit programme. The Internal Audit Plan 2014/15 included internal audit reviews of estates procurement and statutory compliance. Internal Audit Plan 2015/16 included review of Estates Maintenance Compliance (which achieved substantial assurance). | 4 | 2 | 8 | GAP (controls): incomplete information on statutory compliance of rented properties where the obligation sits with the landlord. ACTION: establish a register and process for regular update. Estates & Facilities business plan FY15-17 developed including workstreams to undertake regular surveys of properties and to develop a property database. OWNER: Director of Estates & Facilities | Director of Finance Oversight of HIGH risk through regular reporting to Finance and Investment Committee | 3 | 3 | 9 | Work progressing with landlords and information has been provided. A review of the risk associated with those buildings for which information remains outstanding is underway. Plan to engage with NHS Property Services - work ongoing re NHS PS specification, action plan for the rest.
[10 empty] | GAP (controls): Manchester Tool works Phases 1 and 2 to be undertaken. ACTION: Associate Director of Estates to develop Phase 2 work plan to allow start on site of works in FY17. Deputy Director of Nursing to ensure all staff are aware of remaining ligature risks. OWNER: Associate Director of Estates; Deputy Director of Nursing; and all Service Directors. |  |  |  |  | Phase 1 Manchester Tool works are on site. Remaining works will not commence until FY17.
[10 empty] | GAP (controls): Environmental Sustainability Policy and Sustainable Development Management Plan to be developed. ACTION: completed and Environmental Sustainability Policy and Sustainable Development Management Plan approved by the Quality Committee in July 2015. Quarterly meetings to be held to review SDMP delivery progress. Progress to also be reported in monthly performance reports. OWNER: Director of Estates and Facilities |  |  |  |  | Electrical Safety Policy and Safe Environment - Operational Policy developed. Energy Efficiency schemes being identified, including solar panel installation at Whiteleaf. Oxon bikes installed at Warneford and Littlemore sites.
GAP (assurances): outcome of CQC inspection which took place September-October 2015 and reported in January 2016. Improvements are required in safety to ensure that across all trust services the same high standards are observed. Inspectors noted that some of the Trust's older estate, especially inpatient mental health settings at the Warneford Hospital, was outdated for the delivery of modern mental health care. ACTION: the Trust has long been aware of the challenge of operating from Victorian buildings and a working group is currently developing options for future development of the Warneford Hospital site in particular to better address modern health care needs. OWNER: Director of Estates and Facilities

## Risk Matrix
Risk matrix (since April 2012)
|  | Likelihood |  |  |  |  | Risk Rating (R) = Impact (I) x Likelihood (L)
|  | 1 | 2 | 3 | 4 | 5
|  | Rare | Unlikely | Possible | Likely | Almost certain
Impact | 5 Catastrophic | 5 | 10 | 15 | 20 | 25 |  | Extreme risk
| 4 Major | 4 | 8 | 12 | 16 | 20 |  | High risk
| 3 Moderate | 3 | 6 | 9 | 12 | 15 |  | Medium risk
| 2 Minor | 2 | 4 | 6 | 8 | 10 |  | Low risk
| 1 Negligible | 1 | 2 | 3 | 4 | 5
Impact/Consequence
A guide to the definitions for the impact/consequences, taken from the National Patient Safety Authority (NPSA) definitions:
Potential Consequence |  | Potential impact on individuals |  |  | Patient experience/potential impact on organisation |  |  | Adverse publicity
5 Catastrophic |  | Incident leading to death Multiple permanent injuries or irreversible health effects An event which impacts on a large number of patients |  |  | Totally unacceptable level or quality of treatment/service Gross failure of patient safety if findings not acted on Inquest/ombudsman inquiry Gross failure to meet national standards |  |  | National media coverage with >3 days service well below reasonable public expectation. MP concerned (questions in the House) Total loss of public confidence
4 Major |  | Major injury leading to long-term incapacity/disability Requiring time off work for >14 days Increase in length of hospital stay by >15 days Mismanagement of patient care with long-term effects |  |  | Non-compliance with national standards with significant risk to patients if unresolved Multiple complaints/ independent review Low performance rating Critical report |  |  | National media coverage with <3 days service well below reasonable public expectation
3 Moderate |  | Moderate injury requiring professional intervention Requiring time off work for 4-14 days Increase in length of hospital stay by 4-15 days RIDDOR/agency reportable incident An event which impacts on a small number of patients |  |  | Treatment or service has significantly reduced effectiveness Formal complaint (stage 2) complaint Local resolution (with potential to go to independent review) Repeated failure to meet internal standards Major patient safety implications if findings are not acted on |  |  | Local media coverage long-term reduction in public confidence
2 Minor |  | Minor injury or illness, requiring minor intervention Requiring time off work for >3 days Increase in length of hospital stay by 1-3 days |  |  | Overall treatment or service suboptimal Formal complaint (stage 1) Local resolution Single failure to meet internal standards Minor implications for patient safety if unresolved Reduced performance rating if unresolved |  |  | Local media coverage short-term reduction in public confidence Elements of public expectations not being met
1 Insignificant |  | Minimal injury requiring no/minimal intervention or treatment. No time off work |  |  | Peripheral element of treatment or service suboptimal Informal complaint/inquiry |  |  | Rumours Potential for public concern
Likelihood
Likelihood of occurrence/reoccurence:
1 Rare | Probably never happen/recur
2 Unlikely | Do not expect it to happen/recur but is possible
3 Possible | May happen or recur occasionally
4 Likely | Will probably recur but not a persistent issue
5 Certain | Will undoubtedly happen/recur, possibly frequently

## Guidance
Guidance for completing Board Assurance Framework
Strategic Objectives | The Trust's current strategic objectives: 1) Driving Quality Improvement 2) Delivering Operational Excellence 3) Delivering Innovation, Learning and Teaching 4) Developing our Business through Collaboration and Partnerships 5) Developing Leadership, People and Culture 6) Getting the most out of Technology 7) Using our Estate efficiently
Ref | Risk identifier reference number
Risk description | Specifies the cause of the risk, what the risk/issue is and the possible consequences. A risk is the possibility that an event will occur and adversely affect the achievement of objectives.
Gross/inherent risk rating | Uses the Risk Matrix to score the risk on an inherent basis as it currently appears (before controls or assurances) for: Impact (I) x Likelihood (L) = Risk Rating (R)
Controls (mitigating actions) | Policies, procedures and practices in place to reduce the likelihood of the risk occurring or mitigate the risk if it does occur
Assurances (audit, monitoring, reporting, scrutiny) | Where evidence can be gained about how well the controls are working and what the evidence shows. For example:
| Internal Sources of Assurance | External Sources of Assurance
| Internal Audit | External Audit
| Key Performance Indicators | NHS Litigation Authority
| Performance reports | Monitor
| Committee reports | CQC reviews
| Local counter-fraud work | Royal College visits
| Clinical Audit | Deanery visits
| Staff satisfaction surveys | External benchmarking
| Staff appraisals | Patient Environment action team reports
| Training records | Accreditation schemes
| Training evaluation reports | National and regional audits
| Results of internal investigations | Peer reviews
| Serious untoward incident reports | Feedback from service users
| Complaints records | Feedback from commissioners
| Infection control reports | External advisors
| Declarations to CQC | Local networks
Information governance toolkit self-assessment
PALS reports
HR reports
Internal benchmarking
Policy evaluation or implementation reports
Net/residual risk rating | The residual level of risk remaining if all identified controls are in place and active. Also uses the Risk Matrix to score the risk for Impact (I) x Likelihood (L) = Risk Rating (R)
Gaps in controls/assurance and actions to address gaps | Where there are failures to put effective controls in place or to gain evidence about their effectiveness
Exec Lead | Executive Director who is risk owner
Target risk rating | The realistically acceptable level of risk the Trust is willing to accept in pursuit of its objectives (i.e. the risk appetite or tolerance). Failure to define risk appetite could result in taking on too much risk to achieve objectives or not enough to seize opportunities. Also uses the Risk Matrix to score the risk for target Impact (I) x Likelihood (L) = Risk Rating (R)
Delivery status and action updates | Overall status of the actions planned to mitigate the risk and progress to target for risk reduction e.g. on target, good progress, poor progress