## Sheet1
Out Of Hours Service CQC Action Plan Updated 5 May 2017
Regulated activity(ies) | Regulation |  | How the regulation was not being met | Feedback from accuracy challenges | Please describe clearly the action you are going to take to meet the regulation and what you intend to achieve | Who is responsible for the action? | How are you going to ensure the improvements have been made and are sustainable? What measures are going to be put in place to check this? | Who is responsible? | What resources (if any) are needed to implement the change(s) and are these resources available? | Date actions will be completed | How will people who use the service(s) be affected by you not meeting this regulation until this date?
Diagnostic and screening procedures. Transport services, triage and medical advice provided remotely. Treatment of disease, disorder or injury | Regulation 17 of the health and Social Care Act 2008 (Regulated Activities) Regulations 2014: Good Governance. | 1 | The provider did not hold records to demonstrate the completion of DBS checks for 24 sessional GPs (some of the GPs had worked on a sessional basis for over three years). | Issue is: Monitoring systems has either not identified or not responded to the breach of safety in security of prescriptions, completion of all recruitment checks and ensuring appropriate standards of cleanliness at the Bicester base. | The number of sessional GP's has now increased following successful recruitment since the inspecton. The service is in the process of collating all sessional GP DBS checks. As of 26 April 2017, 65% (93 out of 142 checks) were completed. Weekly progress reports are reviewed by operational managers. | Operations Manager OOH Service | A process is now in place where all checks are tracked by the human resources recruitment department; new starters cannot proceed without this in place. A new contracting mechanism has been agreed for all GP's working for the OOH service. The new GP contract mandates that all GP's have the appropriate employment checks completed. From 30 June 2017, staff who have not gone through all the contracted employment checks will not be approved for working within the service. | Clinical Director Older People Services | Policy and HR recruitment team resource | 2017-07-01 | The OOH's service provision will be maintained for service users. There is a weekly update on progress and any concerns with being able to meet the timescale and maintain a service will be escalated to the clinical director, service director and Executive Team.
|  | 2 | Six out of 124 GPs had not produced evidence of their training in safeguarding children level three. | Issue is: Monitoring systems has either not identified or not responded to the breach of safety in security of prescriptions, completion of all recruitment checks and ensuring appropriate standards of cleanliness at the Bicester base. | The Learning and Development system was updated to include all GP's with a clear matrix to identify their training requirements. Reports were then provided outlining training gaps and those who require training were contacted to complete the training or provide evidence that they have already completed training within primary care. Progress is being monitored by the operational leads on a weekly basis. | Operations Manager OOH Service/ Clinical Lead OOH | Rather than local records being kept for GP training, these were transferred to the central Learning and Development Team system for monitoring. All GPs have been contacted. A further advantage of being added to the central system is that GPs will now get automated reminders to alert them when their training is approaching expiry enabling them to make appropriate arrangements. A process has been established for those GPs who complete their own local training for them to submit certificates as evidence, then the admin team contacts the learning and development team to update their central record. The service tracks progress weekly. Compliance with safeguarding training is reported to the clinical leads meeting in Urgent & Ambulatory Care and at directorate level. The new GP contract arrangements also mandates compliance with all mandatory training. | Clinical Director Older People Services | OOH administration resource is in place alongside the existing central learning and development system. Additional training sessions will be offered to support staff to complete training. | 2017-07-31 | The OOH's service provision will be maintained for service users; if records of completed training are not provided by the oustanding GPs by 31st July 2017 this will be escalated to to the clinical director, service director and Executive Team.
|  | 3 | Systems to monitor the cleanliness of the premises had not identified inappropriate cleaning standards at two of the out of hours bases (Bicester and Oxford City). The disposable curtains in treatment rooms at the Oxford City base should have been changed at the end of September 2016 but had not been replaced. At Bicester base we found dust on the safety rails of two couches in the treatment rooms. Infection control audits we saw had identified these issues but monitoring of cleaning standards had not identified the failure to achieve appropriate standards. | Issue is: Monitoring systems has either not identified or not responded to the breach of safety in security of prescriptions, completion of all recruitment checks and ensuring appropriate standards of cleanliness at the Bicester base. | 1. The concerns identified at the Oxford base were addressed by the facilities team right away. They escalated concerns to NHS PS, who are responsible for delivering the cleaning, via contract management. 2. The issues identified at the Bicester base were also addressed by facilities via contract management; the clinical team replaced the couches and mattress and agreed a new regime for cleaning before use. 3. Both bases were inspected by clinical managers to ensure cleaning was of a good standard- alongside infection control team audits. 4. New mattresses were purchased to replace those that were possibly degrading (this is linked to the couch rail issue; the team noted this could have been black powder from the mattress as opposed to dust). 5. The cleaning schedule was altered to ensure weekend only trolleys are cleaned Friday evening or Saturday morning. | Clinical Managers OOH Service | Amendments have been made to the modern matron and clinical lead checklists to ensure they track actions highlighted in the infection prevention and control audit to completion. Adhere to the updated cleaning schedule. Estates team had several communications over the past three months with Community Health Partnership and NHS PS regarding the poor standard of cleaning being provided by contractors. A deadline was given to the contractor to improve standards otherwise a replacement company will be introduced. | Operations Manager OOH Service | Modern Matrons/Clinical Leads checks are already in place Facilities contract management is already in place | Completed with ongoing monitoring | No impact; the concerns have been addressed.
|  | 4 | Systems to manage medicines were not always operated consistently. The provider did not have a system to track blank prescriptions at five of the six out of hours bases (Henley, Witney, Banbury, Bicester and Oxford Central). The stock management process was not sufficient to identify which prescriptions had been issued to each prescriber. | Issue is: Monitoring systems has either not identified or not responded to the breach of safety in security of prescriptions, completion of all recruitment checks and ensuring appropriate standards of cleanliness at the Bicester base. | A significant event was raised in response to the initial finding relating to a gap in the sequential numbering indicating that some prescriptions could not be tracked. The necessity to comply with the Standard Operating Procedure (SOP) was communicated to staff at the time and again in February 2017. A comprehensive review of the SOP will be undertaken to determine If any technical improvements could be achieved. | Clinical Lead OOH | An audit will be undertaken to demonstrate safe management of prescriptions at all bases. | Head of Service Urgent and Ambulatory Care | Existing urgent care management and pharmacy resources will complete the review of the SOP and undertake an audit to provide assurance. | 2017-07-31 | No impact on service users as interim controls including current SOP is in place.
|  | 5 | Arrangements were in place for planning and monitoring the number of staff needed to meet patients' needs. However, these arrangements had not proven effective in 2016. The provider had experienced shortages of clinical staff since the start of 2016. The actions taken had been time consuming and staff recruitment was still being pursued at the time of inspection. Response to identified risk of failure to employ sufficient numbers of clinical staff had not been completed effectively to ensure national quality standards were achieved in a timely manner. | CQC also recognise that the Trust had taken action to manage sickness absence and to recruit staff. However, most national quality standards had not been met throughout 2016 and our discussions with both Trust officers and commissioners identified staffing shortages as the underlying reason for this. Action taken by the Trust to recruit to and manage staff rosters had not been effective in maintaining essential quality standards. | Sessional GP recruitment remains ongoing. As of April 2017, 21 GP's were interviewed and/or were going through the recruitment process; 32 new sessional GP's have started or have a first shift booked. There is a rolling nurse recruitment programme- 8 Advanced Emergency Practitioners were successfully recruited by the end of April 2017. This will increase capacity to meet clinical demands. | Operational Lead OOH | Regular workforce reporting to the Urgent and Ambulatory Services Clinical leads to include vacancies, progress with adverts/ interviews, retention and turnover rates to be implemented by end of August 2017. The service is working to implement weekly safer staffing reports which will be reported to the Trust management team by end of May 2017. | Head of Service Urgent and Ambulatory Care | Additional management resources will be required. | 2017-08-30 | There would be an impact on waiting and inability to meeting national requirements if recruitment challenges are not resolved.
|  | 6 | NQR10 Face to face assessment (urgent) - the provider had not been meeting this standard since January 2016. Data showed that since April 2016, out of 288 patients defined as in need of urgent assessment 198 (74%) had been assessed within 20 minutes when the target was 95%. | Both Trust officers and commissioners told inspectors that NQR standards had been achieved consistently until the provider experienced staff shortages. The reported NQR data showed that four key targets: NQR7 matching capacity to demand, NQR 10 face to face clinical assessment urgent and non-urgent, NQR12 face to face consultations within 2 hours had not been met throughout 2016. The NQR 12 standard of 2 hours for home visit consultation had been met on 2 occasions between April and September 2016. Actions taken by the Trust had not proven effective to meet the NQRs. No challenge was raised to the CQC re: lack of clarity around NQR11/7. | A number of work streams are underway including the roll out of electronic systems including staff performance monitoring via Adastra. This will include timely recording of observations onto the system for urgent cases as of May 2017. The service has a rolling recruitment programme for clinical staff. Performance has averaged 67% Urgent and 86% Non-Urgent across FY 16/17 improving markedly towards year end due to improved Advanced Emergency Practioners coverage to assess Walk Ins. With improved clinical engagement it was forecast that both targets would be achieved from 30th June 2017. Reinforcement of the processes in place with staff regarding the management of walk-in's and timely reviews and recording of information. | Operational Lead OOH | Weekly performance reporting and management, moved to monthly when performance achieved for 2 consecutive months | Head of Urgent and Ambulatory Care Services | Existing clinical and management resources. | 30/06/17 target will be achieved and monitored weekly to sustain performance/ take action as required | Waiting time in line with national targets will not be met unless recruitment challenges are resolved. Monthly report on access times to the Executive Team.
|  | 7 | NQR10 Face to face assessment (non-urgent) - since April 2016 there had been 3,451 contacts with patients with non-urgent needs. Of these 2,991 (87%) had received their clinical assessment within the 60 minute target. This fell short of the 95% target. |  | Performance has averaged 67% Urgent and 86% Non-Urgent across FY 16/17 improving markedly towards year end due to improved Advanced Emergency Practioners coverage to assess Walk Ins. With improved clinical engagement it was forecast that both targets would be achieved from 30th June 2017. Reinforcement of the processes in place with staff regarding the management of walk-in's and timely reviews and recording of information. | Operational Lead OOH | Weekly performance reporting and management, moved to monthly when performance achieved for 2 consecutive months | Head of Urgent and Ambulatory Care Services | Existing clinical and management resources. | 30/06/17 target will be achieved and monitored weekly to sustain performance/ take action as required | There would be an impact on waiting and inability to meeting national requirements if recruitment challenges are not resolved. Monthly report on access times to the Executive Team.
|  | 8 | Data showed that 4062 (84%) of the target 4813 shifts had been filled since January 2016. |  | Performance has averaged 87% across FY 16/17 ending the year with an improvement to 91% helped by the introduction of greater Advanced Emergency Practioners (AEP) shift working. This will be improved further once the 3 more AEPs recruited start work. Recruitment action is continuing for Emergency Practitioners (EP). Sessional GP recruitment is on-going with 69 active requests and 53 applications received of which 32 individuals have been started in shifts. On current projections it was forecast that the target will be reached by May 2017. | Operational Lead OOH | Recruitment will continue. The service is working to implement weekly safer staffing reports which will be reported to the Trust management team by end of May 2017. | Head of Urgent and Ambulatory Care Services | Existing clinical and management resources. | 2017-05-30 | There would be an impact on waiting and inability to meeting national requirements if recruitment challenges are not resolved.
|  | 9 | NQR12 Face to face consultations (urgent consultation following definitive clinical assessment to be seen within two hours at an OOH centre) - in the six months leading up to inspection the provider had achieved 82% (5,738 out of 7,000) face to face consultations at an out of hours base within two hours of assessment for those patients classified as urgent. This fell short of the 95% target. |  | Performance has averaged 81% across FY 16/17 ending the year with an improvement to 83% helped by improved staffing of the rota. While it is predicted that the resourcing position will improve and reach target from June 2017 it is not possible to accurately predict when this target will be achieved due to the challenges involved in bringing about improvements in individual GPs productivity and ways of working which will also be necessary. One to one meetings are also being held with staff to talk through how productivity can be improved. Adastra data will be used to provide individuals with feedback. | Operational Lead OOH | Weekly performance reporting and management, moved to monthly when performance achieved for 2 consecutive months | Head of Urgent and Ambulatory Care Services | Existing clinical and management resources. | 30/06/17 target will be achieved and monitored weekly to sustain performance/ take action as required | There would be an impact on waiting and inability to meeting national requirements if recruitment challenges are not resolved. Monthly report on access times to the Executive Team.
|  | 10 | NQR12 Face to face consultations(urgent consultation following definitive clinical assessment to be seen within two hours at their place of residence) - in the six months prior to inspection the provider had achieved 94% (2,202 out of 2,349) face to face consultations patients had been seen within two hours of assessment in their place of residence. The target was 95%. |  | Performance has averaged 94% across FY 16/17 just 1% shy of target. As the staffing of the rota improves towards reaching target from June 2017 it is anticipated that this will impact positively upon more achievement of this target moving forward. | Operational Lead OOH | Weekly performance reporting and management, moved to monthly when performance achieved for 2 consecutive months | Head of Urgent and Ambulatory Care Services | Existing clinical and management resources. | 30/06/17 target will be achieved and monitored weekly to sustain performance/ take action as required | There would be an impact on waiting and inability to meeting national requirements if recruitment challenges are not resolved. Monthly report on access times to the Executive Team.
|  | 11 | There was an overarching governance framework which supported the delivery of the strategy and good quality care. However this was inconsistent in monitoring arrangements to improve quality, identify, assess and manage risk. The provider must ensure governance processes and systems are consistently applied in a timely manner to assess, monitor and improve the quality and safety of the services provided. | Issue is: Monitoring systems has either not identified or not responded to the breach of safety in security of prescriptions, completion of all recruitment checks and ensuring appropriate standards of cleanliness at the Bicester base. CQC also recognise that the Trust had taken action to manage sickness absence and to recruit staff. However, most national quality standards had not been met throughout 2016 and our discussions with both Trust officers and commissioners identified staffing shortages as the underlying reason for this. Action taken by the Trust to recruit to and manage staff rosters had not been effective in maintaining essential quality standards. | A review of the governance framework was undertaken to include the following: 1. The OOH senior management meeting takes place every 4-6 weeks and receives performance and quality metric information for management. A quality metrics report (dashboard) has been developed for urgent and ambulatory care services where exceptions identified from performance, incidents and patient feedback are highlighted and discussed. 2. The OOH senior management meeting adopts a standardised agenda where all aspects of quality are reviewed to facilitate monitoring and learning. Risks that cannot be addressed timely are entered onto a risk register for the service and/or are escalated to the directorate risk register. 3. At directorate level, there is a monthly quality and performance management meeting where the quality and performance dashboards from each service are presented, exceptions are highlighted alongside proposed actions to address them. 4. The directorate performance and quality report including all exceptions/notable risks from all services is reviewed monthly at senior management team meeting which reports to the quarterly performance meetings with the Executive Team. | Head of Urgent and Ambulatory Care Services | Monthly performance and quality reporting to senior management meetings. | Clinical Director Older People Services | Existing clinical and management resources. | Completed | No impact.
|  | 12 | The service had methods for communicating with its staff. Staff were able to identify communications relating to safe and effective delivery of services. However, some staff were not clear on the provider's preferred route by which to obtain this information. Three of the staff we spoke with referred to receipt of learning either by e-mail or via Adastra (Adastra is an IT system for patient records used by OOH). This demonstrated that not all staff recognised the Trust's preferred method of communication. | Inspectors found that staff were all able to demonstrate their understanding of information of importance, e.g. significant events. However, they were not all clear by which route they should seek to find this information. The lead inspector held a follow up teleconference with senior managers of the OOH service and sought clarification on the issue of how information was communicated. Senior officers at that time confirmed that e-mails were cascaded via Adastra.(the report was amended to reflect lack of clarity) | The current bi-monthly newsletter and email communications will be maintained. A survey was completed with GPs to identify their preferred method of communication - the response was email. Feedback will be obtained from other staff groups and various methods of feedback will be formalised and communicated. Staff meetings with receptionists/drivers are being revisited and will be delivered on a quarterly basis. | Clinical Lead OOH | Face to face staff meetings are booked into the diary in advance and honoured; considerations will be made with the team regarding how communications can be improved. | Head of Urgent and Ambulatory Care Services | Existing staff resources; potential impact on time/additional pay | 2017-07-31 | No impact; service delivery will be retained
|  | 13 | Drivers and reception staff we spoke with had not received training as a chaperone. Staff could be called upon to carry out chaperone duties both at the out of hours bases and whilst on a home visit. | No direct feedback relating to chaperones | The service provides chaperones; these are predominantly clinical staff on duty. On occasions, a clinician discusses the option of delaying the appointment if non-urgent with the patient to ensure an appropriate chaperone is available. | Clinical Lead OOH | Continue to monitor feedback from patients and clinicians | Head of Nursing | Existing staff resources | Completed | No impact.
|  | 14 | During the inspection we found blood glucose meters were not being calibrated. Calibration and checking of blood glucose meters should be carried out in accordance with the manufacturer's specification at all times. |  | By the end of the inspection calibration of these devices had been introduced. 1. Appropriate books were placed with all machines soon after inspection. 2. A checking process has been introduced by clinical leads' weekly in addition to the matron checks. | OOH Modern Matrons | Clinical leads and matron checklist completion. | Operations Manager OOH Service | Existing management resource | Completed | No impact
|  | 15 | We noted the Controlled Drug order book received section had not been signed since April 2016. This did not follow Trust protocol or best practice. Ensure the controlled drugs receipt log at Oxford City base is signed when controlled drugs are received into stock. | Evidence submitted to CQC clearly shows that the receipt columns had not been completed. | The CQC comments relate to the signing of the pink copy of the controlled drug order book rather than the register itself. Staff were reminded of this requirement. Pharmacy will audit this on a quarterly basis as part of the controlled drug audit and feedback any improvements required. SOP will be reviewed and communicated to all OOH teams including GP's. | Modern Matrons | Regular pharmacy technician checks and feedback to service leads. | Operations Manager OOH Service | Existing clinical resources | 30/07/17 audit completed and SOP reviewed/ communicated | No impact
|  | 16 | The provider had a programme of training for staff to receive basic life support training, including use of an automated external defibrillator. We noted that 11 of the driver /reception staff out of 60 (the majority of non-clinical staff were employed to undertake both driver and reception roles) had not received their training at the time of inspection. |  | 1.Ensure central learning and development training records are up to date and establish receptionists/drivers who require training. 2. Liaise with resus training department and arrange appropriate training. | Unit Manager OOH | This is now included in the urgent care safety metrics for monthly local monitoring. Two training sessions have been arranged for non-clinical staff in June 2017. | Operations Manager OOH Service | Existing learning and development training resources | 2017-06-30 | Training has been delivered/ planned; there should be no adverse impact
|  | 17 | Clinical staff undertaking home visits had access to IT equipment so relevant information could be shared with them while working remotely. This equipment did not always pick up a signal in remote areas thus preventing staff from completing record entries whilst on a visit. Staff had to return to base to complete the records which took time they could have used to treat other patients. |  | Updated equipment had been ordered. This equipment was not due for delivery until early 2017. 11 new laptops have been delivered and are in use. Adastra developments are planned to improve access to special notes. | Unit Manager OOH | Encourage staff to report equipment issues and ensure these are replaced in a timely way. There are signal black spots within the area that we cover that we are unable to mitigate against. | Operations Manager OOH Service | IT resources are now in place | Complete | No impact
|  | 18 | At five of the bases conversations in consulting and treatment rooms could not be overheard. However, at the Banbury base we noted that conversations could be heard from the waiting area. |  | Plans in place to relocate in 2017/18 to a more suitable building on the Banbury site. Currently waiting for the Fiennes building plans to be published. As an interim measure clinicians instructed to use the rooms furthest away from the waiting area first and all the team were made aware of the possibility of conversations being overheard. | Unit Manager OOH | Dependent on site plans. Regular local checks to monitor whether consultations can be overheard. | Operations Manager OOH Service | Estates resources in place | Interim measure completed. | No impact
|  | 19 | Information leaflets were available at all the bases. However, the provider was limited in what could be displayed at three of the bases due to sharing facilities with other health services. |  | All information is still available in each site. Teams were asked to consider improving mechanisms for display. | Unit Manager OOH | Regular local checks. | Operations Manager OOH Service | No additional resources | 2017-05-31 | Information is available so no impact
|  | 20 | A hearing loop was only available at four of the six bases. |  | Missing hearing loops have been ordered and will be installed. | OOH Coordinators | Local checks to ensure these are functioning. | Head of Urgent and Ambulatory Care Services | Financial resource made available | 31/09/2017 | Potential poor patient experience
|  | 21 | When we inspected all six of the out of hours bases we found that signposting to the service at three (Henley, Bicester and Banbury) was not clear and that the out of hours base was not obvious to patients and their relatives. |  | Signage survey was completed; recommendations have been sent to the head of estates for submission to OUH/NHSPS. The changes need to be agreed by the organisations that host these OOH services; changes will be costed once approval has been received and the approved alterations will then be carried out. | Head of Urgent and Ambulatory Care Services | New signage will be installed once proposed changed are approved by the OUH/NHSPS. Local checks will be carried out to ensure appropriate signage. The OOH service will also monitor and address any feedback from patients/staff regarding the signage. | Head of Urgent and Ambulatory Care Services | Financial resource made available | 2017-10-31 | Potential poor patient experience
|  | 22 | During the inspection, we identified that manual records of the fridge temperature dated before 2016 did not provide assurance that medicines had been stored within the correct temperature range. The provider had identified that the fridge temperature recording system required improvement and had installed data loggers in the medicines fridges in October 2016. |  | Data loggers are in place which mitigates the concern raised prior to CQC inspection about correct temperature measures. Paper records are continuing to be used as an additional safety net. | Clinical Lead OOH | Pharmacy will monitor feedback from the data loggers, as well as the service. Overview by the clinical leads to ensure the temperatures are being monitored and this is being documented. | Head of Urgent and Ambulatory Care Services | Investment in IT solution for temperature monitoring | Complete with ongoing monitoring | No impact as safety nets are in place
Completed by:
Position(s):
Date:
Once completed send to: HSCA_Compliance@cqc.org.uk
Location name: Oxford Health NHS Foundation Trust - HQ
Location ID/Account Number: RNUHQ
Our Reference Number: INSI-1560565178
Deadline to return to Sue, Ros and Jane: Thursday 4 May 2017
Deadline to return to CQC: Monday 8 May 2017